## DAFTAR GAMBAR TOTAL
[12 empty] | TOTAL PROGRESS | TOTAL PRELIMINARY DESIGN | TOTAL INTERMIEDIATE DESIGN | TOTAL FINAL DESGIN | RESUME TOTAL PROGRESS
No | DW NUMBER | Title | Car Type | [6 empty] | STATUS | REMARKS |  |  |  |  | JENIS KERETA | TOTAL DD | RELEASE | % TOTAL | PRELIMINARY DESIGN (PDR) |  |  | INTERMEDIATE DESIGN (IDR) |  |  | FINAL DESIGN (FDR) |  |  | TOTAL PROGRESS |  |  | FDR
|  |  | TC1 | M1 | M2 | T1 | T2 | T3 | TC2 |  |  | 100% | 99.55% | 100% | 66.32% |  |  |  |  | DD TOTAL | RELEASE | %-TASE | DD TOTAL | RELEASE | %-TASE | DD TOTAL | RELEASE | %-TASE | PDR + IDR |  | 0.7 | 0.3
100%
1 | 210E1210100 | UNDERFRAME ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d |  |  |  |  | TC1 | 102 | 93 | 91.18% | 48 | 48 | 100% | 8 | 8 | 100% | 46 | 37 | 80.43% | 56 | 56 | 70%
2 | 210E1220100 | UNDERFRAME ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d |  |  |  |  | M1 | 88 | 78 | 88.64% | 36 | 36 | 100% | 6 | 6 | 100% | 46 | 37 | 80.43% | 42 | 42 | 70%
3 | 210E1230100 | UNDERFRAME ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d |  |  |  |  | M2 | 76 | 64 | 84.21% | 32 | 31 | 96.88% | 5 | 5 | 100% | 39 | 28 | 71.79% | 37 | 36 | 68.11%
4 | 210E1240100 | UNDERFRAME ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d |  |  |  |  | T1 | 75 | 63 | 84% | 30 | 30 | 100% | 2 | 2 | 100% | 43 | 31 | 72.09% | 32 | 32 | 70%
5 | 210E1250100 | UNDERFRAME ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d |  |  |  |  | T2 | 69 | 59 | 85.51% | 30 | 30 | 100% | 2 | 2 | 100% | 37 | 27 | 72.97% | 32 | 32 | 70%
6 | 210E1260100 | UNDERFRAME ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d |  |  |  |  | T3 | 65 | 34 | 52.31% | 30 | 30 | 100% | 2 | 2 | 100% | 33 | 2 | 6.061% | 32 | 32 | 70%
7 | 210E1270100 | UNDERFRAME ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d |  |  |  |  | TC2 | 102 | 93 | 91.18% | 48 | 48 | 100% | 8 | 8 | 100% | 46 | 37 | 80.43% | 56 | 56 | 70%
8 | 220E1210100 | SIDEWALL ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d | [19 empty] | 69.73% | 19.9% | 89.63%
9 | 220E1220100 | SIDEWALL ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d
10 | 220E1230100 | SIDEWALL ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d
11 | 220E1240100 | SIDEWALL ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d
12 | 220E1250100 | SIDEWALL ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d
13 | 220E1260100 | SIDEWALL ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d
14 | 220E1270100 | SIDEWALL ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
15 | 230E1210100 | ENDWALL ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d
16 | 230E1220100 | ENDWALL ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d
17 | 230E1230100 | ENDWALL ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d
18 | 230E1240100 | ENDWALL ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d
19 | 230E1250100 | ENDWALL ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d
20 | 230E1260100 | ENDWALL ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d
21 | 230E1270100 | ENDWALL ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
22 | 240E1210100 | CABIN ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d
23 | 240E1270100 | CABIN ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
24 | 230E1210100 | ROOF ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d
25 | 230E1220100 | ROOF ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d
26 | 230E1230100 | ROOF ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d
27 | 230E1240100 | ROOF ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d
28 | 230E1250100 | ROOF ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d
29 | 230E1260100 | ROOF ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d
30 | 230E1270100 | ROOF ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
1 | 210E1210200 | MAIN CONSTRUCTION OF UNDERFRAME TC1&TC2 | • | [5 empty] | • | RELEASE
2 | 210E1220200 | MAIN COSTRUCTION OF UNDERFRAME M1, M2 |  | • | • |  |  |  |  | RELEASE
3 | 210E1240200 | MAIN COSTRUCTION OF UNDERFRAME T |  |  |  | • | • | • |  | RELEASE
4 | 211E1210100 | FRONT PART ASSEMBLY | • | [5 empty] | • | RELEASE
5 | 211E1210200 | END BEAM FRONT TC | • | [5 empty] | • | RELEASE
6 | 211E1200100 | END PART ASSEMBLY | • | • | • | • | • | • | • | RELEASE
7 | 211E1200200 | END BEAM | • | • | • | • | • | • | • | RELEASE
8 | 211E1210400 | ANTI CLIMBER | • | [5 empty] | • | RELEASE
9 | 212E1200100 | BOLSTER | • | • | • | • | • | • | • | RELEASE
10 | 213E1210100 | MIDDLE PART ASSY TC | • | [5 empty] | • | RELEASE
11 | 213E1200100 | MIDDLE PART ASSY M |  | • | • |  |  |  |  | RELEASE
12 | 213K5600200 | JACKING PAD | • | • | • | • | • | • | • | RELEASE
13 | 221E1210200 | MAIN CONSTRUCTION OF SIDEWALL TC1 & TC2 | • | [5 empty] | • | RELEASE
14 | 221E1220200 | MAIN CONSTRUCTION OF SIDEWALL M1, M2 |  | • | • |  |  |  |  | RELEASE
15 | 221E1240200 | MAIN CONSTRUCTION OF SIDEWALL T |  |  |  | • | • | • | • | RELEASE
16 | 221E1200300 | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | • | • | • | • | • | • | • | RELEASE
17 | 221E1200400 | MIDDLE SIDEWALL 2 | • | • | • | • | • | • | • | RELEASE
18 | 221E1200500 | END SIDEWALL 1 --> (LEFT) | • | • | • | • | • | • | • | RELEASE
19 | 221E1200600 | END SIDEWALL 2 --> (RIGHT) |  | • | • | • | • | • |  | RELEASE
20 | 221E1200700 | PASSENGER ENTRANCE | • | • | • | • | • | • | • | RELEASE
21 | 221E1200800 | ARR GUSSET ON SIDEWALL T |  |  |  | • | • | • |  | RELEASE
22 | 221E1201000 | FRAME DOOR SUPPORT 1 | • | • | • | • | • | • | • | RELEASE
23 | 221E1201100 | FRAME DOOR SUPPORT 2 | • | • | • | • | • | • | • | RELEASE
24 | 221E1201200 | FRAME DOOR SUPPORT 2 | • | • | • | • | • | • | • | RELEASE
25 | 221E1210800 | MIDDLE SIDEWALL 3 --> (TC ONLY, SHORT LENGTH) | • | [5 empty] | • | RELEASE
26 | 221E1210900 | BEHIND CAB SIDEWALL 1 --> (LEFT) | • | [5 empty] | • | RELEASE
27 | 221E1211000 | BEHIND CAB SIDEWALL 2 --> (RIGHT) | • | [5 empty] | • | RELEASE
28 | 221E1211100 | DRIVER CAB ENTRANCE | • | [5 empty] | • | RELEASE
29 | 221E1211200 | ARR GUSSET ON SIDEWALL TC1 & TC2 | • | [5 empty] | • | RELEASE
30 | 221E1211300 | CABIN SIDEWALL 1 --> (LEFT) | • | [5 empty] | • | RELEASE
31 | 221E1211400 | CABIN SIDEWALL 2 --> (RIGHT) | • | [5 empty] | • | RELEASE
32 | 221E1211600 | END SIDEWALL 2 --> (RIGHT TC) | • | [5 empty] | • | RELEASE
33 | 221E1211700 | FRAME DOOR SUPPORT 3 --> (RIGHT TC) | • | [5 empty] | • | RELEASE
34 | 221E1211800 | FRAME DOOR SUPPORT 4 --> (LEFT TC) | • | [5 empty] | • | RELEASE
35 | 221E1220300 | MIDDLE SIDEWALL 2 --> (DUCT MOTOR) |  | • | • |  |  |  |  | RELEASE
36 | 221E1220400 | END SIDEWALL 3 --> (DUCT MOTOR) |  | • | • |  |  |  |  | RELEASE
37 | 221E1220800 | ARR GUSSET ON SIDEWALL M1,M2 |  | • | • |  |  |  |  | RELEASE
38 | 231E1200100 | MAIN CONSTRUCTION OF ENDWALL ALL | • | • | • | • | • | • | • | RELEASE
39 | 231E1200200 | END FRAMING | • | • | • | • | • | • | • | RELEASE
40 | 231E1200300 | END SHEETING | • | • | • | • | • | • | • | RELEASE
41 | 231E1200100 | MAIN CONSTRUCTION OF FRONT ENDWALL M1 |  | • | [5 empty] | RELEASE
42 | 231E1200400 | MAIN CONSTRUCTION OF REAR ENDWALL M1 |  | • | [5 empty] | RELEASE
43 | 231E1220200 | END FRAMING FRONT |  | • | [5 empty] | RELEASE
44 | 231E1220500 | END FRAMING REAR |  | • | [5 empty] | RELEASE
45 | 241E1210100 | MAIN CONSTRUCTION OF MASKARA | • | [5 empty] | • | RELEASE
46 | 241E1210400 | SHEATING MASKARA | • | [5 empty] | • | RELEASE
47 | 241E1210500 | FRAME MASKARA | • | [5 empty] | • | RELEASE
48 | 251E1210100 | MAIN CONSTRUCTION OF ROOF TC1 & TC2 | • | [5 empty] | • | RELEASE
49 | 251E1220100 | MAIN CONSTRUCTION OF ROOF M1 |  | • | [5 empty] | RELEASE
50 | 251E1200100 | MAIN CONSTRUCTION OF ROOF M2 & T |  |  | • | • | • | • |  | RELEASE
51 | 251E1210200 | ROOF FRAMING TC1 & TC2 | • | [5 empty] | • | RELEASE
52 | 251E1210300 | ROOF SHEATING TC1 & TC2 | • | [5 empty] | • | RELEASE
53 | 251E1200400 | ROOF FRAMING AC | • | • | • | • | • | • | • | RELEASE
54 | 251E1210500 | ARR GUSSET ON ROOF TC1 & TC2 | • | [5 empty] | • | RELEASE
55 | 251E1210600 | RAIN GUTTER TC1 & TC2 | • | [5 empty] | • | RELEASE
56 | 251E1220200 | ROOF FRAMING M1 |  | • | [5 empty] | RELEASE
57 | 251E1220300 | ROOF SHEATING M1 |  | • | [5 empty] | RELEASE
58 | 251E1220500 | ARR GUSSET ON ROOF M1 |  | • | [5 empty] | RELEASE
59 | 251E1220800 | ROOF FRAMING PANTOGRAPH |  | • | [5 empty] | RELEASE
60 | 251E1200200 | ROOF FRAMING M2,T |  |  | • | • | • | • |  | RELEASE
61 | 251E1200300 | ROOF SHEATING M2,T |  |  | • | • | • | • |  | RELEASE
62 | 251E1200500 | ARR GUSSET ON ROOF M2,T |  |  | • | • | • | • |  | RELEASE
63 | 251E1200600 | RAIN GUTTER M, T | • | • | • | • | • | • | • | RELEASE
63 | [9 empty] | 63 |  | 70% |  | 0.7
1 | 214E1210200 | ARRG FLOOR ON PASSENGER ROOM | • | [5 empty] | • | RELEASE
2 | 214E1210300 | ARR FLOOR PLATE ON CAB | • | [5 empty] | • | RELEASE
3 | 214E1220200 | ARRG FLOOR ON PASSENGER ROOM M1,M2 |  | • | • |  |  |  |  | RELEASE
4 | 214E1240200 | ARRG FLOOR ON PASSENGER ROOM |  |  |  | • | • | • |  | RELEASE
5 | 215E1210200 | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | • | [5 empty] | • | RELEASE
6 | 215E1210300 | BRACKET SUPPORT FLOOR ON CAB | • | [5 empty] | • | RELEASE
7 | 215E1210400 | DRAIN PIPE AND SUPPORT | • | [5 empty] | • | RELEASE
8 | 215E1210500 | TAPPING STRIP | • | [5 empty] | • | RELEASE
9 | 215E1210600 | TAPPING FOR DRIVER AND PASSENGER SEAT ON FLOOR | • | [5 empty] | • | RELEASE
10 | 215E1210700 | TAPPING FOR DOOR POCKET & INTERIOR CABINET | • | [5 empty] | • | RELEASE
11 | 215E1210800 | TAPPING FOR DRIVER DESK | • | [5 empty] | • | RELEASE
12 | 215E1220200 | BRACKET SUPPORT FLOOR ON PASSENGER ROOM |  | • | • |  |  |  |  | RELEASE
13 | 215E1220300 | DRAIN PIPE AND SUPPORT |  | • | • |  |  |  |  | RELEASE
14 | 215E1220400 | TAPPING STRIP |  | • | • |  |  |  |  | RELEASE
15 | 215E1220500 | TAPPING FOR PASSENGER SEAT ON FLOOR |  | • | • |  |  |  |  | RELEASE
16 | 215E1220600 | TAPPING FOR DOOR POCKET INTERIOR |  | • | • |  |  |  |  | RELEASE
17 | 215E1240200 | BRACKET SUPPORT FLOOR ON PASSENGER ROOM |  |  |  | • | • | • |  | RELEASE
18 | 215E1240300 | DRAIN PIPE AND SUPPORT |  |  |  | • | • | • |  | RELEASE
19 | 215E1240400 | TAPPING STRIP |  |  |  | • | • | • |  | RELEASE
20 | 215E1240500 | TAPPING FOR PASSENGER SEAT ON FLOOR |  |  |  | • | • | • |  | RELEASE
21 | 215E1240600 | TAPPING FOR DOOR POCKET INTERIOR |  |  |  | • | • | • |  | RELEASE
22 | 218E1200200 | BRACKET FOR GROUNDING INTER CAR |  | • | • | • | • | • |  | RELEASE
23 | 218E1200300 | BRACKET FOR LEVELING VALVE | • | • | • | • | • | • | • | RELEASE
24 | 218E1200400 | BRACKET FOR COUPLER SUPPORT |  | • | • | • | • | • |  | RELEASE
25 | 218E1200500 | BRACKET FOR LADDER |  | • | • | • | • | • |  | RELEASE
26 | 218E1210200 | BRACKET FOR GROUNDING INTER CAR | • | [5 empty] | • | RELEASE
27 | 218E1200300 | BRACKET FOR LEVELING VALVE | [7 empty] | RELEASE
28 | 218E1210400 | BRACKET FOR COUPLER SUPPORT | • | [5 empty] | • | RELEASE
29 | 218E1210500 | BRACKET FOR CABLE DUCT | • | [6 empty] | RELEASE
30 | 218E1210600 | BRACKET FOR PNEUMATIC PIPING | • | [6 empty] | RELEASE
31 | 218E1210700 | HOLE FOR BATTERY BOX | • | [6 empty] | RELEASE
32 | 218E1210800 | BRACKET OF RECTIFIER BOX | • | [6 empty] | RELEASE
33 | 218E1210900 | BRACKET OF ELECTRIC CONTROL PANEL | • | [6 empty] | RELEASE
34 | 218E1211000 | BRACKET FOR LADDER | • | [6 empty] | RELEASE
35 | 218E1211100 | BRACKET OF AUX SWITCH | • | [6 empty] | RELEASE
36 | 218E1211400 | BRACKET OF AIR RESERVOIR | • | [6 empty] | RELEASE
37 | 218E1211500 | BRACKET OF TRANSFORMER FILTER BOX | • | [6 empty] | RELEASE
38 | 218E1211600 | BRACKET OF COWCATCHER | • | [6 empty] | RELEASE
39 | 218E1211700 | BRACKET OF JUNCTION COUPLER ELECTRIC | • | [6 empty] | RELEASE
40 | 218E1211800 | BRACKET OF PNEUMATIC HORN MODULE | • | [6 empty] | RELEASE
41 | 218E1211900 | BRACKET OF APS BOX | • | [6 empty] | RELEASE
42 | 218E1212000 | BRACKET OF IVHB | • | [6 empty] | RELEASE
43 | 218E1212200 | HOLE FOR BRAKE CONTROL UNIT | • | [6 empty] | RELEASE
44 | 218E1212300 | BRACKET OF HGS (GROUND SWITCH) | • | [6 empty] | RELEASE
45 | 218E1212400 | BRACKET OF GROUNDING PLATE | • | [6 empty] | RELEASE
46 | 218E1212500 | CABLE DIRECTOR ON UNDERFRAME | • | [6 empty] | RELEASE
47 | 218E1220600 | BRACKET VVVF |  | • | • |  |  |  |  | RELEASE
48 | 218E1220700 | BRACKET ELECTRIC CONTROL PANEL |  | • | • |  |  |  |  | RELEASE
49 | 218E1220800 | BRACKET BRAKE RESISTOR |  | • | • |  |  |  |  | RELEASE
50 | 218E1220900 | BRACKET CHOPPER BOX |  | • | • |  |  |  |  | RELEASE
51 | 218E1221000 | BRACKET CHOPPER REACTOR |  | • | • |  |  |  |  | RELEASE
52 | 218E1221100 | BRACKET OF AIR RESEVOIR (100L) |  | • | • |  |  |  |  | RELEASE
53 | 218E1221200 | BRACKET OF BRACKET CONTROL MODULE |  | • | • |  |  |  |  | RELEASE
54 | 218E1221300 | BRACKET FOR CABLE DUCT |  | • | • |  |  |  |  | RELEASE
55 | 218E1221400 | BRACKET FOR PNEUMATIC PIPING |  | • | • |  |  |  |  | RELEASE
56 | 218E1221500 | BRACKET MAIN SWITCH |  | • | [5 empty] | RELEASE
57 | 218E1221600 | BRACKET FILTER REACTOR |  | • | [5 empty] | RELEASE
58 | 218E1221700 | BRACKET HSCB BOX |  | • | [5 empty] | RELEASE
59 | 218E1221800 | BRACKET JUNCTION COUPLER ELECTRIC |  | • | [5 empty] | RELEASE
60 | 218E1221900 | BRACKET OF PANTOGRAPH CONTROL MODULE |  | • | [5 empty] | RELEASE
61 | 218E1222000 | BRACKET OF PANTOGRAPH DISCONNECTOR SWITCH |  | • | [5 empty] | RELEASE
62 | 218E1222100 | BRACKET OF BUS FUSE |  | • | [5 empty] | RELEASE
63 | 218E1222400 | BRACKET OF GROUNDING PLATE |  | • | [5 empty] | RELEASE
64 | 218E1222500 | CABLE DIRECTOR ON UNDERFRAME |  | • | [5 empty] | RELEASE
65 | 218E1231500 | BRACKET AIR RESEVOIR (150L) |  |  | • |  |  |  |  | RELEASE
66 | 218E1231600 | BRACKET OF FILTER REACTOR |  |  | • |  |  |  |  | RELEASE
67 | 218E1231700 | BRACKET OF COMPRESSOR |  |  | • |  |  |  |  | RELEASE
68 | 218E1231800 | BRACKET OF COMPRESSOR CONTROL PANEL |  |  | • |  |  |  |  | RELEASE
69 | 218E1231900 | BRACKET OF EXPANSION BOX |  |  | • |  |  |  |  | RELEASE
70 | 218E1232200 | BRACKET OF GROUNDING PLATE |  |  | • |  |  |  |  | RELEASE
71 | 218E1232300 | CABLE DIRECTOR ON UNDERFRAME |  |  | • |  |  |  |  | RELEASE
72 | 218E1240600 | BRACKET OF ELECTRIC CONTROL PANEL |  |  |  | • | • | • |  | RELEASE
73 | 218E1240700 | BRACKET OF BRAKE CONTROL MODUL |  |  |  | • | • | • |  | RELEASE
74 | 218E1240800 | BRACKET OF AIR RESEVOIR (100L) |  |  |  | • | • | • |  | RELEASE
75 | 218E1241000 | BRACKET OF CABLE DUCTING |  |  |  | • | • | • |  | RELEASE
76 | 218E1241100 | BRACKET OF PNEUMATIC PIPING |  |  |  | • | • | • |  | RELEASE
77 | 218E1241200 | BRACKET OF TRANSFORMER FILTER BOX |  |  |  | • |  |  |  | RELEASE
78 | 218E1241300 | BRACKET OF APS BOX |  |  |  | • |  |  |  | RELEASE
79 | 218E1241400 | BRACKET OF RECTIFIER BOX |  |  |  | • |  |  |  | RELEASE
80 | 218E1241500 | BRACKET OF AUXILIARY SWITCH |  |  |  | • |  |  |  | RELEASE
81 | 218E1241600 | BRACKET OF IVHB |  |  |  | • |  |  |  | RELEASE
82 | 218E1241700 | BRACKET OF BATTERY BOX |  |  |  | • |  |  |  | RELEASE
83 | 218E1241800 | BRACKET OF BATTERY PANEL |  |  |  | • |  |  |  | RELEASE
84 | 218E1241900 | BRACKET OF HGS (GROUND SWITCH) |  |  |  | • |  |  |  | RELEASE
85 | 218E1242000 | BRACKET OF EXPANSION BOX |  |  |  | • |  |  |  | RELEASE
86 | 218E1242200 | BRACKET OF GROUNDING PLATE |  |  |  | • |  |  |  | RELEASE
87 | 218E1242300 | CABLE DIRECTOR ON UNDERFRAME |  |  |  | • |  |  |  | RELEASE
88 | 218E1251200 | BRACKET OF COMPRESSOR CONTROL PANEL |  |  |  |  | • |  |  | RELEASE
89 | 218E1251300 | BRACKET OF AIR RESEVOIR (150L) |  |  |  |  | • |  |  | RELEASE
90 | 218E1251400 | BRACKET OF COMPRESSOR |  |  |  |  | • |  |  | RELEASE
91 | 218E1251600 | BRACKET OF GROUNDING PLATE |  |  |  |  | • |  |  | RELEASE
92 | 218E1251700 | CABLE DIRECTOR ON UNDERFRAME |  |  |  |  | • |  |  | RELEASE
93 | 218E1261200 | BRACKET OF GROUNDING PLATE | [5 empty] | • |  | RELEASE
94 | 218E1261300 | CABLE DIRECTOR ON UNDERFRAME | [5 empty] | • |  | RELEASE
95 | 218E1270500 | BRACKET FOR CABLE DUCT | [6 empty] | • | RELEASE
96 | 218E1270600 | BRACKET FOR PNEUMATIC PIPING | [6 empty] | • | RELEASE
97 | 218E1270700 | BRACKET OF BATTERY BOX | [6 empty] | • | RELEASE
98 | 218E1270800 | BRACKET OF RECTIFIER BOX | [6 empty] | • | RELEASE
99 | 218E1270900 | BRACKET OF ELECTRIC CONTROL PANEL | [6 empty] | • | RELEASE
100 | 218E1271000 | BRACKET FOR LADDER | [6 empty] | • | RELEASE
101 | 218E1271100 | BRACKET OF AUX SWITCH | [6 empty] | • | RELEASE
102 | 218E1271400 | BRACKET OF AIR RESERVOIR | [6 empty] | • | RELEASE
103 | 218E1271500 | BRACKET OF TRANSFORMER FILTER BOX | [6 empty] | • | RELEASE
104 | 218E1271600 | BRACKET OF COWCATCHER | [6 empty] | • | RELEASE
105 | 218E1271700 | BRACKET OF JUNCTION COUPLER ELECTRIC | [6 empty] | • | RELEASE
106 | 218E1271800 | BRACKET OF PNEUMATIC HORN MODULE | [6 empty] | • | RELEASE
107 | 218E1271900 | BRACKET OF APS BOX | [6 empty] | • | RELEASE
108 | 218E1272000 | BRACKET OF IVHB | [6 empty] | • | RELEASE
109 | 218E1272100 | BRACKET OF BATTERY PANEL | [6 empty] | • | RELEASE
110 | 218E1272200 | BRAKE OF CONTROL MODULE | [6 empty] | • | RELEASE
111 | 218E1272300 | BRACKET OF HGS (GROUND SWITCH) | [6 empty] | • | RELEASE
112 | 218E1272400 | BRACKET OF GROUNDING PLATE | [6 empty] | • | RELEASE
113 | 218E1272500 | CABLE DIRECTOR ON UNDERFRAME | [6 empty] | • | RELEASE
114 | 228E1210200 | ARRANGEMENT ADAPTER ON SIDEWALL | • | [5 empty] | • | RELEASE
115 | 228E1210300 | BRACKET FOR CURTAIN | • | [5 empty] | • | RELEASE
116 | 228E1210400 | BRACKET FOR DOOR ENGINE ENTRANCE | • | [5 empty] | • | RELEASE
117 | 228E1210500 | BRACKET FOR LUGGAGE RACK | • | [5 empty] | • | RELEASE
118 | 228E1210600 | BRACKET EMERGENCY DOOR RELEASE | • | [5 empty] | • | RELEASE
119 | 228E1211000 | BRACKET FOR GUTTER PIPE AT CABIN | • | [5 empty] | • | RELEASE
120 | 228E1220200 | ARRANGEMENT OF ADAPTER ON SIDEWALL |  | • | • |  |  |  |  | RELEASE
121 | 228E1200300 | BRACKET FOR CURTAIN |  | • | • | • | • | • |  | RELEASE
122 | 228E1200400 | BRACKET FOR DOOR ENGINE ENTRANCE |  | • | • | • | • | • |  | RELEASE
123 | 228E1200500 | BRACKET FOR LUGGAGE RACK |  | • | • | • | • | • |  | RELEASE
124 | 228E1200600 | BRACKET FOR EMERGENCY DOOR RELEASE |  | • | • | • | • | • |  | RELEASE
125 | 228E1200700 | BRACKET FOR RUNNING TEXT | • | • | • | • | • | • | • | RELEASE
126 | 228E1200800 | BRACKET FOR AC PANEL | • | • | • | • | • | • | • | RELEASE
127 | 228E1200900 | BRACKET FOR FOLDING SEAT | • | • | • | • | • | • | • | RELEASE
128 | 228E1201000 | BRACKET FOR INTERIOR PANEL FRONT END |  | • | • | • | • | • |  | RELEASE
129 | 228E1240200 | ARRANGEMENT OF ADAPTER ON SIDEWALL |  |  |  | • | • | • |  | RELEASE
130 | 238E1210200 | ARRANGEMENT ADAPTER ON ENDWALL | • | [5 empty] | • | RELEASE
131 | 238E1210300 | BRACKET FOR DOOR CLOSER | • | [5 empty] | • | RELEASE
132 | 238E1210400 | BRACKET ENDWALL PANEL | • | [5 empty] | • | RELEASE
133 | 238E1210500 | DIRECTOR CABLE ON ON ENDWALL | • | [5 empty] | • | RELEASE
134 | 238E1210600 | BRACKET OF FALLING PROTECTOR | • | [5 empty] | • | RELEASE
135 | 238E1220200 | ARRANGEMENT ADAPTER ON ENDWALL |  | • | [5 empty] | RELEASE
136 | 238E1220300 | BRACKET FOR DOOR CLOSER |  | • | [5 empty] | RELEASE
137 | 238E1220400 | BRACKET ENDWALL PANEL |  | • | [5 empty] | RELEASE
138 | 238E1200200 | ARRANGEMENT ADAPTER ON ENDWALL |  |  | • | • | • | • |  | RELEASE
139 | 238E1200300 | BRACKET FOR DOOR CLOSER |  |  | • | • | • | • |  | RELEASE
140 | 238E1200400 | BRACKET ENDWALL PANEL |  |  | • | • | • | • |  | RELEASE
141 | 238E1200500 | DIRECTOR CABLE ON ON ENDWALL |  |  | • | • | • | • |  | RELEASE
142 | 238E1200600 | BRACKET OF FALLING PROTECTOR |  |  | • | • | • | • |  | RELEASE
143 | 238E1220600 | BRACKET OF FALLING PROTECTOR |  | • | [5 empty] | RELEASE
144 | 238E1220700 | BRACKET FOR CABLE AND PIPE PANTOGRAPH |  | • | [5 empty] | RELEASE
145 | 245E1210200 | CEILING FRAME ON CAB | • | [5 empty] | • | RELEASE
146 | 245E1210300 | DIRECTOR CABLE ON CEILING FRAME CAB | • | [5 empty] | • | RELEASE
147 | 248E1210200 | INTERIOR LINNING FRAME ON CAB | • | [5 empty] | • | RELEASE
148 | 248E1210300 | DIRECTOR CABLE ON CAB | • | [5 empty] | • | RELEASE
149 | 255E1210200 | CEILING FRAME PASSENGER ROOM (DUCTING+HANDGRIP) | • | [5 empty] | • | RELEASE
150 | 255E1220200 | CEILING FRAME PASSANGER ROOM (DUCTING+HANDGRIP) |  | • | [5 empty] | RELEASE
151 | 255E1200200 | CEILLING FRAMING PASSENGER ROOM (T) |  |  | • | • | • | • |  | RELEASE
152 | 258E1210200 | ARRANGEMENT ADAPTER ON ROOF | • | [5 empty] | • | RELEASE
153 | 258E1210300 | CABLE DIRECTOR ON ROOF | • | [5 empty] | • | RELEASE
154 | 258E1200400 | BRACKET FOR EXTERIOR SPEAKER | • | • | • | • | • | • | • | RELEASE
155 | 258E1210500 | BRACKET FOR DOOR POCKET | [7 empty] | RELEASE
156 | 258E1210600 | BRACKET FOR ELECTRICAL CABINET PANEL | [7 empty] | RELEASE
157 | 258E1200700 | BRACKET FOR DOOR CONTROL UNIT | • | • | • | • | • | • | • | RELEASE
158 | 258E1210800 | BRACKET AND PIPE FOR CABLE ANTENNA | [7 empty] | RELEASE
159 | 258E1220200 | ARRANGEMENT ADAPTER ON ROOF |  | • | [5 empty] | RELEASE
160 | 258E1220300 | CABLE DIRECTOR ON ROOF |  | • | [5 empty] | RELEASE
161 | 258E1220500 | BRACKET FOR DOOR POCKET |  | • | [5 empty] | RELEASE
162 | 258E1200600 | BRACKET FOR ELECTRICAL CABINET PANEL ON ENDWALL |  | • | [5 empty] | RELEASE
163 | 258E1220700 | BRACKET FOR DOOR CONTROL UNIT |  | • | [5 empty] | RELEASE
164 | 258E1220800 | BRACKET OF SURGE ARRESTER |  | • | [5 empty] | RELEASE
165 | 258E1200200 | ARRANGEMENT ADAPTER ON ROOF | [7 empty] | RELEASE
166 | 258E1200500 | BRACKET FOR DOOR POCKET | [7 empty] | RELEASE
166 | [9 empty] | 166 |  | 30% |  | 0.3
229 | [9 empty] | 229 |  | 100%

## TC1 (E121)
[17 empty] | Project |  | : 16 TS KRL KCI (E12) | [5 empty] | WEIGHT LIMIT (KG) : |  | 8000 | [8 empty] | JUMLAH |  | %-TASE
[9 empty] | TREE DIAGRAM & | [7 empty] | Document Number |  | : 201-TDD-H1005MB051-23 | [5 empty] | WEIGHT EST. (KG) |  | 9583.61 | [8 empty] | DRAWING | RELEASE
[9 empty] | WEIGHT CALCULATION | [7 empty] | Date of Issue |  | : JANUARI 2023 | [5 empty] | PROGRESS TOTAL |  | 85.52% | [7 empty] | PDR | 48 | 48 | 100%
[9 empty] | TC1 | [7 empty] | Revision |  | : 0 | [15 empty] | IDR | 8 | 8 | 100%
[17 empty] | Page |  | : | [15 empty] | FDR | 46 | 30 | 65.22%
[17 empty] | Car Type |  | : TC1 | [16 empty] | 102 | 86
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK | WEIGHT EST. (KG) | Tanggal Release Drw | Update Berat | WEIGHT EST. (KG) |  |  | MONITORING |  | REDUCE |  | TAHAPAN DESAIN |  |  | OUTPUT TP
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7 | WEIGHT | SELISIH | WEIGHT | SELISIH |  |  |  | MD | PI | PT | FC | FP | ETC.
1 | 201-BRM-H1005MB051-23 | [7 empty] | BOM RAW MATERIAL |  | • | • | • | • | • | • | [5 empty] | RELEASE
2 | 203-BRM-H1005MB051-23 | [7 empty] | BOM PIECE PART |  | • | • | • | • | • | • | [5 empty] | RELEASE
3 | 000E1210100 | [7 empty] | GA TEC E12 KCI 2022 |  | •
4 |  | 000E1202000 | [6 empty] | TRAILLER BOGIE ASSEMBLY |  | •
5 |  | 002E1210200 | [6 empty] | CARBODY SET (TC1) | 1 | •
6 |  |  | 200E1210100 | [5 empty] | CARBODY SHEEL (TC1) | 1 | •
7 |  |  |  | 210E1210100 |  |  |  |  | UNDERFRAME ARRANGEMENT (TC1) | 1 | • | [13 empty] | 5322.51 | [18 empty] | SIMULASI | TIMBANG | SELISIH
8 |  |  |  |  | 210E1210200 |  |  |  | MAIN CONSTRUCTION OF UNDERFRAME TC1&TC2 | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  | air supply uda update |  | 2023-09-12 | 2024-04-29 | 4570 | [6 empty] | PDR | RELEASE | [7 empty] | 4937.3 | 5051 | 113.7
9 | [5 empty] | 211E1210100 |  |  | FRONT PART ASSEMBLY | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2023-11-04 |  | 1513.7 | 222 |  |  |  |  | PDR | RELEASE
10 | [6 empty] | 211E1210200 |  | END BEAM FRONT TC | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2023-11-04 |  |  | 500 |  |  |  |  | PDR | RELEASE
11 | [6 empty] | 212E1200100 |  | BOLSTER | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE | [7 empty] | 791.7 |  |  |  |  | PDR | RELEASE
12 | [5 empty] | 211E1200100 |  |  | END PART ASSEMBLY | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2023-11-01 |  | 1471 | 234 |  |  |  |  | PDR | RELEASE
13 | [6 empty] | 211E1200200 |  | END BEAM | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2023-11-01 |  |  | 461.5 |  |  |  |  | PDR | RELEASE
14 | [6 empty] | 212E1200100 |  | BOLSTER | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  | BUTUH REVISI | [5 empty] | 791.7 |  |  |  |  | PDR | RELEASE
15 | [5 empty] | 211E1210300 |  |  | ANTI CLIMBER 01 | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2023-11-01 |  | 156 | [5 empty] | PDR | RELEASE
16 | [5 empty] | 211E1200300 |  |  | ANTI CLIMBER 02 | 2 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2023-11-01 |  | 20 | 10 |  |  |  |  | PDR | RELEASE
17 | [5 empty] | 213E1210100 |  |  | MIDDLE PART ASSY | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2023-11-04 |  | 1322.6 | [5 empty] | PDR | RELEASE
18 | [5 empty] | 213E1210200 |  |  | BACKING MIDDLE PART ASSY | 1 | • | [5 empty] | RELEASE | RELEASE |  |  |  | RELEASE |  | BUTUH REVISI |  |  |  |  | 181.4 | [5 empty] | PDR | RELEASE
19 | [5 empty] | 213K5600200 |  |  | JACKING PAD | 4 | • | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [6 empty] | 21.6 | 5.4 |  |  |  |  | PDR | RELEASE
20 |  |  |  |  | 214E1210100 |  |  |  | FLOOR CONSTRUCTION TC1 & TC2 | 1 | • | [15 empty] | 2024-04-29 | 336 | [7 empty] | 0
21 | [5 empty] | 214E1210200 |  |  | ARRG FLOOR ON PASSENGER ROOM | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | CANDRA | RELEASE | [12 empty] | PDR | RELEASE
22 | [5 empty] | 214E1210300 |  |  | ARR FLOOR PLATE ON CAB | 1 | • | [5 empty] | RELEASE | RELEASE |  |  | CANDRA | RELEASE | [12 empty] | PDR | RELEASE
23 |  |  |  |  | 215E1210100 |  |  |  | ARR SUPORTING FRAME FOR FLOOR TC1 & TC2 | 1 | • | [15 empty] | 2024-04-29 | 246.23 | [7 empty] | 0
24 | [5 empty] | 215E1210200 |  |  | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | CANDRA | RELEASE |  | BUTUH REVISI |  |  |  |  | 46.1 |  | 214.93 |  |  |  | PDR | RELEASE
25 | [5 empty] | 215E1210300 |  |  | BRACKET SUPPORT FLOOR ON CAB | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | CANDRA | RELEASE |  | BUTUH REVISI |  |  |  |  | 21.23 | [5 empty] | PDR | RELEASE
26 | [5 empty] | 215E1210400 |  |  | DRAIN PIPE AND SUPPORT | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | CANDRA | RELEASE |  | BUTUH REVISI |  |  |  |  | 85.6 | [5 empty] | PDR | RELEASE
27 | [5 empty] | 215E1210500 |  |  | TAPPING STRIP | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | CANDRA | RELEASE |  |  |  |  | 2023-12-08 |  | 31.3 | [5 empty] | PDR | RELEASE
28 | [5 empty] | 215E1210600 |  |  | TAPPING FOR DRIVER AND PASSENGER SEAT ON FLOOR | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | IFA | RELEASE | [6 empty] | 31 | [5 empty] | IDR | RELEASE
29 | [5 empty] | 215E1210700 |  |  | TAPPING FOR DOOR POCKET & INTERIOR CABINET | 1 | • | [5 empty] | RELEASE | RELEASE |  |  | IFA | RELEASE | [6 empty] | 27 | [5 empty] | IDR | RELEASE
30 | [5 empty] | 215E1210800 |  |  | TAPPING FOR DRIVER DESK | 1 | • | [5 empty] | RELEASE | RELEASE |  |  | IFA | RELEASE |  | SIAP RELEASE |  |  |  |  | 4 | [5 empty] | IDR | RELEASE
31 | [5 empty] | 215E1210900 |  |  | HOLE FOR DRAIN SUPPORT | 1 | [6 empty] | RELEASE | RELEASE |  |  | CANDRA | RELEASE |  | BUTUH REVISI | [10 empty] | IDR | RELEASE
32 |  |  |  |  | 218E1210100 |  |  |  | ARRANGEMENT BRACKET & FRAME ON U/F TC1 | 1 | • | [16 empty] | 170.28 |  |  | 170.28 |  |  |  |  | 0
33 | [5 empty] | 218E1210200 |  |  | BRACKET FOR GROUNDING INTER CAR | 1 | • | [9 empty] | HADI | FOR REVIEW |  | INPUTAN BELUM FIX | [10 empty] | FDR | FOR REVIEW
34 | [5 empty] | 218E1200300 |  |  | BRACKET FOR LEVELING VALVE | 1 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ | IFA | RELEASE | [6 empty] | 1.7 | [5 empty] | FDR | RELEASE
35 | [5 empty] | 218E1210400 |  |  | BRACKET FOR COUPLER SUPPORT | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  |  | HADI | RELEASE | [6 empty] | 22.2 | [5 empty] | IDR | RELEASE
36 | [5 empty] | 218E1210500 |  |  | BRACKET FOR CABLE DUCT | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  |  | KAFI | FOR REVIEW |  | BUTUH CEK |  |  |  |  | 31.9 | [5 empty] | FDR | FOR REVIEW
37 | [5 empty] | 218E1210600 |  |  | BRACKET FOR PNEUMATIC PIPING | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  |  | KAFI | FOR REVIEW |  | BUTUH CEK |  |  |  |  | 16.5 | [5 empty] | FDR | FOR REVIEW
38 | [5 empty] | 218E1210700 |  |  | HOLE FOR BATTERY BOX | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  | √ | HADI | FOR REVIEW |  | 30.1-E12108 |  |  |  |  | 1.8 | [5 empty] | FDR | FOR REVIEW
39 | [5 empty] | 218E1210800 |  |  | BRACKET OF RECTIFIER BOX | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12112 |  |  |  |  | 4.3 | [5 empty] | FDR | RELEASE
40 | [5 empty] | 218E1210900 |  |  | BRACKET OF ELECTRIC CONTROL PANEL | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  |  | KAFI | RELEASE |  | 30.1-E12113 |  |  |  |  | 3.8 | [5 empty] | FDR | RELEASE
41 | [5 empty] | 218E1211000 |  |  | BRACKET FOR LADDER | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  | KAFI | RELEASE | [6 empty] | 2.3 | [5 empty] | FDR | RELEASE
42 | [5 empty] | 218E1211100 |  |  | BRACKET OF AUX SWITCH | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12110 |  |  |  |  | 0.9 | [5 empty] | FDR | RELEASE
43 | [5 empty] | 218E1211200 |  |  | BRACKET OF TERMINAL BOX | 1 | • | [12 empty] | INPUTAN BELUM FIX |  |  |  |  | 0 | [5 empty] | FDR | 0
44 | [5 empty] | 218E1211300 |  |  | BRACKET OF LGS (GROUND SWITCH) | 1 | • | [12 empty] | SUDAH INCLUDE DI ELEC PANEL | [10 empty] | FDR | 0
45 | [5 empty] | 218E1211400 |  |  | BRACKET OF AIR RESERVOIR | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12104 |  |  |  |  | 14.78 | [5 empty] | FDR | RELEASE
46 | [5 empty] | 218E1211500 |  |  | BRACKET OF TRANSFORMER FILTER BOX | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  |  | HADI | RELEASE |  | 30.1-E12107 |  |  |  |  | 31 | [5 empty] | FDR | RELEASE
47 | [5 empty] | 218E1211600 |  |  | BRACKET OF COWCATCHER | 1 | • | [9 empty] | INDRA | WORKING |  | 30.1-E12105 |  |  |  |  | 2 | [5 empty] | FDR | WORKING
48 | [5 empty] | 218E1211700 |  |  | BRACKET OF JUNCTION COUPLER ELECTRIC | 1 | • | [12 empty] | INPUTAN BELUM FIX |  |  |  |  | 2 | [5 empty] | FDR | 0
49 | [5 empty] | 218E1211800 |  |  | BRACKET OF PNEUMATIC HORN MODULE | 1 | • | [9 empty] | HADI | FOR REVIEW |  | REF. 30.1-E12117 |  |  |  |  | 5 | [5 empty] | FDR | FOR REVIEW
50 | [5 empty] | 218E1211900 |  |  | BRACKET OF APS BOX | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12106 |  |  |  |  | 10.3 | [5 empty] | FDR | RELEASE
51 | [5 empty] | 218E1212000 |  |  | BRACKET OF IVHB | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | YOGI | RELEASE |  | 30.1-E12111 |  |  |  |  | 4 | [5 empty] | FDR | RELEASE
52 | [5 empty] | 218E1212100 |  |  | HOLE FOR BATTERY CONTROL PANEL | 1 | • | [5 empty] | WORKING | WORKING |  |  | HADI |  |  | SUDAH INCLUDE DI ELEC PANEL | [10 empty] | FDR | 0
53 | [5 empty] | 218E1212200 |  |  | HOLE FOR BRAKE CONTROL UNIT | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  | KAFI | RELEASE |  | 30.1-E12103 | [10 empty] | FDR | RELEASE
54 | [5 empty] | 218E1212300 |  |  | BRACKET OF HGS (GROUND SWITCH) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | IFA | REVISI |  | CEK FEM |  |  |  |  | 3.8 | [5 empty] | FDR | REVISI
55 | [5 empty] | 218E1212400 |  |  | BRACKET OF GROUNDING PLATE | 1 | • | [9 empty] | BOY | FOR REVIEW | [6 empty] | 5 | [5 empty] | FDR | FOR REVIEW
56 | [5 empty] | 218E1212500 |  |  | CABLE DIRECTOR ON UNDERFRAME | 1 | • | [9 empty] | INDRA | FOR REVIEW |  | INPUTAN BELUM FIX |  |  |  |  | 7 | [5 empty] | FDR | FOR REVIEW
57 |  |  |  | 220E1210100 |  |  |  |  | SIDEWALL ARRANGEMENT TC1 & TC2 | 1 | • | [13 empty] | 2076.7 | [10 empty] | 0 | [7 empty] | 1927 | 1820 | -107
58 |  |  |  |  | 221E1210200 |  |  |  | MAIN CONSTRUCTION OF SIDEWALL TC1 & TC2 | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE |  |  |  |  | 2024-04-29 | 1824 |  |  | 45182 |  |  |  | PDR | RELEASE
59 | [5 empty] | 221E1200300 |  |  | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | 2 | • |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 248 | 124 | 45182 |  |  |  | PDR | RELEASE
60 | [5 empty] | 221E1200400 |  |  | MIDDLE SIDEWALL 2 | 2 | • |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 248 | 124 | 45182 |  |  |  | PDR | RELEASE
61 | [5 empty] | 221E1200500 |  |  | END SIDEWALL 1 --> (LEFT) | 1 | • |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 72.1 | 72.1 | 45182 |  |  |  | PDR | RELEASE
62 | [5 empty] | 221E1200700 |  |  | PASSENGER ENTRANCE | 8 | • |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 464.8 | 58.1 | 45182 |  |  |  | PDR | RELEASE
63 | [5 empty] | 221E1201000 |  |  | FRAME DOOR SUPPORT 1 | 2 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 40 | 20 | 45182 |  |  |  | PDR | RELEASE
64 | [5 empty] | 221E1201100 |  |  | FRAME DOOR SUPPORT 2 | 2 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 39.8 | 19.9 | 45182 |  |  |  | PDR | RELEASE
65 | [5 empty] | 221E1201200 |  |  | FRAME DOOR SUPPORT 3 --> (RIGHT TC) | 2 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 39.8 | 19.9 | 45182 |  |  |  | PDR | RELEASE
66 | [5 empty] | 221E1210800 |  |  | MIDDLE SIDEWALL 3 --> (TC ONLY, SHORT LENGTH) | 2 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 166.8 | 83.4 | 45182 |  |  |  | PDR | RELEASE
67 | [5 empty] | 221E1210900 |  |  | BEHIND CAB SIDEWALL 1 --> (LEFT) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 37.4 | 37.4 | 45182 |  |  |  | PDR | RELEASE
68 | [5 empty] | 221E1211000 |  |  | BEHIND CAB SIDEWALL 2 --> (RIGHT) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 37.4 | 37.4 | 45182 |  |  |  | PDR | RELEASE
69 | [5 empty] | 221E1211100 |  |  | DRIVER CAB ENTRANCE | 2 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 137.2 | 68.6 | 45182 |  |  |  | PDR | RELEASE
70 | [5 empty] | 221E1211200 |  |  | ARR GUSSET ON SIDEWALL TC1 & TC2 | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [6 empty] | 68.1 | 68.1 | 45182 |  |  |  | PDR | RELEASE
71 | [5 empty] | 221E1211300 |  |  | CABIN SIDEWALL 1 --> (LEFT) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 53.6 | 53.6 | 45182 |  |  |  | PDR | RELEASE
72 | [5 empty] | 221E1211400 |  |  | CABIN SIDEWALL 2 --> (RIGHT) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 53.6 | 53.6 | 45182 |  |  |  | PDR | RELEASE
73 | [5 empty] | 221E1211600 |  |  | END SIDEWALL 2 --> (RIGHT TC) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 72.1 | 72.1 | 45182 |  |  |  | PDR | RELEASE
74 | [5 empty] | 221E1211700 |  |  | FRAME DOOR SUPPORT 4 --> (RIGHT TC) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 19.9 | 19.9 | 45182 |  |  |  | PDR | RELEASE
75 | [5 empty] | 221E1211800 |  |  | FRAME DOOR SUPPORT 5 --> (LEFT TC) | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ |  | RELEASE | [6 empty] | 19.9 | 19.9 | 45182 |  |  |  | PDR | RELEASE
76 |  |  |  |  | 228E1210100 |  |  |  | ARR BRACKET ON SIDE WALL TC1 & TC2 | 1 | • | [8 empty] | √ | [6 empty] | 2024-04-29 | 252.7 | [7 empty] | 0
77 | [5 empty] | 228E1210200 |  |  | ARRANGEMENT ADAPTER ON SIDEWALL | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | DICKY | RELEASE | [6 empty] | 19.8 |  | 155 |  |  |  | IDR | RELEASE
78 | [5 empty] | 228E1210300 |  |  | BRACKET FOR CURTAIN | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | DICKY | RELEASE | [6 empty] | 10.5 | [5 empty] | FDR | RELEASE
79 | [5 empty] | 228E1210400 |  |  | BRACKET FOR DOOR ENGINE ENTRANCE | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | CANDRA | RELEASE | [6 empty] | 83.2 | [5 empty] | FDR | RELEASE
80 | [5 empty] | 228E1210500 |  |  | BRACKET FOR LUGGAGE RACK | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | DICKY | RELEASE | [6 empty] | 88.3 | [5 empty] | FDR | RELEASE
81 | [5 empty] | 228E1210600 |  |  | BRACKET EMERGENCY DOOR RELEASE | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  | √ | CANDRA | RELEASE |  | BUTUH CEK |  |  |  |  | 3.1 | [5 empty] | FDR | RELEASE
82 | [5 empty] | 228E1200700 |  |  | BRACKET FOR RUNNING TEXT | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | CANDRA | RELEASE | [6 empty] | 5.2 | [5 empty] | FDR | RELEASE
83 | [5 empty] | 228E1200800 |  |  | BRACKET FOR AC PANEL | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  |  | DICKY | FOR REVIEW |  | BUTUH CEK |  |  |  |  | 0 | [5 empty] | FDR | FOR REVIEW
84 | [5 empty] | 228E1200900 |  |  | BRACKET FOR FOLDING SEAT | 1 | • | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  | √ | dicky | RELEASE | [6 empty] | 42 | [5 empty] | FDR | RELEASE
85 | [5 empty] | 228E1211000 |  |  | BRACKET FOR GUTTER PIPE AT CABIN | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  | √ | IFA | RELEASE |  | BUTUH REVISI |  |  |  |  | 0.6 | [5 empty] | FDR | RELEASE
86 | [5 empty] | 228E1201100 |  |  | BRACKET FOR ROLL FILTER PANEL |  |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  | DICKY | FOR REVIEW | [6 empty] | 5.3
87 | [5 empty] | 228E1211200 |  |  | HOLE FOR INDICATOR LAMP ON SIDEWALL | [11 empty] | DICKY | RELEASE
88 | [5 empty] | 228E1211300 |  |  | STIFFENER ON TAPPING SIDEWALL | [7 empty] | RELEASE | RELEASE |  |  | CANDRA | RELEASE
89 | [5 empty] | 228E1211400 |  |  | CABLE DIRECTOR ON SIDEWALL | [7 empty] | RELEASE | RELEASE |  |  | INDRA | RELEASE
90 |  |  |  | 230E1210100 |  |  |  |  | ENDWALL ARRANGEMENT TC1 & TC2 | 1 | • | [24 empty] | 0
91 |  |  |  |  | 231E1200100 |  |  |  | MAIN CONSTRUCTION OF ENDWALL | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE |  |  | 181 |  | 2024-04-29 | 181 |  |  | 45182 |  |  |  | PDR | RELEASE | [7 empty] | 181 | 186 | 5
92 | [5 empty] | 231E1200200 |  |  | END FRAMING | 1 | • |  | • | • | • |  | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [6 empty] | 111.2 | 111.2 | 45182 |  |  |  | PDR | RELEASE
93 | [5 empty] | 231E1200300 |  |  | END SHEETING | 1 | • |  | • | • | • |  | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [6 empty] | 66.7 | 66.7 | 45182 |  |  |  | PDR | RELEASE
94 |  |  |  |  | 238E1210100 |  |  |  | ARR BRACKET ON ENDWALL TC1 & TC2 | 1 | • | [13 empty] | 7.1 |  | 2024-04-29 | 7.1 | [7 empty] | 0
95 | [5 empty] | 238E1210200 |  |  | ARRANGEMENT ADAPTER ON ENDWALL | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  | IFA | RELEASE | [6 empty] | 0.8 |  | 7.1 |  |  |  | IDR | RELEASE
96 | [5 empty] | 238E1210300 |  |  | BRACKET FOR DOOR CLOSER | 1 | • | • | • | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  | IFA | RELEASE | [6 empty] | 2.9 | [5 empty] | FDR | RELEASE
97 | [5 empty] | 238E1210400 |  |  | BRACKET ENDWALL PANEL | 1 | • | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  | IFA | RELEASE | [6 empty] | 1.2 | [5 empty] | FDR | RELEASE
98 | [5 empty] | 238E1210500 |  |  | DIRECTOR CABLE ON ON ENDWALL | 1 | • | [17 empty] | 1 | [5 empty] | FDR | 0
99 | [5 empty] | 238E1210600 |  |  | TAPPING FOR FALLING PROTECTOR | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  | BOY | RELEASE | [6 empty] | 1.2 | [5 empty] | FDR | RELEASE
100 |  |  |  | 240E1210100 |  |  |  |  | DRIVER CAB ARRANGEMENT | 1 | • | [24 empty] | 0 | [7 empty] | 225 | 216 | -9
101 |  |  |  |  | 241E1210100 |  |  |  | MAIN CONSTRUCTION OF MASKARA | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE |  |  | 225 |  | 2024-04-29 | 225 |  |  | 45182 |  |  |  | PDR | RELEASE
102 | [5 empty] | 241E1210200 |  |  | SHEATING MASKARA | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | CANCELED | [6 empty] | 79.9 | 79.9 | [5 empty] | CANCELED
103 | [5 empty] | 241E1210300 |  |  | FRAME MASKARA | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | CANCELED | [6 empty] | 129.1 | 129.1 | [5 empty] | CANCELED
104 | [5 empty] | 241E1210400 |  |  | SHEATING MASKARA | [7 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [12 empty] | PDR | RELEASE
105 | [5 empty] | 241E1210500 |  |  | FRAME MASKARA | [7 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [12 empty] | PDR | RELEASE
106 |  |  |  |  | 245E1210100 |  |  |  | ARR CEILING FRAME ON CAB TC1 & TC2 | 1 | • | [13 empty] | 31.6 |  | 2024-04-29 | 31.6 | [7 empty] | 0
107 | [5 empty] | 245E1210200 |  |  | CEILING FRAME ON CAB | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  | √ | BOY | RELEASE | [6 empty] | 27.6 |  | 44.6 |  |  |  | FDR | RELEASE
108 | [5 empty] | 245E1210300 |  |  | DIRECTOR CABLE ON CEILING FRAME CAB | 1 | • | [8 empty] | √ | BOY | RELEASE |  | SIAP RELEASE |  |  |  |  | 4 | [5 empty] | FDR | RELEASE
109 |  |  |  |  | 248E1210100 |  |  |  | ARR BRACKET WELDED ON CAB TC1 & TC2 | 1 | • | [13 empty] | 13 |  | 2024-04-29 | 13 | [7 empty] | 0
110 | [5 empty] | 248E1210200 |  |  | BRACKET FOR RUNNING TEXT | 1 | • | [9 empty] | KAFI | FOR REVIEW |  | BUTUH CEK | [11 empty] | FOR REVIEW
111 | [5 empty] | 248E1210300 |  |  | INTERIOR LINNING FRAME ON CAB | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  | √ | HADI | RELEASE |  | BUTUH CEK |  |  |  |  | 11 | [5 empty] | FDR | RELEASE
112 | [5 empty] | 248E1210400 |  |  | DIRECTOR CABLE ON CAB | 1 | • | [8 empty] | √ | DICKY | RELEASE |  | BUTUH CEK |  |  |  |  | 2 | [5 empty] | FDR | RELEASE
113 |  |  |  | 250E12101000 |  |  |  |  | ROOF ARRANGEMENT TC1 & TC2 | 1 | • | [24 empty] | 0 | [7 empty] | 1531 | 1410 | -121
114 |  |  |  |  | 251E1210100 |  |  |  | MAIN CONSTRUCTION OF ROOF TC1 & TC2 | 1 | • | [8 empty] | √ |  | RELEASE |  | sheeting update | 1497 |  | 2024-04-29 | 1497 |  |  | 45182 |  |  |  | PDR | RELEASE
115 | [5 empty] | 251E1210200 |  |  | ROOF FRAMING TC1 & TC2 | 1 | • | [8 empty] | √ |  | RELEASE | [6 empty] | 304.5 | 304.5 | 45182 |  |  |  | PDR | RELEASE
116 | [5 empty] | 251E1210300 |  |  | ROOF SHEATING TC1 & TC2 | 1 | • | [8 empty] | √ |  | RELEASE | [6 empty] | 395.4 | 395.4 | 45201 |  |  |  | PDR | RELEASE
117 | [5 empty] | 251E1200400 |  |  | ROOF FRAMING AC | 1 | • | [8 empty] | √ |  | RELEASE | [6 empty] | 709.4 | 709.4 | 45182 |  |  |  | PDR | RELEASE
118 | [5 empty] | 251E1210500 |  |  | ARR GUSSET ON ROOF TC1 & TC2 | 1 | • | [8 empty] | √ |  | RELEASE | [6 empty] | 16.3 | 16.3 | 45182 |  |  |  | PDR | RELEASE
119 | [5 empty] | 251E1210600 |  |  | RAIN GUTTER TC1 & TC2 | 1 | • | [8 empty] | √ |  | RELEASE |  | BUTUH REVISI |  |  |  |  | 150.2 | 150.2 | 45182 |  |  |  | PDR | RELEASE
120 |  |  |  |  | 255E1210100 |  |  |  | ARRG CEILING FRAME | 1 | • | [13 empty] | 0 | [10 empty] | 0
121 | [5 empty] | 255E1210200 |  |  | CEILING FRAME PASSENGER ROOM (DUCTING+HANDGRIP) | 1 | • | [5 empty] | FOR REVIEW | FOR REVIEW |  |  | HADI | RELEASE |  | SIAP RELEASE | 114 |  | 2024-04-29 | 109 | 104 | [5 empty] | FDR | RELEASE
122 | [5 empty] | 255E1200400 |  |  | BRACKET FOR ROLL FILTER | [11 empty] | DICKY | RELEASE | [5 empty] | 5
123 |  |  |  |  | 258E1210100 |  |  |  | ARR BRACKET ON ROOF | 1 | • | [13 empty] | 115.7 |  | 2024-04-29 | 115.7 |  |  | 88.1 |  |  |  |  | 0
124 | [5 empty] | 258E1210200 |  |  | ARRANGEMENT ADAPTER ON ROOF | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | CANDRA | RELEASE |  | BUTUH CEK |  |  | 2024-04-29 |  | 27.6 | [5 empty] | IDR | RELEASE
125 | [5 empty] | 258E1210300 |  |  | CABLE DIRECTOR ON ROOF | 1 | • | [5 empty] | WORKING | WORKING |  | √ | HADI | RELEASE |  | SIAP RELEASE |  |  | 2024-04-29 |  | 5.2 | [5 empty] | FDR | RELEASE
126 | [5 empty] | 258E1200400 |  |  | BRACKET FOR EXTERIOR SPEAKER | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | HADI | RELEASE |  |  |  |  | 2024-04-29 |  | 0.9 | [5 empty] | FDR | RELEASE
127 | [5 empty] | 258E1210500 |  |  | BRACKET FOR DOOR POCKET | 1 | • | [5 empty] | RELEASE | RELEASE |  | √ | CANDRA | RELEASE |  |  |  |  | 2024-04-29 |  | 37 | [5 empty] | FDR | RELEASE
128 | [5 empty] | 258E1210600 |  |  | BRACKET FOR ELECTRICAL CABINET PANEL ON CABIN & ENDWALL | 1 | • | [5 empty] | WORKING | WORKING |  | √ | CANDRA | RELEASE |  | SIAP RELEASE |  |  | 2024-04-29 |  | 10.4 | [5 empty] | FDR | RELEASE
129 | [5 empty] | 258E1210700 |  |  | BRACKET FOR DOOR CONTROL UNIT | 1 | • | [5 empty] | WORKING | WORKING |  | √ | CANDRA | RELEASE |  | SIAP RELEASE |  |  | 2024-04-29 |  | 30 | [5 empty] | FDR | RELEASE
130 | [5 empty] | 258E1210800 |  |  | BRACKET AND PIPE FOR CABLE ANTENNA | 1 | • | [9 empty] | DICKY | FOR REVIEW |  | BUTUH CEK |  |  |  |  | 2 | [5 empty] | FDR | FOR REVIEW
131 | [5 empty] | 258E1210900 |  |  | CABLE DIRECTOR ON CABIN AND REAR ROOF FRAME | [10 empty] | √ | HADI | RELEASE |  | BUTUH CEK |  |  |  |  | 2.6
BATASBAWAH
680.01
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Krisna Bilal Arief) | [9 empty] | (Fathur Rokhman Hidayat) | [12 empty] | (Hernawan Prasanto)
[7 empty] | No | BOBOT CATEGORY | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | BERAT (SEBELUM PENGURANGAN) |  | BERAT (SETELAH PENGURANGAN) | SELISIH BERAT | DRAWING YANG BELUM
[7 empty] | 1 | BOM | BOM MATERIAL | 2 |  | 2 |  | 100% | [8 empty] | BOBOT % DARI TOTAL DRAWING
[7 empty] | 1 | MAIN | MAIN CONSTRUCTION OF UNDERFRAME TC1&TC2 | 12 |  | 12 |  | 100% |  | 4570 |  | 4208 | 362 | 0 |  |  |  | MAIN | 60%
[7 empty] | 2 | MAIN | MAIN CONSTRUCTION OF SIDEWALL TC1 & TC2 | 18 |  | 18 |  | 100% |  | 1824 |  | 1824 | 0 | 0
[7 empty] | 3 | MAIN | MAIN CONSTRUCTION OF ENDWALL | 3 |  | 3 |  | 100% |  | 181 |  | 181 | 0 | 0 |  |  |  | BKT | 40% | floor, interior SW/RF/EW, big komp
[7 empty] | 4 | MAIN | MAIN CONSTRUCTION OF MASKARA | 3 |  | 3 |  | 100% |  | 225 |  | 225 | 0 | 0 | [5 empty] | cable director, small komp.
[7 empty] | 5 | MAIN | MAIN CONSTRUCTION OF ROOF TC1 & TC2 | 6 |  | 6 |  | 100% |  | 1497 |  | 1497 | 0 | 0
[9 empty] | GREEN CAR | 42 |  | 42 |  | 60% |  | 8297 |  | 7935 | 362 |  |  |  |  | ganti arahan pada 27 des 2023
[7 empty] | 1 | BKT | FLOOR CONSTRUCTION TC1 & TC2 | 2 |  | 2 |  | 100% |  | 336 |  | 336 | 0 | 0 | 0 |  |  | MAIN | 80%
[7 empty] | 2 | BKT | ARR SUPORTING FRAME FOR FLOOR TC1 & TC2 | 7 |  | 7 |  | 100% |  | 246.23 |  | 246.23 | 0 | 7 | 0
[7 empty] | 3 | BKT | ARRANGEMENT BRACKET & FRAME ON U/F TC1 | 24 |  | 11 |  | 45.83% |  | 170.28 |  | 170.28 | 0 | 10 | 14 | 695.38 |  | BKT | 20%
[7 empty] | 4 | BKT | ARR BRACKET ON SIDE WALL TC1 & TC2 | 8 |  | 6 |  | 75% |  | 252.7 |  | 252.7 | 0 | 1 | 7
[7 empty] | 5 | BKT | ARR BRACKET ON ENDWALL TC1 & TC2 | 5 |  | 4 |  | 80% |  | 7.1 |  | 7.1 | 0 | 0 | 5
[7 empty] | 6 | BKT | ARR CEILING FRAME ON CAB TC1 & TC2 | 2 |  | 2 |  | 100% |  | 27.6 |  | 27.6 | 0 | -3 | 5
[7 empty] | 7 | BKT | ARR BRACKET WELDED ON CAB TC1 & TC2 | 2 |  | 2 |  | 100% |  | 13 |  | 13 | 0 | 2 | 0
[7 empty] | 8 | BKT | ARRG CEILING FRAME | 1 |  | 1 |  | 100% |  | 109 |  | 109 | 0 | 1 | 0
[7 empty] | 9 | BKT | ARR BRACKET ON ROOF | 7 |  | 2 |  | 28.57% |  | 115.7 |  | 115.7 | 0 | 4 | 3
[9 empty] | BRACKET AND SUPPORT | 58 |  | 37 |  | 25.52% |  | 1277.61 |  | 1277.61 | 0
[9 empty] | TOTAL DRAWING /TOTAL BERAT | 100 |  | 79 |  |  |  | 9574.61 |  | 9212.61 | 362
[9 empty] | PROGRESS TOTAL |  |  |  |  | 85.52% | [6 empty] | 695.38
79%
DRAWING UNTUK KEBUTUHAN CARBODY ASSY
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | SCOPE OF WORK
[8 empty] | 1 | CARBODY SHEEL (TC1) | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 2 | SIDEWALL ARRANGEMENT TC1 & TC2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 3 | ENDWALL ARRANGEMENT TC1 & TC2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 4 | DRIVER CAB ARRANGEMENT | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 5 | ROOF ARRANGEMENT TC1 & TC2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[9 empty] | TOTAL DRAWING INKA | 5 |  | 0
[9 empty] | PROGRESS INKA |  |  |  |  | 0%
INKA

## M1 (E122)
[17 empty] | Project |  | : 16 TS KRL KCI (E12) | [5 empty] | WEIGHT LIMIT (KG) : |  | 8000 | [5 empty] | JUMLAH |  | %-TASE
[9 empty] | TREE DIAGRAM & | [7 empty] | Document Number |  | : 201-TDD-H1005MB051-23 | [5 empty] | WEIGHT EST. (KG) |  | 9551.46 | [5 empty] | DRAWING | RELEASE
[9 empty] | WEIGHT CALCULATION | [7 empty] | Date of Issue |  | : JANUARI 2023 | [5 empty] | PROGRESS TOTAL |  | 86.79% |  |  |  |  | PDR | 36 | 36 | 100%
[9 empty] | M1 | [7 empty] | Revision |  | : 0 | [12 empty] | IDR | 6 | 6 | 100%
[17 empty] | Page |  | : | [12 empty] | FDR | 46 | 32 | 69.57%
[17 empty] | Car Type |  | : M1 | [13 empty] | 88 | 74
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK (SOW) | WEIGHT EST. (KG) | Tanggal Drawing Release | Update Berat | WEIGHT EST. (KG)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7
1 | 201-BRM-H1005MB051-23 | [7 empty] | BOM RAW MATERIAL | [12 empty] | RELEASE
2 | 203-BRM-H1005MB051-23 | [7 empty] | BOM PIECE PART |  | • | • | • | • | • | • | [5 empty] | RELEASE
3 | 000E1220100 | [7 empty] | GA M1 KRL KCI 2022 | 1
4 |  | 000E1202000 | [6 empty] | TRAILLER BOGIE ASSEMBLY | 1
5 |  | 002E1220200 | [6 empty] | CARBODY SET M1 | 1
6 |  |  | 200E1220100 | [5 empty] | CARBODY SHEEL M1 | 1 | [24 empty] | SELISIH BERAT | BERAT TIMBANG
7 |  |  |  | 210E1220100 |  |  |  |  | UNDERFRAME ARRANGEMENT (M1, M2) | 1 |  |  | • | [11 empty] | 5060.46
8 |  |  |  |  | 210E1220200 |  |  |  | MAIN COSTRUCTION OF UNDERFRAME M1, M2 | 1 |  | • | • | • | • | • | [5 empty] | RELEASE |  | air supply update |  |  | 2024-04-29 | 4325 |  |  |  | PDR | RELEASE |  | 61.4 | 4874
9 | [5 empty] | 211E1220100 |  |  | END PART ASSEMBLY | 2 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 2924 | 219 |  | PDR | RELEASE
10 | [6 empty] | 211E1200200 |  | END PART | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [7 empty] | 470 |  | PDR | RELEASE
11 | [6 empty] | 212E1200100 |  | BOLSTER | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [7 empty] | 684 |  | PDR | RELEASE
12 | [5 empty] | 211E1200300 |  |  | ANTI CLIMBER 02 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 40 |  |  | PDR | RELEASE
13 | [5 empty] | 213E1200100 |  |  | MIDDLE PART ASSY | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 1341 |  |  | PDR | RELEASE
14 | [5 empty] | 213E1220200 |  |  | BACKING MIDDLE PART ASSY | 1 |  | • | • | [8 empty] | RELEASE | [6 empty] | 0 |  |  | PDR | RELEASE
15 | [5 empty] | 213K5600200 |  |  | JACKING PAD | 4 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 21.6 | 5.4 |  | PDR | RELEASE
16 |  |  |  |  | 214E1220100 |  |  |  | FLOOR CONSTRUCTION M1&M2 | 1 |  | • | • | [13 empty] | 2024-04-29 | 341.1 |  |  |  |  | 0
17 | [5 empty] | 214E1220200 |  |  | ARRG FLOOR ON PASSENGER ROOM | 1 |  | • | • |  |  |  | PRE-RELEASE | PRE-RELEASE |  |  | HADI | RELEASE | [6 empty] | 341.1 |  |  | PDR | RELEASE
18 |  |  |  |  | 215E1220100 |  |  |  | ARR SUPORTING FRAME FOR FLOOR M1 | 1 |  | • | • | [13 empty] | 2024-04-29 | 197 |  |  |  |  | 0
19 | [5 empty] | 215E1220200 |  |  | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | 1 |  | • | • |  |  |  | PRE-RELEASE | PRE-RELEASE |  | √ | KAFI | RELEASE |  | BUTUH REVISI |  |  |  |  | 57 |  | 150.3 | PDR | RELEASE
20 | [5 empty] | 215E1220300 |  |  | DRAIN PIPE AND SUPPORT | 1 |  | • | • |  |  |  | PRE-RELEASE | PRE-RELEASE |  | √ | HADI | RELEASE |  | BUTUH REVISI |  |  |  |  | 86.2 |  |  | PDR | RELEASE
21 | [5 empty] | 215E1220400 |  |  | TAPPING STRIP | 1 |  | • | • |  |  |  | PRE-RELEASE | PRE-RELEASE |  | √ | KAFI | RELEASE | [6 empty] | 32.2 |  |  | PDR | RELEASE
22 | [5 empty] | 215E1220500 |  |  | TAPPING FOR PASSENGER SEAT ON FLOOR | 1 |  | • | • |  |  |  | PRE-RELEASE | PRE-RELEASE |  | √ | CANDRA | RELEASE | [6 empty] | 31 |  |  | IDR | RELEASE
23 | [5 empty] | 215E1220600 |  |  | TAPPING FOR DOOR POCKET &INTERIOR CABINET | 1 |  | • | • |  |  |  | PRE-RELEASE | PRE-RELEASE |  |  | IFA | RELEASE | [6 empty] | 7.1 |  |  | IDR | RELEASE
24 | [5 empty] | 215E1220700 |  |  | TAPPING STRIP FOR EVACUATION LINE | 1 |  | • | • | [19 empty] | 0
25 |  |  |  |  | 218E1220100 |  |  |  | ARRANGEMENT BRACKET & FRAME ON U/F M1 | 1 |  | • | [15 empty] | 197.36 |  |  |  |  | 0
26 | [5 empty] | 218E1200200 |  |  | BRACKET FOR GROUNDING INTER CAR | 1 |  | • | • | • | • | • |  |  |  |  | HADI |  |  | 30.1-E12019 | [7 empty] | FDR | 0
27 | [5 empty] | 218E1200300 |  |  | BRACKET FOR LEVELING VALVE | 1 | • | • | • | • | • | • | RELEASE | RELEASE |  |  | IFA | RELEASE | [6 empty] | 1.7 |  |  | FDR | RELEASE
28 | [5 empty] | 218E1220400 |  |  | BRACKET FOR COUPLER SUPPORT | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  | HADI | RELEASE | [6 empty] | 15.6 |  |  | IDR | RELEASE
29 | [5 empty] | 218E1200500 |  |  | BRACKET FOR LADDER | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  |  | KAFI | RELEASE | [6 empty] | 1.1 |  |  | FDR | RELEASE
30 | [5 empty] | 218E1220600 |  |  | BRACKET VVVF | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ | KAFI | RELEASE |  | 30.1-E12006 |  |  |  |  | 17.7 |  |  | FDR | RELEASE
31 | [5 empty] | 218E1220700 |  |  | BRACKET FOR ELECTRIC CONTROL PANEL | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12213 |  |  |  |  | 12.7 |  |  | FDR | RELEASE
32 | [5 empty] | 218E1220800 |  |  | BRACKET BRAKE RESISTOR | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12010 |  |  |  |  | 4.1 |  |  | FDR | RELEASE
33 | [5 empty] | 218E1220900 |  |  | BRACKET CHOPPER BOX | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ | KAFI | RELEASE |  | 30.1-E12012 |  |  |  |  | 12 |  |  | FDR | RELEASE
34 | [5 empty] | 218E1221000 |  |  | BRACKET CHOPPER REACTOR | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  |  | KAFI | RELEASE |  | 30.1-E12011 |  |  |  |  | 6 |  |  | FDR | RELEASE
35 | [5 empty] | 218E1221100 |  |  | BRACKET OF AIR RESEVOIR (100L) | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ | YOGI | RELEASE |  | 30.1-E12204 |  |  |  |  | 19.2 |  |  | FDR | RELEASE
36 | [5 empty] | 218E1221200 |  |  | BRACKET OF BRAKE CONTROL UNIT | 1 |  | • | • |  |  |  | PRE-RELEASE | PRE-RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12203 |  |  |  |  | 0.66 |  |  | FDR | RELEASE
37 | [5 empty] | 218E1221300 |  |  | BRACKET FOR CABLE DUCT | 1 |  | • | • |  |  |  | FOR REVIEW | FOR REVIEW |  |  | KAFI | FOR REVIEW |  | 30.1-E12015 |  |  |  |  | 32 |  |  | FDR | FOR REVIEW
38 | [5 empty] | 218E1221400 |  |  | BRACKET FOR PNEUMATIC PIPING | 1 |  | • | • |  |  |  | FOR REVIEW | FOR REVIEW |  |  | KAFI | FOR REVIEW |  | 30.1-E12220 |  |  |  |  | 20.8 |  |  | FDR | FOR REVIEW
39 | [5 empty] | 218E1221500 |  |  | BRACKET MAIN SWITCH | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  | √ | YOGI | RELEASE |  | 30.1-E12208 |  |  |  |  | 6.7 |  |  | FDR | RELEASE
40 | [5 empty] | 218E1221600 |  |  | BRACKET FILTER REACTOR | 1 |  | • | [7 empty] | √ | HADI | FOR REVIEW |  | 30.1-E12207 |  |  |  |  | 7 |  |  | FDR | FOR REVIEW
41 | [5 empty] | 218E1221700 |  |  | BRACKET HSCB BOX | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  | √ | YOGI | RELEASE |  | 30.1-E12209 |  |  |  |  | 7.8 |  |  | FDR | RELEASE
42 | [5 empty] | 218E1221800 |  |  | BRACKET JUNCTION COUPLER ELECTRIC | 1 |  | • | [11 empty] | INPUTAN BELUM FIX |  |  |  |  | 2 |  |  | FDR | 0
43 | [5 empty] | 218E1221900 |  |  | BRACKET OF PANTOGRAPH CONTROL MODULE | 1 |  | • | [8 empty] | HADI | FOR REVIEW |  | 30.1-E12217 |  |  |  |  | 10 |  |  | FDR | FOR REVIEW
44 | [5 empty] | 218E1222000 |  |  | BRACKET OF PANTOGRAPH DISCONNECTOR SWITCH | 1 |  | • |  |  |  |  | PRE-RELEASE | PRE-RELEASE |  | √ | KAFI | RELEASE |  | 30.1-E12210 |  |  |  |  | 0.6 |  |  | FDR | RELEASE
45 | [5 empty] | 218E1222100 |  |  | BRACKET OF BUS FUSE | 1 |  | • |  |  |  |  | PRE-RELEASE | PRE-RELEASE |  | √ | HADI | RELEASE |  | 30.1-E12211 |  |  |  |  | 2.7 |  |  | FDR | RELEASE
46 | [5 empty] | 218E1222200 |  |  | BRACKET OF LGS (GROUND SWITCH) | 1 |  | • | [20 empty] | 0
47 | [5 empty] | 218E1222300 |  |  | BRACKET OF TRACTION MOTOR JUNCTION BOX | 1 |  | • | [8 empty] | INDRA | WORKING |  | 30.1-E12212 |  |  |  |  | 5 |  |  | FDR | WORKING
48 | [5 empty] | 218E1222400 |  |  | BRACKET OF GROUNDING PLATE | 1 |  | • | [8 empty] | KAFI | FOR REVIEW | [6 empty] | 5 |  |  | FDR | FOR REVIEW
49 | [5 empty] | 218E1222500 |  |  | CABLE DIRECTOR ON UNDERFRAME | 1 |  | • | [8 empty] | INDRA | FOR REVIEW |  | INPUTAN BELUM FIX |  |  |  |  | 7 |  |  | FDR | FOR REVIEW
50 |  |  |  | 220E1220100 |  |  |  |  | SIDEWALL ARRANGEMENT M1 | 1 |  | • | [12 empty] | 2008.5 | [7 empty] | 0
51 |  |  |  |  | 221E1220200 |  |  |  | SIDEWALL CONSTRUCTION M1, M2 | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2024-04-29 | 1730 |  |  |  | PDR | RELEASE |  | -86.8 | 1750 | 875
52 | [5 empty] | 221E1200300 |  |  | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | 2 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 248 | 124 |  | PDR | RELEASE
53 | [5 empty] | 221E1200400 |  |  | MIDDLE SIDEWALL 2 | 2 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 248 | 124 |  | PDR | RELEASE
54 | [5 empty] | 221E1200600 |  |  | END SIDEWALL 2 --> (RIGHT) | 2 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 144.8 | 72.4 |  | PDR | RELEASE
55 | [5 empty] | 221E1200700 |  |  | PASSENGER ENTRANCE | 8 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 464.8 | 58.1 |  | PDR | RELEASE
56 | [5 empty] | 221E1220800 |  |  | ARR GUSSET ON SIDEWALL M1,M2 | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 62.3 | 62.3 |  | PDR | RELEASE
57 | [5 empty] | 221E1201000 |  |  | SIDEWALL DOOR SUPPORT 1 | 4 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 80 | 20 |  | PDR | RELEASE
58 | [5 empty] | 221E1201100 |  |  | SIDEWALL DOOR SUPPORT 2 | 2 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 39.8 | 19.9 |  | PDR | RELEASE
59 | [5 empty] | 221E1201200 |  |  | SIDEWALL DOOR SUPPORT 3 | 2 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 39.8 | 19.9 |  | PDR | RELEASE
60 | [5 empty] | 221E1220300 |  |  | MIDDLE SIDEWALL 2 --> (DUCT MOTOR) | 2 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 247.6 | 123.8 |  | PDR | RELEASE
61 | [5 empty] | 221E1220400 |  |  | END SIDEWALL 3 --> (DUCT MOTOR) | 2 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 143.8 | 71.9 |  | PDR | RELEASE
62 |  |  |  |  | 228E1220100 |  |  |  | ARR BRACKET ON SIDE WALL M1 | 1 | [16 empty] | 2024-04-29 | 278.5 |  |  |  |  | 0
63 | [5 empty] | 228E1220200 |  |  | ARRANGEMENT OF ADAPTER ON SIDEWALL | 1 |  | • | • |  |  |  | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 23.6 |  | #REF! | IDR | RELEASE
64 | [5 empty] | 228E1200300 |  |  | BRACKET FOR CURTAIN | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 19.4 |  |  | FDR | RELEASE
65 | [5 empty] | 228E1200400 |  |  | BRACKET FOR DOOR ENGINE ENTRANCE | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 83.2 |  |  | FDR | RELEASE
66 | [5 empty] | 228E1200500 |  |  | BRACKET FOR LUGGAGE RACK | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 91.7 |  |  | FDR | RELEASE
67 | [5 empty] | 228E1200600 |  |  | BRACKET FOR EMERGENCY DOOR RELEASE | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ | CANDRA | RELEASE |  | BUTUH CEK |  |  |  |  | 3.4 |  |  | FDR | RELEASE
68 | [5 empty] | 228E1200700 |  |  | BRACKET FOR RUNNING TEXT | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 5.2 |  |  | FDR | RELEASE
69 | [5 empty] | 228E1200800 |  |  | BRACKET FOR AC PANEL | 1 |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  | DICKY | FOR REVIEW |  | BUTUH CEK |  |  |  |  | 0 |  |  | FDR | FOR REVIEW
70 | [5 empty] | 228E1200900 |  |  | BRACKET FOR FOLDING SEAT | 1 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 42 |  |  | FDR | RELEASE
71 | [5 empty] | 228E1201000 |  |  | BRACKET FOR SIDEWALL & ENDWALL PANEL | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 10 |  |  | FDR | RELEASE
72 | [5 empty] | 228E1201100 |  |  | BRACKET ROLL FILTER PANEL
73 | [5 empty] | 228E1221200 |  |  | HOLE FOR INDICATOR LAMP ON SIDEWALL | [11 empty] | DICKY | RELEASE
74 | [5 empty] | 228E1201300 |  |  | STIFFENER ON TAPPING SIDEWALL | [7 empty] | RELEASE | RELEASE |  |  | CANDRA | RELEASE
75 | [5 empty] | 228E1201400 |  |  | CABLE DIRECTOR ON SIDEWALL | [7 empty] | RELEASE | RELEASE |  |  | CANDRA | RELEASE
76 |  |  |  | 230E1220100 |  |  |  |  | ENDWALL ARRANGEMENT M1 | 1 |  | • | [12 empty] | 415.9 | [7 empty] | 0
77 |  |  |  |  | 231E1220100 |  |  |  | MAIN CONSTRUCTION OF FRONT ENDWALL M1 | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  | 2023-09-13 | 2024-04-29 | 198 |  |  |  | PDR | RELEASE |  | 4 | 400 | 200
78 | [5 empty] | 231E1220200 |  |  | END FRAMING FRONT | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE | [6 empty] | 127.7 | 127.7 |  | PDR | RELEASE
79 | [5 empty] | 231E1200300 |  |  | END SHEETING | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE | [6 empty] | 66.7 | 66.7 |  | PDR | RELEASE
80 |  |  |  |  | 231E1220400 |  |  |  | MAIN CONSTRUCTION OF REAR ENDWALL M1 | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE |  |  |  |  | 2024-04-29 | 198 |  |  |  | PDR | RELEASE
81 | [5 empty] | 231E1200300 |  |  | END SHEETING | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE | [6 empty] | 66.7 | 66.7 |  | PDR | RELEASE
82 | [5 empty] | 231E1220500 |  |  | END FRAMING REAR | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE | [6 empty] | 127.7 | 127.7 |  | PDR | RELEASE
83 |  |  |  |  | 238E1220100 |  |  |  | ARR BRACKET ON ENDWALL M1 | 1 |  | • | [14 empty] | 2024-04-29 | 19.9 |  |  | 19.9 |  | 0
84 | [5 empty] | 238E1220200 |  |  | ARRANGEMENT ADAPTER ON ENDWALL | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ | IFA | RELEASE |  |  |  |  | 2024-04-29 |  | 1.6 |  |  | IDR | RELEASE
85 | [5 empty] | 238E1220300 |  |  | BRACKET FOR DOOR CLOSER | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ | IFA | RELEASE |  | siap release |  |  | 2024-04-29 |  | 11.7 |  |  | FDR | RELEASE
86 | [5 empty] | 238E1220400 |  |  | BRACKET ENDWALL PANEL | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ | IFA | RELEASE |  | siap release |  |  | 2024-04-29 |  | 4.5 |  |  | FDR | RELEASE
87 | [5 empty] | 238E1200500 |  |  | DIRECTOR CABLE ON ON ENDWALL | 1 |  | • | • | • | • | • | [15 empty] | FDR | 0
88 | [5 empty] | 238E1220600 |  |  | TAPPING FOR FALLING PROTECTOR | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ | BOY | RELEASE |  |  |  |  | 2024-04-29 |  | 2.1 |  |  | FDR | RELEASE
89 | [5 empty] | 238E1220700 |  |  | BRACKET FOR CABLE AND PIPE PANTOGRAPH | 1 |  | • | [8 empty] | INDRA | RELEASE |  | INPUTAN BELUM FIX | [7 empty] | FDR | RELEASE
90 |  |  |  | 250E1220100 |  |  |  |  | ROOF ARRANGEMENT M1 | 1 |  | • | [12 empty] | 2066.6 | [7 empty] | 0
91 |  |  |  |  | 251E1220100 |  |  |  | MAIN CONSTRUCTION OF ROOF M | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  |  | RELEASE |  | sheeting update |  | 2023-09-13 | 2024-04-29 | 1782 |  |  |  | PDR | RELEASE |  | -125 | 1678 | 1678
92 | [5 empty] | 251E1220200 |  |  | ROOF FRAMING M1 | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 258.4 | 258.4 |  | PDR | RELEASE
93 | [5 empty] | 251E1220300 |  |  | ROOF SHEATING M1 | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 328.3 | 328.3 |  | PDR | RELEASE
94 | [5 empty] | 251E1200400 |  |  | ROOF FRAMING AC | 1 | • | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 709.4 | 709.4 |  | PDR | RELEASE
95 | [5 empty] | 251E1220500 |  |  | ARR GUSSET ON ROOF M,T | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 16.3 | 16.3 |  | PDR | RELEASE
96 | [5 empty] | 251E1200600 |  |  | RAIN GUTTER M, T | 1 | [6 empty] | RELEASE | RELEASE |  | √ |  | RELEASE | [6 empty] | 150.1 | 150.1 |  | PDR | RELEASE
97 | [5 empty] | 251E1220800 |  |  | ROOF FRAMING PANTOGRAPH | 2 |  | • | • | • | • | • | RELEASE | RELEASE |  | √ |  | RELEASE |  | BUTUH REVISI |  |  |  |  | 390.2 | 195.1 |  | PDR | RELEASE
98 |  |  |  |  | 255E1220100 |  |  |  | ARR CEILLING FRAMING M1 | 1 |  | • | [15 empty] | 144 |  |  | 260.6 |  | 0
99 | [5 empty] | 255E1220200 |  |  | CEILING FRAME PASSANGER ROOM (DUCTING+HANDGRIP) | 1 |  | • |  |  |  |  | PRE-RELEASE | PRE-RELEASE |  |  | DIKCY | RELEASE |  | siap release |  |  | 2024-04-29 |  | 139 |  |  | FDR | RELEASE
100 | [5 empty] | 255E1200400 |  |  | BRACKET FOR ROLL FILTER | [11 empty] | DICKY | RELEASE | [6 empty] | 5
101 |  |  |  |  | 258E1220100 |  |  |  | ARR BRACKET ON ROOF M1 | 1 |  | • | [15 empty] | 140.6 |  |  |  |  | 0
102 | [9 empty] | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  | √ | CANDRA | RELEASE | [6 empty] | 21 |  |  | IDR | RELEASE
103 | [5 empty] | 258E1220300 |  |  | CABLE DIRECTOR ON ROOF | 1 |  | • |  |  |  |  | FOR REVIEW | FOR REVIEW |  | √ | BOY | RELEASE |  | SIAP RELEASE |  |  |  |  | 8 |  |  | FDR | RELEASE
104 | [5 empty] | 258E1200400 |  |  | BRACKET FOR EXTERIOR SPEAKER | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  | √ | HADI | RELEASE | [6 empty] | 0.9 |  |  | FDR | RELEASE
105 | [5 empty] | 258E1220500 |  |  | BRACKET FOR DOOR POCKET | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  | √ | CANDRA | RELEASE | [6 empty] | 55 |  |  | FDR | RELEASE
106 | [5 empty] | 258E1200600 |  |  | BRACKET FOR ELECTRICAL CABINET ON ENDWALL | 1 |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  | √ | HADI | RELEASE |  | siap release |  |  |  |  | 3.1 |  |  | FDR | RELEASE
107 | [5 empty] | 258E1220700 |  |  | BRACKET FOR DOOR CONTROL UNIT | 1 |  | • |  |  |  |  | FOR REVIEW | FOR REVIEW |  | √ | CANDRA | RELEASE |  | BUTUH CEK |  |  |  |  | 30 |  |  | FDR | RELEASE
108 | [5 empty] | 258E1220800 |  |  | BRACKET OF SURGE ARRESTER | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  | BOY | RELEASE | [6 empty] | 3.6 |  |  | FDR | RELEASE
109 | [5 empty] | 258E1220900 |  |  | BRACKET OF MANUAL HOOK RELEASE | 1 |  | • |  |  |  |  | FOR REVIEW | FOR REVIEW |  |  | BOY | FOR REVIEW |  | BUTUH CEK |  |  |  |  | 5.6 |  |  | FDR | FOR REVIEW
110 | [5 empty] | 258E1221000 |  |  | BRACKET OF CABLE DUCT PANTOGRAPH | 1 |  | • | [16 empty] | 5 |  |  | FDR | 0
111 | [5 empty] | 258E1221100 |  |  | BRACKET OF RISE DETECTION BOX | 1 |  | • |  |  |  |  | RELEASE | RELEASE |  |  | BOY | RELEASE | [6 empty] | 3.4 |  |  | FDR | RELEASE
112 | [5 empty] | 258E1221200 |  |  | BRACKET OF PIPING PANTOGRAPH | 1 |  | • | [16 empty] | 5 |  |  | FDR | 0
113 | [5 empty] | 258E1221300 |  |  | CABLE DIRECTOR ON REAR ROOF FRAME | [10 empty] | √ | HADI | RELEASE |  | BUTUH CEK |  |  |  |  | 2
[9 empty] | BATASBAWAH | [26 empty] | 8702
#REF!
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Krisna Bilal Arief) | [9 empty] | (Fathur Rokhman Hidayat) | [12 empty] | (Hernawan Prasanto)
[7 empty] | No | BOBOT CATEGORY | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | BERAT (SEBELUM PENGURANGAN) |  | BERAT (SETELAH PENGURANGAN) | SELISIH BERAT |  |  | DRAWING YANG BELUM
[7 empty] | 1 | BOM | BOM MATERIAL | 2 |  | 2 |  | 100%
[7 empty] | 1 | MAIN | UNDERFRAME ARRANGEMENT (M1, M2) | 8 |  | 8 |  | 100% |  | 4325 |  | 3864 | 461 |  |  | 0
[7 empty] | 2 | MAIN | SIDEWALL ARRANGEMENT M1 | 11 |  | 11 |  | 100% |  | 1730 |  | 1730 |  |  |  | 0
[7 empty] | 3 | MAIN | ENDWALL ARRANGEMENT M1 | 6 |  | 6 |  | 100% |  | 396 |  | 396 |  |  |  | 0
[7 empty] | 4 | MAIN | ROOF ARRANGEMENT M1 | 7 |  | 7 |  | 100% |  | 1782 |  | 1782 |  |  |  | 0
[9 empty] | GREEN CAR | 34 |  | 34 |  | 80% |  | 8233 |  | 7772
[7 empty] | 1 | BKT | FLOOR CONSTRUCTION M1&M2 | 1 |  | 1 |  | 100% |  | 341.1 |  | 341.1 |  | 538.1 |  | 0
[7 empty] | 2 | BKT | ARR SUPORTING FRAME FOR FLOOR M1 | 5 |  | 5 |  | 100% |  | 197 |  | 197 |  |  |  | 0
[7 empty] | 3 | BKT | ARRANGEMENT BRACKET & FRAME ON U/F M1 | 24 |  | 2 |  | 8.333% |  | 197.36 |  | 197.36 |  | 780.36 |  | 13 | 11
[7 empty] | 4 | BKT | ARR BRACKET ON SIDE WALL M1 | 8 |  | 5 |  | 62.5% |  | 278.5 |  | 278.5 |  |  |  | 2 | 6
[7 empty] | 5 | BKT | ARR BRACKET ON ENDWALL M1 | 6 |  | 3 |  | 50% |  | 19.9 |  | 19.9 |  |  |  | 2 | 4
[7 empty] | 6 | BKT | ARR CEILLING FRAMING M1 | 1 |  | 1 |  | 100% |  | 144 |  | 144 |  |  |  | 1 | 0
[7 empty] | 7 | BKT | ARR BRACKET ON ROOF M1 | 11 |  | 2 |  | 18.18% |  | 140.6 |  | 140.6 |  |  |  | 6 | 5
[9 empty] | BRACKET AND SUPPORT | 56 |  | 19 |  | 6.786% |  | 1318.46 |  | 1318.46
[9 empty] | TOTAL DRAWING/ TOTAL BERAT | 90 |  | 53 |  |  |  | 9551.46 |  | 9090.46 | 461
[9 empty] | PROGRESS TOTAL |  |  |  |  | 86.79%
DRAWING UNTUK KEBUTUHAN CARBODY ASSY
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | SCOPE OF WORK
[8 empty] | 1 | CARBODY SHEEL M1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 2 | SIDEWALL ARRANGEMENT M1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 3 | ENDWALL ARRANGEMENT M1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 4 | ROOF ARRANGEMENT M1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[9 empty] | TOTAL DRAWING INKA | 4 |  | 0
[9 empty] | PROGRESS INKA |  |  |  |  | 0%
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Fathur Rokhman Hidayat) | [9 empty] | (Hernawan Prasanto) | [12 empty] | ( Kristanto)
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) | [6 empty] | Release (Jumlah Status Release Drawing per sub Assy) | %-tase (besaran % tase per sub assy) | SCOPE OF WORK
[8 empty] | 1 | END SIDEWALL 2 --> (RIGHT) | 14 | [6 empty] | 13 | 92.86% | INKA 3D+2D
[8 empty] | 2 | BRACKET ENDWALL PANEL | 12 | [6 empty] | 10 | 83.33% | INKA 3D+2D
[8 empty] | 3 | #REF! | 0 | [6 empty] | #REF! | #REF! | INKA 3D+2D
[8 empty] | 4 | #REF! | 0 | [6 empty] | #REF! | #REF! | INKA 3D+2D
[8 empty] | 5 | #REF! | 0 | [6 empty] | #REF! | #REF! | IMS 3D+2D
[8 empty] | 6 | #REF! | 10 | [6 empty] | 8 | 80% | IMS 3D+2D
[8 empty] | 7 | ARR CEILLING FRAMING M1 | 6 | [6 empty] | 4 | 66.67% | IMS 3D+2D
[8 empty] | 8 | #REF! | 0 | [6 empty] | #REF! | #REF! | IMS 3D+2D
[8 empty] | 9 | #REF! | 0 | [6 empty] | #REF! | #REF! | IMS 3D+2D
[8 empty] | 10 | #REF! | 0 | [6 empty] | #REF! | #REF! | IMS 3D+2D
[9 empty] | TOTAL DRAWING INKA | 26 | [6 empty] | #REF!
[9 empty] | TOTAL DRAWING IMS | 16 | [6 empty] | #REF!
[9 empty] | TOTAL DRAWING KERETA | 42 | [6 empty] | #REF!
[9 empty] | PROGRESS TOTAL | [8 empty] | #REF!
[9 empty] | PROGRESS INKA | [8 empty] | #REF!
[9 empty] | PROGRESS IMS | [8 empty] | #REF!
INKA

## M2 (E123)
[17 empty] | Project |  | : 16 TS KRL KCI (E12) | [8 empty] | WEIGHT LIMIT (KG) : |  | 8000 |  | JUMLAH |  | %-TASE
[9 empty] | TREE DIAGRAM & | [7 empty] | Document Number |  | : 201-TDD-H1005MB051-23 | [8 empty] | WEIGHT ESTIMATION (KG) |  | 9228.86 |  | DRAWING | RELEASE
[9 empty] | WEIGHT CALCULATION | [7 empty] | Date of Issue |  | : JANUARI 2023 | [8 empty] | PROGRESS TOTAL |  | 57.14% | PDR | 32 | 32 | 100%
[17 empty] | Revision |  | : 0 | [11 empty] | IDR | 5 | 4 | 80%
[17 empty] | Page |  | : | [11 empty] | FDR | 39 | 24 | 61.54%
[17 empty] | Car Type |  | : M2 | [12 empty] | 76 | 60
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK (SOW) | WEIGHT EST. (KG) | Tanggal Pengambilan Berat | Target Release | WEIGHT EST. (KG)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7
1 | 201-BRM-H1005MB051-23 | [7 empty] | BOM RAW MATERIAL | [12 empty] | RELEASE
2 | 203-BRM-H1005MB051-23 | [7 empty] | BOM PIECE PART | [12 empty] | RELEASE
3 | 000E1220100 | [7 empty] | GA M2 KRL KCI 2022
4 |  | 000E1202000 | [6 empty] | TRAILLER BOGIE ASSEMBLY
5 |  | 002E1230200 | [6 empty] | CARBODY SET M2
6 |  |  | 200E1230100 | [5 empty] | CARBODY SHEEL M2 | [11 empty] | BOY
7 |  |  |  | 210E1230100 |  |  |  |  | UNDERFRAME ARRANGEMENT (M2) |  |  |  | • | [12 empty] | 5060.46
8 |  |  |  |  | 210E1220200 |  |  |  | MAIN COSTRUCTION OF UNDERFRAME M1, M2 | 1 |  | • | • | • | • | • | [5 empty] | RELEASE |  |  |  |  | 4325 |  |  |  | PDR | RELEASE
9 | [5 empty] | 211E1220100 |  |  | END PART ASSEMBLY | 2 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
10 | [6 empty] | 211E1200200 |  | END PART | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
11 | [6 empty] | 212E1200100 |  | BOLSTER | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
12 | [5 empty] | 211E1200300 |  |  | ANTI CLIMBER 02 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
13 | [5 empty] | 213E1200100 |  |  | MIDDLE PART ASSY | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
14 | [5 empty] | 213E1220200 |  |  | BACKING MIDDLE PART ASSY | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
15 | [5 empty] | 213K5600200 |  |  | JACKING PAD | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
16 |  |  |  |  | 214E1220100 |  |  |  | FLOOR CONSTRUCTION M1, M2 | 1 |  | • | • | [13 empty] | 341.1 |  |  |  |  | 0
17 | [5 empty] | 214E1220200 |  |  | ARRG FLOOR ON PASSENGER ROOM | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
18 |  |  |  |  | 215E1230100 |  |  |  | ARR SUPORTING FRAME FOR FLOOR M1, M2 | 1 |  | • | • | [13 empty] | 197 |  |  |  |  | 0
19 | [5 empty] | 215E1220200 |  |  | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
20 | [5 empty] | 215E1220300 |  |  | DRAIN PIPE AND SUPPORT | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
21 | [5 empty] | 215E1220400 |  |  | TAPPING STRIP | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
22 | [5 empty] | 215E1220500 |  |  | TAPPING FOR PASSENGER SEAT ON FLOOR | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | IDR | RELEASE
23 | [5 empty] | 215E1220600 |  |  | TAPPING FOR DOOR POCKET &INTERIOR CABINET | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | IDR | RELEASE
24 | [5 empty] | 215E1220700 |  |  | TAPPING STRIP FOR EVACUATION LINE | 1 |  | • | • | [8 empty] | 0 | [9 empty] | 0
25 |  |  |  |  | 218E1230100 |  |  |  | ARRANGEMENT BRACKET & FRAME ON U/F M2 | 1 |  |  | • | [13 empty] | 197.36 |  |  |  |  | 0
26 | [5 empty] | 218E1200200 |  |  | BRACKET FOR GROUNDING INTER CAR | 1 |  | • | • | • | • | • |  |  |  |  | HADI | 0 | [8 empty] | FDR | 0
27 | [5 empty] | 218E1200300 |  |  | BRACKET FOR LEVELING VALVE | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | FDR | RELEASE
28 | [5 empty] | 218E1230400 |  |  | BRACKET FOR COUPLER SUPPORT | 1 |  |  | • | [8 empty] | FOR REVIEW | [8 empty] | IDR | FOR REVIEW
29 | [5 empty] | 218E1200500 |  |  | BRACKET FOR LADDER | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | FDR | RELEASE
30 | [5 empty] | 218E1220600 |  |  | BRACKET VVVF | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | FDR | RELEASE
31 | [5 empty] | 218E1220700 |  |  | BRACKET ELECTRIC CONTROL PANEL | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | FDR | RELEASE
32 | [5 empty] | 218E1220800 |  |  | BRACKET BRAKE RESISTOR | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | FDR | RELEASE
33 | [5 empty] | 218E1220900 |  |  | BRACKET CHOPPER BOX | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | FDR | RELEASE
34 | [5 empty] | 218E1221000 |  |  | BRACKET CHOPPER REACTOR | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | FDR | RELEASE
35 | [5 empty] | 218E1221100 |  |  | BRACKET OF AIR RESEVOIR (100L) | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | FDR | RELEASE
36 | [5 empty] | 218E1221200 |  |  | BRACKET OF BRAKE CONTROL UNIT | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | FDR | RELEASE
37 | [5 empty] | 218E1221300 |  |  | BRACKET OF CABLE DUCTING | 1 |  | • | • | [7 empty] | KAFI | FOR REVIEW | [8 empty] | FDR | FOR REVIEW
38 | [5 empty] | 218E1231400 |  |  | BRACKET OF PNEUMATIC PIPING | 1 |  |  | • | [7 empty] | KAFI | WORKING | [8 empty] | FDR | WORKING
39 | [5 empty] | 218E1231500 |  |  | BRACKET MAIN AIR RESEVOIR | 1 |  |  | • | [7 empty] | BOY | RELEASE |  | 30.1-E12023 |  |  |  |  | 12.9 |  | FDR | RELEASE
40 | [5 empty] | 218E1231600 |  |  | BRACKET OF FILTER REACTOR | 1 |  |  | • | [7 empty] | BOY | WORKING |  | 30.1-E12307 | [6 empty] | FDR | WORKING
41 | [5 empty] | 218E1231700 |  |  | BRACKET OF AIR SUPPLY MODUL | 1 |  |  | • | [7 empty] | BOY | WORKING |  | 30.1-E12022 | [6 empty] | FDR | WORKING
42 | [5 empty] | 218E1231800 |  |  | BRACKET OF COMPRESSOR CONTROL BOX | 1 |  |  | • | [7 empty] | boy | WORKING |  | 30.1-E12024 | [6 empty] | FDR | WORKING
43 | [5 empty] | 218E1231900 |  |  | BRACKET OF EXPANSION BOX | 1 |  |  | • | [7 empty] | BOY | WORKING |  | 30.1-E12321 | [6 empty] | FDR | WORKING
44 | [5 empty] | 218E1232000 |  |  | BRACKET OF LGS (GROUND SWITCH) | 1 |  |  | • | [18 empty] | 0
45 | [5 empty] | 218E1232100 |  |  | BRACKET OF TERMINAL BOX | 1 |  |  | • | [17 empty] | FDR | 0
46 | [5 empty] | 218E1232200 |  |  | BRACKET OF GROUNDING PLATE | 1 |  |  | • | [17 empty] | FDR | 0
47 | [5 empty] | 218E1222300 |  |  | BRACKET OF TRACTION MOTOR JUNCTION BOX | [11 empty] | INDRA | WORKING |  | 30.1-E12212
48 | [5 empty] | 218E1232400 |  |  | CABLE DIRECTOR ON UNDERFRAME | 1 |  |  | • | [8 empty] | WORKING | [8 empty] | FDR | WORKING
49 |  |  |  | 220E1230100 |  |  |  |  | SIDEWALL ARRANGEMENT M2 | 1 |  |  | • | [12 empty] | 2008.5 | [5 empty] | 0
50 |  |  |  |  | 221E1200200 |  |  |  | SIDEWALL CONSTRUCTION M | 1 |  | • | • | • | • | • | [5 empty] | RELEASE |  |  |  |  | 1730 |  |  |  | PDR | RELEASE
51 | [5 empty] | 221E1200300 |  |  | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
52 | [5 empty] | 221E1200400 |  |  | MIDDLE SIDEWALL 2 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
53 | [5 empty] | 221E1200600 |  |  | END SIDEWALL 2 --> (RIGHT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
54 | [5 empty] | 221E1200700 |  |  | PASSENGER ENTRANCE | 8 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
55 | [5 empty] | 221E1220800 |  |  | ARR GUSSET ON SIDEWALL M1,M2 | 1 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
56 | [5 empty] | 221E1201000 |  |  | SIDEWALL DOOR SUPPORT 1 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
57 | [5 empty] | 221E1201100 |  |  | SIDEWALL DOOR SUPPORT 2 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
58 | [5 empty] | 221E1201200 |  |  | SIDEWALL DOOR SUPPORT 3 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
59 | [5 empty] | 221E1220300 |  |  | MIDDLE SIDEWALL 2 --> (DUCT MOTOR) | 2 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
60 | [5 empty] | 221E1220400 |  |  | END SIDEWALL 3 --> (DUCT MOTOR) | 2 |  | • | • | [8 empty] | RELEASE | [8 empty] | PDR | RELEASE
61 |  |  |  |  | 228E1220100 |  |  |  | ARR BRACKET ON SIDE WALL M2 |  |  |  | • | [13 empty] | 278.5 |  |  |  |  | 0
62 | [5 empty] | 228E1220200 |  |  | ARRANGEMENT OF ADAPTER ON SIDEWALL |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | IDR | RELEASE
63 | [5 empty] | 228E1200300 |  |  | BRACKET FOR CURTAIN |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
64 | [5 empty] | 228E1200400 |  |  | BRACKET FOR DOOR ENGINE ENTRANCE |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
65 | [5 empty] | 228E1200500 |  |  | BRACKET FOR LUGGAGE RACK |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
66 | [5 empty] | 228E1200600 |  |  | BRACKET FOR EMERGENCY DOOR RELEASE |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | FDR | RELEASE
67 | [5 empty] | 228E1200700 |  |  | BRACKET FOR RUNNING TEXT |  |  | • | • | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [7 empty] | 0 | FDR | RELEASE
68 | [5 empty] | 228E1200800 |  |  | BRACKET FOR AC PANEL |  |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  |  | FOR REVIEW | [8 empty] | FDR | FOR REVIEW
69 | [5 empty] | 228E1200900 |  |  | BRACKET FOR FOLDING SEAT |  |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
70 | [5 empty] | 228E1201000 |  |  | BRACKET FOR SIDEWALL & ENDWALL PANEL |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
71 | [5 empty] | 228E1201100 |  |  | BRACKET ROLL FILTER PANEL |  | • | • | • | • | • | • |  |  |  |  | DICKY
72 | [5 empty] | 228E1221200 |  |  | HOLE FOR INDICATOR LAMP ON SIDEWALL | [12 empty] | RELEASE
73 | [5 empty] | 228E1201300 |  |  | STIFFENER ON TAPPING SIDEWALL | [12 empty] | RELEASE
74 | [5 empty] | 228E1201400 |  |  | CABLE DIRECTOR ON SIDEWALL | [12 empty] | RELEASE
75 |  |  |  | 230E1220100 |  |  |  |  | ENDWALL ARRANGEMENT M2 |  |  |  | • | [12 empty] | 381.9 | [5 empty] | 0
76 |  |  |  |  | 231E1200100 |  |  |  | MAIN CONSTRUCTION OF ENDWALL | 2 | • | • | • | • | • | • | [5 empty] | RELEASE |  |  |  |  | 362 |  |  |  | PDR | RELEASE
77 | [5 empty] | 231E1200200 |  |  | END FRAMING |  | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
78 | [5 empty] | 231E1200300 |  |  | END SHEETING |  | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
79 |  |  |  |  | 238E1200100 |  |  |  | ARR BRACKET ON ENDWALL M2 | 1 |  |  | • | [13 empty] | 19.9 |  |  |  |  | 0
80 | [5 empty] | 238E1200200 |  |  | ARRANGEMENT ADAPTER ON ENDWALL | 1 | [11 empty] | RELEASE | [8 empty] | FDR | RELEASE
81 | [5 empty] | 238E1200300 |  |  | BRACKET FOR DOOR CLOSER | 1 | [11 empty] | RELEASE | [8 empty] | FDR | RELEASE
82 | [5 empty] | 238E1200400 |  |  | BRACKET ENDWALL PANEL | 1 | [11 empty] | RELEASE | [8 empty] | FDR | RELEASE
83 | [5 empty] | 238E1200500 |  |  | DIRECTOR CABLE ON ON ENDWALL | 1 | [20 empty] | FDR | 0
84 | [5 empty] | 238E1200600 |  |  | TAPPING FOR FALLING PROTECTOR | 1 | [6 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
85 |  |  |  | 250E1220100 |  |  |  |  | ROOF ARRANGEMENT M2 |  |  |  | • | [12 empty] | 1778 | [5 empty] | 0
86 |  |  |  |  | 251E1200100 |  |  |  | MAIN CONSTRUCTION OF ROOF |  |  |  | • | [8 empty] | RELEASE |  |  |  |  | 1516 |  |  |  | PDR | RELEASE
87 | [5 empty] | 251E1200200 |  |  | ROOF FRAMING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
88 | [5 empty] | 251E1200300 |  |  | ROOF SHEATING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
89 | [5 empty] | 251E1200400 |  |  | ROOF FRAMING AC |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
90 | [5 empty] | 251E1200500 |  |  | ARR GUSSET ON ROOF M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
91 | [5 empty] | 251E1200600 |  |  | RAIN GUTTER M, T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
92 |  |  |  |  | 255E1220100 |  |  |  | ARR CEILLING FRAMING M2 |  |  |  | • | [13 empty] | 144 |  |  |  |  | 0
93 | [5 empty] | 255E1200200 |  |  | CEILLING FRAMING PASSANGER ROOM | [11 empty] | BOY | FOR REVIEW | [8 empty] | FDR | FOR REVIEW
94 | [5 empty] | 255E1200400 |  |  | BRACKET FOR ROLL FILTER | [12 empty] | RELEASE
95 |  |  |  |  | 258E1230100 |  |  |  | ARR BRACKET ON ROOF M2 |  |  |  | • | [13 empty] | 118 |  |  |  |  | 0
96 | [5 empty] | 258E1200200 |  |  | ARRANGEMENT ADAPTER ON ROOF |  |  |  | • | • | • | • | CEK | CEK |  |  | CANDRA | RELEASE | [8 empty] | IDR | RELEASE
97 | [5 empty] | 258E1200300 |  |  | CABLE DIRECTOR ON ROOF |  |  |  | • | • | • | • |  |  |  |  | BOY | FOR REVIEW | [8 empty] | FDR | FOR REVIEW
98 | [5 empty] | 258E1200400 |  |  | BRACKET FOR EXTERIOR SPEAKER |  |  |  | • | • | • | • | [5 empty] | RELEASE | [8 empty] | FDR | RELEASE
99 | [5 empty] | 258E1200500 |  |  | BRACKET FOR DOOR POCKET |  |  |  | • | • | • | • | CEK | CEK |  |  | CANDRA | RELEASE | [8 empty] | FDR | RELEASE
100 | [5 empty] | 258E1200600 |  |  | BRACKET FOR ELECTRICAL CABINET |  |  |  | • | • | • | • | [5 empty] | RELEASE | [8 empty] | FDR | RELEASE
101 | [5 empty] | 258E1200700 |  |  | BRACKET FOR DOOR CONTROL UNIT |  |  |  | • | • | • | • | WORKING | WORKING |  |  | CANDRA | PRE-RELEASE | [8 empty] | FDR | PRE-RELEASE
102 | [5 empty] | 258E1200800 |  |  | CABLE DIRECTOR ON REAR ROOF FRAME | [11 empty] | HADI | FOR REVIEW
BATASBAWAH
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Fathur Rokhman Hidayat) | [9 empty] | (Hernawan Prasanto) | [12 empty] | ( Kristanto)
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | BERAT (SEBELUM PENGURANGAN) |  | BERAT (SETELAH PENGURANGAN) | SELISIH BERAT |  |  | DRAWING YANG BELUM
[8 empty] | 1 | BOM RAW MATERIAL | 2 |  | 2 |  | 100%
[8 empty] | 1 | MAIN COSTRUCTION OF UNDERFRAME M1, M2 | 8 |  | 8 |  | 100% |  | 4325 |  | 3864 | 461 |  |  | 0
[8 empty] | 2 | SIDEWALL CONSTRUCTION M | 11 |  | 11 |  | 100% |  | 1730 |  | 1730 |  |  |  | 0
[8 empty] | 3 | MAIN CONSTRUCTION OF ENDWALL | 3 |  | 3 |  | 100% |  | 362 |  | 362 |  |  |  | 0
[8 empty] | 4 | MAIN CONSTRUCTION OF ROOF | 6 |  | 6 |  | 100% |  | 1516 |  | 1516 |  |  |  | 0
[9 empty] | GREEN CAR | 30 |  | 30 |  | 80% |  | 7933 |  | 7472
[8 empty] | 1 | FLOOR CONSTRUCTION M1, M2 | 2 |  | 1 |  | 50% |  | 341.1 |  | 341.1 |  | 538.1 |  | 0
[8 empty] | 2 | ARR SUPORTING FRAME FOR FLOOR M1, M2 | 6 |  | 5 |  | 83.33% |  | 197 |  | 197 |  |  |  | 0
[8 empty] | 3 | ARRANGEMENT BRACKET & FRAME ON U/F M2 | 24 |  | 10 |  | 41.67% |  | 197.36 |  | 197.36 |  | 757.76 |  | 14
[8 empty] | 4 | ARR BRACKET ON SIDE WALL M2 | 9 |  | 7 |  | 77.78% |  | 278.5 |  | 278.5 |  |  |  | 2
[8 empty] | 5 | ARR BRACKET ON ENDWALL M2 | 6 |  | 4 |  | 66.67% |  | 19.9 |  | 19.9 |  |  |  | 2
[8 empty] | 6 | ARR CEILLING FRAMING M2 | 2 |  | 0 |  | 0% |  | 144 |  | 144 |  |  |  | 1
[8 empty] | 7 | ARR BRACKET ON ROOF M2 | 7 |  | 4 |  | 57.14% |  | 118 |  | 118 | 2 |  |  | 4
[9 empty] | BRACKET AND SUPPORT | 56 |  | 31 |  | 11.07% |  | 1295.86 |  | 560.4
[9 empty] | TOTAL DRAWING/BERAT KERETA | 116 |  | 91 |  |  |  | 9228.86 |  | 8032.4
[9 empty] | PROGRESS TOTAL |  |  |  |  | 91.07%
Note on Z8: PENGISIAN BERAT DI LVL 5 (MAIN ASSY)
INKA

## T1 (E124)
[17 empty] | Project |  | : 16 TS E12 KCI (E12) | [5 empty] | WEIGHT LIMIT (KG) : |  | 8000 | [5 empty] | JUMLAH |  | %-TASE
[9 empty] | TREE DIAGRAM & | [7 empty] | Document Number |  | : 201-TDD-H1005MB051-23 | [5 empty] | WEIGHT ESTIMATION (KG) |  | 9028.3 | [5 empty] | DRAWING | RELEASE
[9 empty] | WEIGHT CALCULATION | [7 empty] | Date of Issue |  | : JANUARI 2023 | [5 empty] | PROGRESS TOTAL |  | 66.67% |  |  |  |  | PDR | 30 | 30 | 100%
[17 empty] | Revision |  | : 0 | [12 empty] | IDR | 2 | 2 | 100%
[17 empty] | Page |  | : | [12 empty] | FDR | 43 | 18 | 41.86%
[17 empty] | Car Type |  | : T1 | [13 empty] | 75 | 50
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK (SOW) | WEIGHT EST. (KG) | Tanggal Pengambilan Berat | Update Berat | WEIGHT EST. (KG)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7
1 | 201-BRM-H1005MB051-23 | [7 empty] | BOM RAW MATERIAL | [12 empty] | RELEASE
2 | 203-BRM-H1005MB051-23 | [7 empty] | BOM PIECE PART | [12 empty] | RELEASE
3 | 000E1240100 | [7 empty] | GA T E12 KCI 2022
4 |  | 000E1202000 | [6 empty] | TRAILLER BOGIE ASSEMBLY
5 |  | 000E1240200 | [6 empty] | CARBODY SET T1 | 1
6 |  |  | 200E1240100 | [5 empty] | CARBODY SHEEL T1 | 1 | [10 empty] | INDRA
7 |  |  |  | 210E1240100 |  |  |  |  | UNDERFRAME ARRANGEMENT T1 | 1 |  |  |  | • | [10 empty] | 4847
8 |  |  |  |  | 210E1240200 |  |  |  | MAIN COSTRUCTION OF UNDERFRAME T1, T2, T3 | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [5 empty] | 4306 |  |  | 4115.6 | PDR | RELEASE
9 | [5 empty] | 211E1200100 |  |  | END PART ASSEMBLY | 2 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 2942 |  |  | PDR | RELEASE
10 | [6 empty] | 211E1200200 |  | END PART | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [9 empty] | PDR | RELEASE
11 | [6 empty] | 212E1200100 |  | BOLSTER | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [9 empty] | PDR | RELEASE
12 | [5 empty] | 211E1200300 |  |  | ANTI CLIMBER 02 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 40 |  |  | PDR | RELEASE
13 | [5 empty] | 213E1200100 |  |  | MIDDLE PART ASSY | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 1341 |  | 1112 | PDR | RELEASE
14 | [5 empty] | 213K5600200 |  |  | JACKING PAD | 4 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 21.6 | 5.4 |  | PDR | RELEASE
15 |  |  |  |  | 214E1240100 |  |  |  | FLOOR CONSTRUCTION | 1 |  |  |  | • | [13 empty] | 344 |  |  |  |  | 0
16 | [5 empty] | 214E1240200 |  |  | ARRG FLOOR ON PASSENGER ROOM | 1 |  |  |  | • |  |  | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [9 empty] | PDR | RELEASE
17 |  |  |  |  | 215E1240100 |  |  |  | ARR SUPORTING FRAME FOR FLOOR | 1 |  |  |  | • | [13 empty] | 197 |  |  |  |  | 0
18 | [5 empty] | 215E1240200 |  |  | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | 1 |  |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE |  | BUTUH REVISI | [7 empty] | PDR | RELEASE
19 | [5 empty] | 215E1240300 |  |  | DRAIN PIPE AND SUPPORT | 1 |  |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE |  | BUTUH REVISI | [7 empty] | PDR | RELEASE
20 | [5 empty] | 215E1240400 |  |  | TAPPING STRIP | 1 |  |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [9 empty] | PDR | RELEASE
21 | [5 empty] | 215E1240500 |  |  | TAPPING FOR PASSENGER SEAT ON FLOOR | 1 |  |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  | IFA | RELEASE | [9 empty] | FDR | RELEASE
22 | [5 empty] | 215E1240600 |  |  | TAPPING FOR INTERIOR CABINET | 1 |  |  |  | • | • | • | FOR REVIEW | FOR REVIEW |  | √ | IFA | RELEASE |  | BUTUH CEK | [7 empty] | FDR | RELEASE
23 | [5 empty] | 215E1240700 |  |  | TAPPING STRIP FOR EVACUATION LINE | 1 |  |  |  | • | • | • | [16 empty] | 0
24 |  |  |  |  | 218E1240100 |  |  |  | ARRANGEMENT BRACKET & FRAME ON U/F | 1 |  |  |  | • | [13 empty] | 158.54 |  |  |  |  | 0
25 | [5 empty] | 218E1200200 |  |  | BRACKET FOR GROUNDING INTER CAR | 1 |  | • | • | • | • | • | [5 empty] | 0 | [9 empty] | FDR | 0
26 | [5 empty] | 218E1200300 |  |  | BRACKET FOR LEVELING VALVE | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 1.7 |  |  | FDR | RELEASE
27 | [5 empty] | 218E1240400 |  |  | BRACKET FOR COUPLER SUPPORT | 1 |  |  |  | • | • | • | [5 empty] | FOR REVIEW | [6 empty] | 15.6 |  |  | FDR | FOR REVIEW
28 | [5 empty] | 218E1200500 |  |  | BRACKET FOR LADDER | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 1.1 |  |  | FDR | RELEASE
29 | [5 empty] | 218E1240600 |  |  | BRACKET OF ELECTRIC CONTROL PANEL | 1 |  |  |  | • | • | • |  |  |  |  | KAFI | FOR REVIEW |  | 30.1-E12113 TC1 |  |  |  |  | 3.8 |  |  | FDR | FOR REVIEW
30 | [5 empty] | 218E1240700 |  |  | BRACKET OF BRAKE CONTROL UNIT | 1 |  |  |  | • | • | • |  |  |  |  | KAFI | FOR REVIEW |  | 30.1-E12103 TC1 |  |  |  |  | 0.66 |  |  | FDR | FOR REVIEW
31 | [5 empty] | 218E1240800 |  |  | BRACKET OF AIR RESEVOIR (100L) | 1 |  |  |  | • | • | • |  |  |  |  | KAFI | RELEASE |  | 30.1-E12104 TC1 |  |  |  |  | 14.78 |  |  | FDR | RELEASE
32 | [5 empty] | 218E1240900 |  |  | BRACKET OF LGS (GROUND SWITCH) | 1 |  |  |  | • | • | • | [15 empty] | FDR | 0
33 | [5 empty] | 218E1241000 |  |  | BRACKET OF CABLE DUCTING | 1 |  |  |  | • | [6 empty] | INDRA | FOR REVIEW | [6 empty] | 32 |  |  | FDR | FOR REVIEW
34 | [5 empty] | 218E1241100 |  |  | BRACKET OF PNEUMATIC PIPING | 1 |  |  |  | • |  | • |  |  |  |  | INDRA | FOR REVIEW | [6 empty] | 20.8 |  |  | FDR | FOR REVIEW
35 | [5 empty] | 218E1241200 |  |  | BRACKET OF TRANSFORMER FILTER BOX | 1 |  |  |  | • | [6 empty] | KAFI | WORKING |  | 30.1-E12107 & 21.8-E12115 |  |  |  |  | 31 |  |  | FDR | WORKING
36 | [5 empty] | 218E1241300 |  |  | BRACKET OF APS BOX | 1 |  |  |  | • | [6 empty] | KAFI | WORKING |  | 30.1-E12106&TC1 |  |  |  |  | 10.3 |  |  | FDR | WORKING
37 | [5 empty] | 218E1241400 |  |  | BRACKET OF RECTIFIER BOX | 1 |  |  |  | • | [6 empty] | KAFI | WORKING |  | 30.1-E12112 & TC1 |  |  |  |  | 4.3 |  |  | FDR | WORKING
38 | [5 empty] | 218E1241500 |  |  | BRACKET OF AUXILIARY SWITCH | 1 |  |  |  | • | [6 empty] | KAFI | WORKING |  | 30.1-E12110&TC1 |  |  |  |  | 0.9 |  |  | FDR | WORKING
39 | [5 empty] | 218E1241600 |  |  | BRACKET OF IVHB | 1 |  |  |  | • | [6 empty] | KAFI | FOR REVIEW |  | 30.1-E12411 |  |  |  |  | 4 |  |  | FDR | FOR REVIEW
40 | [5 empty] | 218E1241700 |  |  | BRACKET OF BATTERY BOX | 1 |  |  |  | • | [6 empty] | INDRA | WORKING |  | 30.1-E12408 |  |  |  |  | 1.8 |  |  | FDR | WORKING
41 | [5 empty] | 218E1241800 |  |  | BRACKET OF BATTERY PANEL | 1 |  |  |  | • | [17 empty] | FDR | 0
42 | [5 empty] | 218E1241900 |  |  | BRACKET OF HGS (GROUND SWITCH) | 1 |  |  |  | • | [6 empty] | INDRA | WORKING |  | 30.1-E12127 |  |  |  |  | 3.8 |  |  | FDR | WORKING
43 | [5 empty] | 218E1242000 |  |  | BRACKET OF EXPANSION BOX | 1 |  |  |  | • | [6 empty] | INDRA | FOR REVIEW |  | 30.1-E12421 | [7 empty] | FDR | FOR REVIEW
44 | [5 empty] | 218E1242100 |  |  | BRACKET OF TERMINAL BOX | 1 |  |  |  | • | [14 empty] | 0 |  |  | FDR | 0
45 | [5 empty] | 218E1242200 |  |  | BRACKET OF GROUNDING PLATE | 1 |  |  |  | • | [6 empty] | INDRA | WORKING | [6 empty] | 5 |  |  | FDR | WORKING
46 | [5 empty] | 218E1242300 |  |  | CABLE DIRECTOR ON UNDERFRAME | 1 |  |  |  | • | [6 empty] | INDRA | WORKING | [6 empty] | 7 |  |  | FDR | WORKING
47 |  |  |  | 220E1240100 |  |  |  |  | SIDEWALL ARRANGEMENT T1 | 8 |  |  |  | • | [10 empty] | 2001.5 | [7 empty] | 0
48 |  |  |  |  | 221E1240200 |  |  |  | SIDEWALL CONSTRUCTION T | 1 |  |  |  | • | • | • | [5 empty] | RELEASE |  |  |  | 2023-09-13 |  | 1723 |  |  |  | PDR | RELEASE
49 | [5 empty] | 221E1200300 |  |  | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 248 | 124 |  | PDR | RELEASE
50 | [5 empty] | 221E1200400 |  |  | MIDDLE SIDEWALL 2 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 496 | 124 |  | PDR | RELEASE
51 | [5 empty] | 221E1200500 |  |  | END SIDEWALL 1 --> (LEFT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 144.2 | 72.1 |  | PDR | RELEASE
52 | [5 empty] | 221E1200600 |  |  | END SIDEWALL 2 --> (RIGHT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 144.8 | 72.4 |  | PDR | RELEASE
53 | [5 empty] | 221E1200700 |  |  | PASSENGER ENTRANCE | 8 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 464.8 | 58.1 |  | PDR | RELEASE
54 | [5 empty] | 221E1200800 |  |  | ARR GUSSET ON SIDEWALL T | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [6 empty] | 62.3 | 62.3 |  | PDR | RELEASE
55 | [5 empty] | 221E1201000 |  |  | SIDEWALL DOOR SUPPORT 1 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 80 | 20 |  | PDR | RELEASE
56 | [5 empty] | 221E1201100 |  |  | SIDEWALL DOOR SUPPORT 2 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 39.8 | 19.9 |  | PDR | RELEASE
57 | [5 empty] | 221E1201200 |  |  | SIDEWALL DOOR SUPPORT 3 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 39.8 | 19.9 |  | PDR | RELEASE
58 |  |  |  |  | 228E1240100 |  |  |  | ARR BRACKET ON SIDE WALL T1 | 1 |  |  |  | • | [13 empty] | 278.5 |  |  |  |  | 0
59 | [5 empty] | 228E1240200 |  |  | ARRANGEMENT OF ADAPTER ON SIDEWALL | 1 |  |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [9 empty] | IDR | RELEASE
60 | [5 empty] | 228E1200300 |  |  | BRACKET FOR CURTAIN | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [9 empty] | FDR | RELEASE
61 | [5 empty] | 228E1200400 |  |  | BRACKET FOR DOOR ENGINE ENTRANCE | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [9 empty] | FDR | RELEASE
62 | [5 empty] | 228E1200500 |  |  | BRACKET FOR LUGGAGE RACK | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [9 empty] | FDR | RELEASE
63 | [5 empty] | 228E1200600 |  |  | BRACKET FOR EMERGENCY DOOR RELEASE | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [9 empty] | FDR | RELEASE
64 | [5 empty] | 228E1200700 |  |  | BRACKET FOR RUNNING TEXT | 1 |  | • | • | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [7 empty] | 0 |  | FDR | RELEASE
65 | [5 empty] | 228E1200800 |  |  | BRACKET FOR AC PANEL | 1 |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  |  | FOR REVIEW | [9 empty] | FDR | FOR REVIEW
66 | [5 empty] | 228E1200900 |  |  | BRACKET FOR FOLDING SEAT | 1 |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  |  | RELEASE | [9 empty] | FDR | RELEASE
67 | [5 empty] | 228E1201000 |  |  | BRACKET FOR SIDEWALL & ENDWALL PANEL | 1 |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [9 empty] | FDR | RELEASE
68 | [5 empty] | 228E1201100 |  |  | BRACKET ROLL FILTER PANEL | 1 | • | • | • | • | • | • |  |  |  |  | DICKY | FOR REVIEW
69 | [5 empty] | 228E1241200 |  |  | HOLE FOR INDICATOR LAMP ON SIDEWALL | 1 |  |  |  | • | • | • | [5 empty] | FOR REVIEW
70 | [5 empty] | 228E1201300 |  |  | STIFFENER ON TAPPING SIDEWALL | 1 |  | • | • | • | • | • | [5 empty] | RELEASE
71 | [5 empty] | 228E1201400 |  |  | CABLE DIRECTOR ON SIDEWALL |  |  | • | • | • | • | • | [5 empty] | RELEASE
72 |  |  |  | 230E1240100 |  |  |  |  | ENDWALL ARRANGEMENT T1 | 1 |  |  |  | • | [10 empty] | 381.9 | [7 empty] | 0
73 |  |  |  |  | 231E1200100 |  |  |  | MAIN CONSTRUCTION OF ENDWALL | 2 | • | • | • | • | • | • | [5 empty] | RELEASE |  |  |  | 2023-09-13 |  | 362 |  |  |  | PDR | RELEASE
74 | [5 empty] | 231E1200200 |  |  | END FRAMING | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [9 empty] | PDR | RELEASE
75 | [5 empty] | 231E1200300 |  |  | END SHEETING 1 | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [9 empty] | PDR | RELEASE
76 |  |  |  |  | 238E1200100 |  |  |  | ARR BRACKET ON ENDWALL T | 1 |  |  |  | • | [10 empty] | 19.9 |  |  | 19.9 |  |  |  |  | 0
77 | [5 empty] | 238E1200200 |  |  | ARRANGEMENT ADAPTER ON ENDWALL | 1 | [9 empty] | √ |  | RELEASE | [9 empty] | FDR
78 | [5 empty] | 238E1200300 |  |  | BRACKET FOR DOOR CLOSER | 1 | [9 empty] | √ |  | RELEASE | [9 empty] | FDR | RELEASE
79 | [5 empty] | 238E1200400 |  |  | BRACKET ENDWALL PANEL | [10 empty] | √ |  | RELEASE | [9 empty] | FDR | RELEASE
80 | [5 empty] | 238E1200500 |  |  | DIRECTOR CABLE ON ON ENDWALL | [22 empty] | FDR | 0
81 | [5 empty] | 238E1200600 |  |  | TAPPING FOR FALLING PROTECTOR | 1 | [6 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [9 empty] | FDR | RELEASE
82 |  |  |  | 250E1240100 |  |  |  |  | ROOF ARRANGEMENT T1 |  |  |  |  | • | [10 empty] | 1778 | [7 empty] | 0
83 |  |  |  |  | 251E1200100 |  |  |  | MAIN CONSTRUCTION OF ROOF T | 1 |  |  |  | • | [7 empty] | RELEASE |  |  |  | 2023-09-13 |  | 1516 |  |  |  | PDR | RELEASE
84 | [5 empty] | 251E1200200 |  |  | ROOF FRAMING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 305.5 |  |  | PDR | RELEASE
85 | [5 empty] | 251E1200300 |  |  | ROOF SHEATING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 398.6 |  |  | PDR | RELEASE
86 | [5 empty] | 251E1200400 |  |  | ROOF FRAMING AC |  |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 709.4 |  |  | PDR | RELEASE
87 | [5 empty] | 251E1200500 |  |  | ARR GUSSET ON ROOF M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 16.3 |  |  | PDR | RELEASE
88 | [5 empty] | 251E1200600 |  |  | RAIN GUTTER M, T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 150.1 |  |  | PDR | RELEASE
89 |  |  |  |  | 255E1240100 |  |  |  | ARR CEILLING FRAMING T1 | 1 |  |  |  | • | [13 empty] | 144 |  |  |  |  | 0
90 | [5 empty] | 255E1200200 |  |  | CEILLING FRAMING PASSANGER ROOM (T) | [22 empty] | FDR | 0
91 | [5 empty] | 255E1200400 |  |  | BRACKET FOR ROLL FILTER | [12 empty] | RELEASE
92 |  |  |  |  | 258E1240100 |  |  |  | ARR BRACKET ON ROOF T1 | 1 |  |  |  | • | [13 empty] | 118 |  |  |  |  | 0
93 | [5 empty] | 258E1200200 |  |  | ARRANGEMENT ADAPTER ON ROOF | [12 empty] | RELEASE | [6 empty] | 21 |  |  | IDR | RELEASE
94 | [5 empty] | 258E1200300 |  |  | CABLE DIRECTOR ON ROOF | [12 empty] | FOR REVIEW | [6 empty] | 8 |  |  | FDR | FOR REVIEW
95 | [5 empty] | 258E1200400 |  |  | BRACKET FOR EXTERIOR SPEAKER | [12 empty] | RELEASE | [6 empty] | 0.9 |  |  | FDR | RELEASE
96 | [5 empty] | 258E1200500 |  |  | BRACKET FOR DOOR POCKET | [12 empty] | RELEASE | [6 empty] | 55 |  |  | FDR | RELEASE
97 | [5 empty] | 258E1200600 |  |  | BRACKET FOR ELECTRICAL CABINET | [12 empty] | RELEASE | [6 empty] | 3.1 |  |  | FDR | RELEASE
98 | [5 empty] | 258E1200700 |  |  | BRACKET FOR DOOR CONTROL UNIT | [12 empty] | PRE-RELEASE | [6 empty] | 30 |  |  | FDR | PRE-RELEASE
99 | [5 empty] | 258E1200800 |  |  | CABLE DIRECTOR ON REAR ROOF FRAME | [12 empty] | FOR REVIEW
BATASBAWAH
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Fathur Rokhman Hidayat) | [9 empty] | (Hernawan Prasanto) | [12 empty] | ( Kristanto)
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | BERAT (SEBELUM PENGURANGAN) |  | BERAT (SETELAH PENGURANGAN) | SELISIH BERAT | DRAWING YANG BELUM
[8 empty] | 1 | BOM RAW MATERIAL | 2 |  | 2 |  | 100%
[8 empty] | 1 | MAIN COSTRUCTION OF UNDERFRAME T1, T2, T3 | 7 |  | 7 |  | 100% |  | 4306 |  | 3844 |  | 0
[8 empty] | 2 | SIDEWALL CONSTRUCTION T | 10 |  | 10 |  | 100% |  | 1723 |  |  |  | 0
[8 empty] | 3 | MAIN CONSTRUCTION OF ENDWALL | 3 |  | 3 |  | 100% |  | 362 |  |  |  | 0
[8 empty] | 4 | MAIN CONSTRUCTION OF ROOF T | 6 |  | 6 |  | 100% |  | 1516 |  |  |  | 0
[9 empty] | GREEN CAR | 28 |  | 28 |  | 80% |  | 7907
[8 empty] | 1 | FLOOR CONSTRUCTION | 2 |  | 1 |  | 50% |  | 344 |  |  |  | 0
[8 empty] | 2 | ARR SUPORTING FRAME FOR FLOOR | 7 |  | 5 |  | 71.43% |  | 197 |  |  |  | 0
[8 empty] | 3 | ARRANGEMENT BRACKET & FRAME ON U/F | 23 |  | 3 |  | 13.04% |  | 158.54 |  |  |  | 21 | 718.94
[8 empty] | 4 | ARR BRACKET ON SIDE WALL T1 | 8 |  | 7 |  | 87.5% |  | 278.5 |  |  |  | 2
[8 empty] | 5 | ARR BRACKET ON ENDWALL T | 5 |  | 4 |  | 80% |  | 19.9 |  |  |  | 2
[8 empty] | 6 | ARR CEILLING FRAMING T1 | 2 |  | 0 |  | 0% |  | 144 |  |  |  | 0
[8 empty] | 7 | ARR BRACKET ON ROOF T1 | 6 |  | 4 |  | 66.67% |  | 118 |  |  |  | 4
[9 empty] | BRACKET AND SUPPORT | 53 |  | 24 |  | 9.057% |  | 1259.94
[9 empty] | TOTAL DRAWING/BERAT KERETA | 107 |  | 78 |  |  |  | 9166.94
[9 empty] | PROGRESS TOTAL |  |  |  |  | 89.06%
DRAWING UNTUK KEBUTUHAN CARBODY ASSY
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | SCOPE OF WORK
[8 empty] | 1 | CARBODY SHEEL T1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 2 | SIDEWALL ARRANGEMENT T1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 3 | ENDWALL ARRANGEMENT T1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 4 | ROOF ARRANGEMENT T1 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[9 empty] | TOTAL DRAWING INKA | 4 |  | 0
[9 empty] | PROGRESS INKA |  |  |  |  | 0%
INKA

## T2 (E125)
[17 empty] | Project |  | : 16 TS E12 KCI (E12) | [8 empty] | WEIGHT LIMIT (KG) : |  | 8000 |  | JUMLAH |  | %-TASE
[9 empty] | TREE DIAGRAM & | [7 empty] | Document Number |  | : 201-TDD-H1005MB051-23 | [8 empty] | WEIGHT ESTIMATION (KG) |  | 9169.24 |  | DRAWING | RELEASE
[9 empty] | WEIGHT CALCULATION | [7 empty] | Date of Issue |  | : JANUARI 2023 | [8 empty] | PROGRESS TOTAL |  | 0% | PDR | 30 | 30 | 100%
[17 empty] | Revision |  | : 0 | [11 empty] | IDR | 2 | 2 | 100%
[17 empty] | Page |  | : | [11 empty] | FDR | 37 | 18 | 48.65%
[17 empty] | Car Type |  | : T2 | [12 empty] | 69 | 50
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK (SOW) | WEIGHT EST. (KG) | Tanggal Pengambilan Berat | Target Release | WEIGHT EST. (KG)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7
1 | 201-BRM-H1005MB051-23 | [7 empty] | BOM RAW MATERIAL | [12 empty] | RELEASE
2 | 203-BRM-H1005MB051-23 | [7 empty] | BOM PIECE PART | [12 empty] | RELEASE
3 | 000E1250100 | [7 empty] | GA T E12 KCI 2022
4 |  | 000E1202000 | [6 empty] | TRAILLER BOGIE ASSEMBLY
5 |  | 000E1250200 | [6 empty] | CARBODY SET T2 | 1
6 |  |  | 200E1250100 | [5 empty] | CARBODY SHEEL T2 | 1 | [10 empty] | INDRA
7 |  |  |  | 210E1250100 |  |  |  |  | UNDERFRAME ASSY T2 | 1 |  |  |  |  | • | [9 empty] | 4989.44
8 |  |  |  |  | 210E1240200 |  |  |  | MAIN COSTRUCTION OF UNDERFRAME T | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [5 empty] | 4306 |  |  | PDR | RELEASE
9 | [5 empty] | 211E1200100 |  |  | END PART ASSEMBLY | 2 |  |  |  | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
10 | [6 empty] | 211E1200200 |  | END PART | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
11 | [6 empty] | 212E1200100 |  | BOLSTER | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
12 | [5 empty] | 211E1200300 |  |  | ANTI CLIMBER 02 | 4 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
13 | [5 empty] | 213E1200100 |  |  | MIDDLE PART ASSY | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
14 | [5 empty] | 213K5600200 |  |  | JACKING PAD | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
15 |  |  |  |  | 214E1250100 |  |  |  | FLOOR CONSTRUCTION | [18 empty] | 344 |  |  |  | 0
16 | [5 empty] | 214E1240200 |  |  | ARRG FLOOR ON PASSENGER ROOM | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
17 |  |  |  |  | 215E1250100 |  |  |  | ARR SUPORTING FRAME FOR FLOOR | [5 empty] | • | [12 empty] | 197 |  |  |  | 0
18 | [5 empty] | 215E1240200 |  |  | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
19 | [5 empty] | 215E1240300 |  |  | DRAIN PIPE AND SUPPORT | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
20 | [5 empty] | 215E1240400 |  |  | TAPPING STRIP | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
21 | [5 empty] | 215E1240500 |  |  | TAPPING FOR PASSENGER SEAT ON FLOOR | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
22 | [5 empty] | 215E1240600 |  |  | TAPPING FOR INTERIOR CABINET | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
23 | [5 empty] | 215E1240700 |  |  | TAPPING STRIP FOR EVACUATION LINE | [22 empty] | 0
24 |  |  |  |  | 218E1250100 |  |  |  | ARRANGEMENT BRACKET & FRAME ON U/F | [5 empty] | • | [12 empty] | 142.44 |  |  |  | 0
25 | [5 empty] | 218E1200200 |  |  | BRACKET FOR GROUNDING INTER CAR | 1 |  | • | • | • | • | • | [5 empty] | 0 | [8 empty] | FDR | 0
26 | [5 empty] | 218E1200300 |  |  | BRACKET FOR LEVELING VALVE | 1 |  | • | • | • | • | • | [5 empty] | RELEASE |  |  | 1.7 |  |  |  | 1.7 |  | FDR | RELEASE
27 | [5 empty] | 218E1240400 |  |  | BRACKET FOR COUPLER SUPPORT | 1 |  |  |  | • | • | • | [5 empty] | FOR REVIEW |  |  | 15.6 |  |  |  | 15.6 |  | FDR | FOR REVIEW
28 | [5 empty] | 218E1200500 |  |  | BRACKET FOR LADDER | 1 |  | • | • | • | • | • | [5 empty] | RELEASE |  |  | 1.1 |  |  |  | 1.1 |  | FDR | RELEASE
29 | [5 empty] | 218E1240600 |  |  | BRACKET OF ELECTRIC CONTROL PANEL | 1 |  |  |  | • | • | • | [5 empty] | FOR REVIEW | [6 empty] | 3.8 |  | FDR | FOR REVIEW
30 | [5 empty] | 218E1240700 |  |  | BRACKET OF BRAKE CONTROL MODUL | 1 |  |  |  | • | • | • | [5 empty] | FOR REVIEW | [6 empty] | 0.66 |  | FDR | FOR REVIEW
31 | [5 empty] | 218E1240800 |  |  | BRACKET OF AIR RESEVOIR (100L) | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [6 empty] | 14.78 |  | FDR | RELEASE
32 | [5 empty] | 218E1240900 |  |  | BRACKET OF LGS (GROUND SWITCH) |  |  |  |  | • | • | • | [14 empty] | FDR | 0
33 | [5 empty] | 218E1251000 |  |  | BRACKET OF CABLE DUCTING | [5 empty] | • | • |  |  |  |  | INDRA | FOR REVIEW | [6 empty] | 32 |  | FDR | FOR REVIEW
34 | [5 empty] | 218E1251100 |  |  | BRACKET OF PNEUMATIC PIPING | [5 empty] | • | [5 empty] | INDRA | FOR REVIEW | [6 empty] | 20.8 |  | FDR | FOR REVIEW
35 | [5 empty] | 218E1251200 |  |  | BRACKET OF COMPRESSOR CONTROL PANEL | [5 empty] | • | [5 empty] | INDRA | F | [6 empty] | 10 |  | FDR | F
36 | [5 empty] | 218E1251300 |  |  | BRACKET OF MAIN RESEVOIR | [5 empty] | • | [5 empty] | INDRA | PRE-RELEASE | [6 empty] | 20 |  | FDR | PRE-RELEASE
37 | [5 empty] | 218E1251400 |  |  | BRACKET OF AIR SUPPLY | [5 empty] | • | [5 empty] | INDRA | FOR REVIEW | [6 empty] | 10 |  | FDR | FOR REVIEW
38 | [5 empty] | 218E1251500 |  |  | BRACKET OF TERMINAL BOX | [5 empty] | • | [13 empty] | 0 |  | FDR | 0
39 | [5 empty] | 218E1251600 |  |  | BRACKET OF GROUNDING PLATE | [5 empty] | • | [5 empty] | INDRA | WORKING | [6 empty] | 5 |  | FDR | WORKING
40 | [5 empty] | 218E1251700 |  |  | CABLE DIRECTOR ON UNDERFRAME | [5 empty] | • | [5 empty] | INDRA | WORKING | [6 empty] | 7 |  | FDR | WORKING
41 |  |  |  | 220E1250100 |  |  |  |  | SIDEWALL ARRANGEMENT T2 | 8 |  |  |  |  | • | [9 empty] | 2001.5 | [6 empty] | 0
42 |  |  |  |  | 221E1240200 |  |  |  | SIDEWALL CONSTRUCTION T | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [5 empty] | 1723 |  |  | PDR | RELEASE
43 | [5 empty] | 221E1200300 |  |  | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
44 | [5 empty] | 221E1200400 |  |  | MIDDLE SIDEWALL 2 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
45 | [5 empty] | 221E1200500 |  |  | END SIDEWALL 1 --> (LEFT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
46 | [5 empty] | 221E1200600 |  |  | END SIDEWALL 2 --> (RIGHT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
47 | [5 empty] | 221E1200700 |  |  | PASSENGER ENTRANCE | 8 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
48 | [5 empty] | 221E1200800 |  |  | ARR GUSSET ON SIDEWALL T | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
49 | [5 empty] | 221E1201000 |  |  | SIDEWALL DOOR SUPPORT 1 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
50 | [5 empty] | 221E1201100 |  |  | SIDEWALL DOOR SUPPORT 2 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
51 | [5 empty] | 221E1201200 |  |  | SIDEWALL DOOR SUPPORT 3 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
52 |  |  |  |  | 228E1250100 |  |  |  | ARR BRACKET ON SIDE WALL T2 | [5 empty] | • | [12 empty] | 278.5 |  |  |  | 0
53 | [5 empty] | 228E1240200 |  |  | ARRANGEMENT OF ADAPTER ON SIDEWALL |  |  |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [8 empty] | IDR | RELEASE
54 | [5 empty] | 228E1200300 |  |  | BRACKET FOR CURTAIN |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
55 | [5 empty] | 228E1200400 |  |  | BRACKET FOR DOOR ENGINE ENTRANCE |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
56 | [5 empty] | 228E1200500 |  |  | BRACKET FOR LUGGAGE RACK |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
57 | [5 empty] | 228E1200600 |  |  | BRACKET FOR EMERGENCY DOOR RELEASE |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | FDR | RELEASE
58 | [5 empty] | 228E1200700 |  |  | BRACKET FOR RUNNING TEXT |  |  | • | • | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [7 empty] | 0 | FDR | RELEASE
59 | [5 empty] | 228E1200800 |  |  | BRACKET FOR AC PANEL |  |  | • | • | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | FOR REVIEW | [8 empty] | FDR | FOR REVIEW
60 | [5 empty] | 228E1200900 |  |  | BRACKET FOR FOLDING SEAT |  |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
61 | [5 empty] | 228E1201000 |  |  | BRACKET FOR SIDEWALL & ENDWALL PANEL |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
62 | [5 empty] | 228E1201100 |  |  | BRACKET ROLL FILTER PANEL |  | • | • | • | • | • | • |  |  |  |  | DICKY
63 | [5 empty] | 228E1241200 |  |  | HOLE FOR INDICATOR LAMP ON SIDEWALL
64 | [5 empty] | 228E1201300 |  |  | STIFFENER ON TAPPING SIDEWALL
65 |  |  |  | 230E1250100 |  |  |  |  | ENDWALL ARRANGEMENT T2 | [5 empty] | • | [9 empty] | 381.9 | [6 empty] | 0
66 |  |  |  |  | 231E1200100 |  |  |  | MAIN CONSTRUCTION OF ENDWALL |  | • | • | • | • | • | • | [5 empty] | RELEASE | [5 empty] | 362 |  |  | PDR | RELEASE
67 | [5 empty] | 231E1200200 |  |  | END FRAMING |  | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
68 | [5 empty] | 231E1200300 |  |  | END SHEETING 1 |  | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
69 |  |  |  |  | 238E1200100 |  |  |  | ARR BRACKET ON ENDWALL T2 | [5 empty] | • | [12 empty] | 19.9 |  |  |  | 0
70 | [5 empty] | 238E1200200 |  |  | ARRANGEMENT ADAPTER ON ENDWALL | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
71 | [5 empty] | 238E1200300 |  |  | BRACKET FOR DOOR CLOSER | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
72 | [5 empty] | 238E1200400 |  |  | BRACKET ENDWALL PANEL | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
73 | [5 empty] | 238E1200500 |  |  | DIRECTOR CABLE ON ON ENDWALL | [21 empty] | FDR | 0
74 | [5 empty] | 238E1200600 |  |  | TAPPING FOR FALLING PROTECTOR | [7 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
75 |  |  |  | 250E1250100 |  |  |  |  | ROOF ARRANGEMENT T2 | [5 empty] | • | [9 empty] | 1778 | [6 empty] | 0
76 |  |  |  |  | 251E1200100 |  |  |  | MAIN CONSTRUCTION OF ROOF M & T | [5 empty] | • | [6 empty] | RELEASE | [5 empty] | 1516 |  |  | PDR | RELEASE
77 | [5 empty] | 251E1200200 |  |  | ROOF FRAMING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
78 | [5 empty] | 251E1200300 |  |  | ROOF SHEATING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
79 | [5 empty] | 251E1200400 |  |  | ROOF FRAMING AC |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
80 | [5 empty] | 251E1200500 |  |  | ARR GUSSET ON ROOF M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
81 | [5 empty] | 251E1200600 |  |  | RAIN GUTTER M, T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
82 |  |  |  |  | 255E1250100 |  |  |  | ARR CEILLING FRAMING T2 | [5 empty] | • | [12 empty] | 144 |  |  |  | 0
83 | [5 empty] | 255E1200200 |  |  | CEILLING FRAMING PASSANGER ROOM (T) | [21 empty] | FDR | 0
84 | [5 empty] | 255E1200400 |  |  | BRACKET FOR ROLL FILTER | [12 empty] | RELEASE
85 |  |  |  |  | 258E1250100 |  |  |  | ARR BRACKET ON ROOF T2 | [5 empty] | • | [12 empty] | 118 |  |  |  | 0
86 | [5 empty] | 258E1200200 |  |  | ARRANGEMENT ADAPTER ON ROOF | [12 empty] | RELEASE | [8 empty] | IDR | RELEASE
87 | [5 empty] | 258E1200300 |  |  | CABLE DIRECTOR ON ROOF | [12 empty] | FOR REVIEW | [8 empty] | FDR | FOR REVIEW
88 | [5 empty] | 258E1200400 |  |  | BRACKET FOR EXTERIOR SPEAKER | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
89 | [5 empty] | 258E1200500 |  |  | BRACKET FOR DOOR POCKET | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
90 | [5 empty] | 258E1200600 |  |  | BRACKET FOR ELECTRICAL CABINET | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
91 | [5 empty] | 258E1200700 |  |  | BRACKET FOR DOOR CONTROL UNIT | [12 empty] | PRE-RELEASE | [8 empty] | FDR | PRE-RELEASE
92 | [5 empty] | 258E1200800 |  |  | CABLE DIRECTOR ON REAR ROOF FRAME | [12 empty] | FOR REVIEW
BATASBAWAH
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Fathur Rokhman Hidayat) | [9 empty] | (Hernawan Prasanto) | [12 empty] | ( Kristanto)
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | BERAT (SEBELUM PENGURANGAN) |  | BERAT (SETELAH PENGURANGAN) | SELISIH BERAT |  |  | DRAWING YANG BELUM
[8 empty] | 1 | BOM RAW MATERIAL | 2 |  | 2 |  | 100%
[8 empty] | 1 | MAIN COSTRUCTION OF UNDERFRAME T | 6 |  | 6 |  | 100% |  | 4306 | [5 empty] | 0
[8 empty] | 2 | SIDEWALL CONSTRUCTION T | 10 |  | 10 |  | 100% |  | 1723 | [5 empty] | 0
[8 empty] | 3 | MAIN CONSTRUCTION OF ENDWALL | 3 |  | 3 |  | 100% |  | 362 | [5 empty] | 0
[8 empty] | 4 | MAIN CONSTRUCTION OF ROOF M & T | 6 |  | 6 |  | 100% |  | 1516 | [5 empty] | 0
[9 empty] | GREEN CAR | 27 |  | 27 |  | 80% |  | 7907
[8 empty] | 1 | FLOOR CONSTRUCTION | 2 |  | 1 |  | 50% |  | 344 | [5 empty] | 0
[8 empty] | 2 | ARR SUPORTING FRAME FOR FLOOR | 6 |  | 5 |  | 83.33% |  | 197 | [5 empty] | 0
[8 empty] | 3 | ARRANGEMENT BRACKET & FRAME ON U/F | 17 |  | 3 |  | 17.65% |  | 142.44 | [5 empty] | 15
[8 empty] | 4 | ARR BRACKET ON SIDE WALL T2 | 8 |  | 7 |  | 87.5% |  | 278.5 |  |  |  | 560.4 |  | 2
[8 empty] | 5 | ARR BRACKET ON ENDWALL T2 | 5 |  | 4 |  | 80% |  | 19.9 | [5 empty] | 2
[8 empty] | 6 | ARR CEILLING FRAMING T2 | 2 |  | 0 |  | 0% |  | 144 | [5 empty] | 0
[8 empty] | 7 | ARR BRACKET ON ROOF T2 | 6 |  | 4 |  | 66.67% |  | 118 | [5 empty] | 4
[9 empty] | BRACKET AND SUPPORT | 46 |  | 24 |  | 10.43% |  | 1243.84
[9 empty] | TOTAL DRAWING | 100 |  | 78 |  |  |  | 9150.84
[9 empty] | PROGRESS TOTAL |  |  |  |  | 90.43%
DRAWING UNTUK KEBUTUHAN CARBODY ASSY
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | SCOPE OF WORK
[8 empty] | 1 | CARBODY SHEEL T2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 2 | SIDEWALL ARRANGEMENT T2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 3 | ENDWALL ARRANGEMENT T2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 4 | ROOF ARRANGEMENT T2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[9 empty] | TOTAL DRAWING INKA | 4 |  | 0
[9 empty] | PROGRESS INKA |  |  |  |  | 0%
Note on Z8: PENGISIAN BERAT DI LVL 5 (MAIN ASSY)
INKA

## T3 (E126)
[17 empty] | Project |  | : 16 TS E12 KCI (E12) | [8 empty] | WEIGHT LIMIT (KG) : |  | 8000 |  | JUMLAH |  | %-TASE
[9 empty] | TREE DIAGRAM & | [7 empty] | Document Number |  | : 201-TDD-H1005MB051-23 | [8 empty] | WEIGHT ESTIMATION (KG) |  | 0 |  | DRAWING | RELEASE
[9 empty] | WEIGHT CALCULATION | [7 empty] | Date of Issue |  | : JANUARI 2023 | [8 empty] | PROGRESS TOTAL |  | 66.67% | PDR | 30 | 30 | 100%
[17 empty] | Revision |  | : 0 | [11 empty] | IDR | 2 | 2 | 100%
[17 empty] | Page |  | : | [11 empty] | FDR | 33 | 2 | 6.061%
[17 empty] | Car Type |  | : T3 | [12 empty] | 65 | 34
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK (SOW) | WEIGHT EST. (KG) | Tanggal Pengambilan Berat | Target Release | WEIGHT EST. (KG)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7
1 | 201-BRM-H1005MB051-23 | [7 empty] | BOM RAW MATERIAL | [12 empty] | RELEASE
2 | 203-BRM-H1005MB051-23 | [7 empty] | BOM PIECE PART | [12 empty] | RELEASE
3 | 000E1260100 | [7 empty] | GA T E12 KCI 2022
4 |  | 000E1202000 | [6 empty] | TRAILLER BOGIE ASSEMBLY
5 |  | 000E1260200 | [6 empty] | CARBODY SET T3
6 |  |  | 200E1260100 | [5 empty] | CARBODY SHEEL T3 | [11 empty] | INDRA
7 |  |  |  | 210E1260100 |  |  |  |  | UNDERFRAME ASSY T3 | [6 empty] | •
8 |  |  |  |  | 210E1240200 |  |  |  | MAIN COSTRUCTION OF UNDERFRAME T | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [5 empty] | 4306 |  |  | PDR | RELEASE
9 | [5 empty] | 211E1200100 |  |  | END PART ASSEMBLY | 2 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
10 | [6 empty] | 211E1200200 |  | END PART | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
11 | [6 empty] | 212E1200100 |  | BOLSTER | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
12 | [5 empty] | 211E1200300 |  |  | ANTI CLIMBER 02 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
13 | [5 empty] | 213E1200100 |  |  | MIDDLE PART ASSY | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
14 | [5 empty] | 213K5600200 |  |  | JACKING PAD | 4 |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
15 |  |  |  |  | 214E1260100 |  |  |  | FLOOR CONSTRUCTION | [6 empty] | • | [11 empty] | 344 |  |  |  | 0
16 | [5 empty] | 214E1240200 |  |  | ARRG FLOOR ON PASSENGER ROOM | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
17 |  |  |  |  | 215E1260100 |  |  |  | ARR SUPORTING FRAME FOR FLOOR | [6 empty] | • | [11 empty] | 197 |  |  |  | 0
18 | [5 empty] | 215E1240200 |  |  | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
19 | [5 empty] | 215E1240300 |  |  | DRAIN PIPE AND SUPPORT | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
20 | [5 empty] | 215E1240400 |  |  | TAPPING STRIP | [12 empty] | RELEASE | [8 empty] | PDR | RELEASE
21 | [5 empty] | 215E1240500 |  |  | TAPPING FOR PASSENGER SEAT ON FLOOR | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
22 | [5 empty] | 215E1240600 |  |  | TAPPING FOR INTERIOR CABINET | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
23 | [5 empty] | 215E1240700 |  |  | TAPPING STRIP FOR EVACUATION LINE | [22 empty] | 0
24 |  |  |  |  | 218E1260100 |  |  |  | ARRANGEMENT BRACKET & FRAME ON U/F | [6 empty] | • | [11 empty] | 102.44 |  |  |  | 0
25 | [5 empty] | 218E1200200 |  |  | BRACKET FOR GROUNDING INTER CAR | 1 |  | • | • | • | • | • | [5 empty] | 0 | [8 empty] | FDR | 0
26 | [5 empty] | 218E1200300 |  |  | BRACKET FOR LEVELING VALVE | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 1.7 |  | FDR | RELEASE
27 | [5 empty] | 218E1240400 |  |  | BRACKET FOR COUPLER SUPPORT | 1 |  |  |  | • | • | • | [5 empty] | FOR REVIEW | [6 empty] | 15.6 |  | FDR | FOR REVIEW
28 | [5 empty] | 218E1200500 |  |  | BRACKET FOR LADDER | 1 |  | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 1.1 |  | FDR | RELEASE
29 | [5 empty] | 218E1240600 |  |  | BRACKET OF ELECTRIC CONTROL PANEL | 1 |  |  |  | • | • | • |  |  |  |  | KAFI | FOR REVIEW | [6 empty] | 3.8 |  | FDR | FOR REVIEW
30 | [5 empty] | 218E1240700 |  |  | BRACKET OF BRAKE CONTROL UNIT | 1 |  |  |  | • | • | • |  |  |  |  | KAFI | FOR REVIEW | [6 empty] | 0.66 |  | FDR | FOR REVIEW
31 | [5 empty] | 218E1240800 |  |  | BRACKET OF AIR RESEVOIR (100L) | 1 |  |  |  | • | • | • |  |  |  |  | KAFI | RELEASE | [6 empty] | 14.78 |  | FDR | RELEASE
32 | [5 empty] | 218E1240900 |  |  | BRACKET OF LGS (GROUND SWITCH) | 1 |  |  |  | • | • | • | [14 empty] | FDR | 0
33 | [5 empty] | 218E1251000 |  |  | BRACKET OF CABLE DUCTING | 1 |  |  |  |  | • | • |  |  |  | INDRA | INDRA | [7 empty] | 32 |  | FDR | 0
34 | [5 empty] | 218E1241100 |  |  | BRACKET OF PNEUMATIC PIPING | 1 |  |  |  | • |  | • |  |  |  | INDRA | INDRA | FOR REVIEW | [6 empty] | 20.8 |  | FDR | FOR REVIEW
35 | [5 empty] | 218E1261200 |  |  | BRACKET OF GROUNDING PLATE | 1 | [5 empty] | • |  |  |  |  | INDRA | WORKING | [6 empty] | 5 |  | FDR | WORKING
36 | [5 empty] | 218E1261300 |  |  | CABLE DIRECTOR ON UNDERFRAME | 1 | [5 empty] | • |  |  |  |  | INDRA | WORKING | [6 empty] | 7 |  | FDR | WORKING
37 |  |  |  | 220E1260100 |  |  |  |  | SIDEWALL ARRANGEMENT T3 | [6 empty] | • | [15 empty] | 0
38 |  |  |  |  | 221E1240200 |  |  |  | SIDEWALL CONSTRUCTION T |  |  |  |  | • | • | • | [5 empty] | RELEASE | [5 empty] | 1723 |  |  | PDR | RELEASE
39 | [5 empty] | 221E1200300 |  |  | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
40 | [5 empty] | 221E1200400 |  |  | MIDDLE SIDEWALL 2 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
41 | [5 empty] | 221E1200500 |  |  | END SIDEWALL 1 --> (LEFT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
42 | [5 empty] | 221E1200600 |  |  | END SIDEWALL 2 --> (RIGHT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
43 | [5 empty] | 221E1200700 |  |  | PASSENGER ENTRANCE | 8 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
44 | [5 empty] | 221E1200800 |  |  | ARR GUSSET ON SIDEWALL T | 1 |  |  |  | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
45 | [5 empty] | 221E1201000 |  |  | SIDEWALL DOOR SUPPORT 1 | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
46 | [5 empty] | 221E1201100 |  |  | SIDEWALL DOOR SUPPORT 2 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
47 | [5 empty] | 221E1201200 |  |  | SIDEWALL DOOR SUPPORT 3 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
48 |  |  |  |  | 228E1260100 |  |  |  | ARR BRACKET ON SIDE WALL T3 | [5 empty] | • | [12 empty] | 278.5 |  |  |  | 0
49 | [5 empty] | 228E1240200 |  |  | ARRANGEMENT OF ADAPTER ON SIDEWALL |  |  |  |  | • | • | • | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [8 empty] | IDR | RELEASE
50 | [5 empty] | 228E1200300 |  |  | BRACKET FOR CURTAIN |  |  | • | • | • | • | • | RELEASE | RELEASE | [12 empty] | FDR | 0
51 | [5 empty] | 228E1200400 |  |  | BRACKET FOR DOOR ENGINE ENTRANCE |  |  | • | • | • | • | • | RELEASE | RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
52 | [5 empty] | 228E1200500 |  |  | BRACKET FOR LUGGAGE RACK |  |  | • | • | • | • | • | RELEASE | RELEASE | [12 empty] | FDR | 0
53 | [5 empty] | 228E1200600 |  |  | BRACKET FOR EMERGENCY DOOR RELEASE |  |  | • | • | • | • | • | [14 empty] | FDR | 0
54 | [5 empty] | 228E1200700 |  |  | BRACKET FOR RUNNING TEXT |  |  | • | • | • | • | • | PRE-RELEASE | PRE-RELEASE | [11 empty] | 0 | FDR | 0
55 | [5 empty] | 228E1200800 |  |  | BRACKET FOR AC PANEL |  |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW | [12 empty] | FDR | 0
56 | [5 empty] | 228E1200900 |  |  | BRACKET FOR FOLDING SEAT |  |  | • | • | • | • | • | FOR REVIEW | FOR REVIEW | [12 empty] | FDR | 0
57 | [5 empty] | 228E1201000 |  |  | BRACKET FOR SIDEWALL & ENDWALL PANEL |  |  | • | • | • | • | • | RELEASE | RELEASE | [12 empty] | FDR | 0
58 | [5 empty] | 228E1201100 |  |  | BRACKET ROLL FILTER PANEL |  | • | • | • | • | • | • |  |  |  |  | DIKCY
59 | [5 empty] | 228E1241200 |  |  | HOLE FOR INDICATOR LAMP ON SIDEWALL
60 | [5 empty] | 228E1201300 |  |  | STIFFENER ON TAPPING SIDEWALL
61 |  |  |  | 230E1260100 |  |  |  |  | ENDWALL ARRANGEMENT T3 | [6 empty] | • | [15 empty] | 0
62 |  |  |  |  | 231E1200100 |  |  |  | MAIN CONSTRUCTION OF ENDWALL |  | • | • | • | • | • | • | [5 empty] | RELEASE | [5 empty] | 362 |  |  | PDR | RELEASE
63 | [5 empty] | 231E1200200 |  |  | END FRAMING |  | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
64 | [5 empty] | 231E1200300 |  |  | END SHEETING |  | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
65 |  |  |  |  | 238E1200100 |  |  |  | ARR BRACKET ON ENDWALL T3 |  |  | • | [15 empty] | 19.9 |  |  |  | 0
66 | [5 empty] | 238E1200200 |  |  | ARRANGEMENT ADAPTER ON ENDWALL | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
67 | [5 empty] | 238E1200300 |  |  | BRACKET FOR DOOR CLOSER | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
68 | [5 empty] | 238E1200400 |  |  | BRACKET ENDWALL PANEL | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
69 | [5 empty] | 238E1200500 |  |  | DIRECTOR CABLE ON ON ENDWALL | [21 empty] | FDR | 0
70 | [5 empty] | 238E1200600 |  |  | TAPPING FOR FALLING PROTECTOR | [7 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [8 empty] | FDR | RELEASE
71 |  |  |  | 250E1260100 |  |  |  |  | ROOF ARRANGEMENT T3 | [6 empty] | • | [15 empty] | 0
72 |  |  |  |  | 251E1200100 |  |  |  | MAIN CONSTRUCTION OF ROOF M & T | [6 empty] | • | [5 empty] | RELEASE | [5 empty] | 1516 |  |  | PDR | RELEASE
73 | [5 empty] | 251E1200200 |  |  | ROOF FRAMING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
74 | [5 empty] | 251E1200300 |  |  | ROOF SHEATING M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
75 | [5 empty] | 251E1200400 |  |  | ROOF FRAMING AC |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
76 | [5 empty] | 251E1200500 |  |  | ARR GUSSET ON ROOF M,T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
77 | [5 empty] | 251E1200600 |  |  | RAIN GUTTER M, T |  |  | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | PDR | RELEASE
78 |  |  |  |  | 255E1260100 |  |  |  | ARR CEILLING FRAMING T3 | [6 empty] | • | [11 empty] | 144 |  |  |  | 0
79 | [5 empty] | 255E1200200 |  |  | CEILLING FRAMING PASSANGER ROOM (T) | [21 empty] | FDR | 0
80 | [5 empty] | 255E1200400 |  |  | BRACKET FOR ROLL FILTER | [12 empty] | RELEASE
81 |  |  |  |  | 258E1260100 |  |  |  | ARR BRACKET ON ROOF T3 | [6 empty] | • | [11 empty] | 118 |  |  |  | 0
82 | [5 empty] | 258E1200200 |  |  | ARRANGEMENT ADAPTER ON ROOF | [12 empty] | RELEASE | [8 empty] | IDR | RELEASE
83 | [5 empty] | 258E1200300 |  |  | CABLE DIRECTOR ON ROOF | [12 empty] | FOR REVIEW | [8 empty] | FDR | FOR REVIEW
84 | [5 empty] | 258E1200400 |  |  | BRACKET FOR EXTERIOR SPEAKER | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
85 | [5 empty] | 258E1200500 |  |  | BRACKET FOR DOOR POCKET | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
86 | [5 empty] | 258E1200600 |  |  | BRACKET FOR ELECTRICAL CABINET | [12 empty] | RELEASE | [8 empty] | FDR | RELEASE
87 | [5 empty] | 258E1200700 |  |  | BRACKET FOR DOOR CONTROL UNIT | [12 empty] | PRE-RELEASE | [8 empty] | FDR | PRE-RELEASE
88 | [5 empty] | 258E1200800 |  |  | CABLE DIRECTOR ON REAR ROOF FRAME | [12 empty] | FOR REVIEW
BATASBAWAH
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Fathur Rokhman Hidayat) | [9 empty] | (Hernawan Prasanto) | [12 empty] | ( Kristanto)
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | BERAT (SEBELUM PENGURANGAN) |  | BERAT (SETELAH PENGURANGAN) | SELISIH BERAT | DRAWING YANG BELUM
[8 empty] | 1 | BOM RAW MATERIAL | 2 |  | 2 |  | 100%
[8 empty] | 1 | MAIN COSTRUCTION OF UNDERFRAME T | 6 |  | 6 |  | 100% |  | 4306 |  |  |  | 0
[8 empty] | 2 | SIDEWALL CONSTRUCTION T | 10 |  | 10 |  | 100% |  | 1723 |  |  |  | 0
[8 empty] | 3 | MAIN CONSTRUCTION OF ENDWALL | 3 |  | 3 |  | 100% |  | 362 |  |  |  | 0
[8 empty] | 4 | MAIN CONSTRUCTION OF ROOF M & T | 6 |  | 6 |  | 100% |  | 1516 |  |  |  | 0
[9 empty] | GREEN CAR | 27 |  | 27 |  | 80% |  | 7907
[8 empty] | 1 | FLOOR CONSTRUCTION | 2 |  | 1 |  | 50% |  | 344 |  |  |  | 0
[8 empty] | 2 | ARR SUPORTING FRAME FOR FLOOR | 6 |  | 5 |  | 83.33% |  | 197 |  |  |  | 0
[8 empty] | 3 | ARRANGEMENT BRACKET & FRAME ON U/F | 12 |  | 3 |  | 25% |  | 102.44 |  |  |  | 10
[8 empty] | 4 | ARR BRACKET ON SIDE WALL T3 | 8 |  | 2 |  | 25% |  | 278.5 |  |  |  | 2
[8 empty] | 5 | ARR BRACKET ON ENDWALL T3 | 5 |  | 4 |  | 80% |  | 19.9 |  |  |  | 2
[8 empty] | 6 | ARR CEILLING FRAMING T3 | 2 |  | 0 |  | 0% |  | 144 |  |  |  | 0
[8 empty] | 7 | ARR BRACKET ON ROOF T3 | 6 |  | 4 |  | 66.67% |  | 118 |  |  |  | 4
[9 empty] | BRACKET AND SUPPORT | 41 |  | 19 |  | 9.268% |  | 1203.84
[9 empty] | TOTAL DRAWING/BERAT | 95 |  | 73 |  |  |  | 9110.84
[9 empty] | PROGRESS TOTAL |  |  |  |  | 89.27%
DRAWING UNTUK KEBUTUHAN CARBODY ASSY
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | SCOPE OF WORK
[8 empty] | 1 | CARBODY SHEEL T3 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 2 | SIDEWALL ARRANGEMENT T3 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 3 | ENDWALL ARRANGEMENT T3 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 4 | ROOF ARRANGEMENT T3 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[9 empty] | TOTAL DRAWING INKA | 4 |  | 0
[9 empty] | PROGRESS INKA |  |  |  |  | 0%
Note on Z8: PENGISIAN BERAT DI LVL 5 (MAIN ASSY)
INKA

## TC2 (E127)
[17 empty] | Project |  | : 16 TS KRL KCI (E12) | [5 empty] | WEIGHT LIMIT (KG) : |  | 8000 | [5 empty] | JUMLAH |  | %-TASE
[9 empty] | TREE DIAGRAM & | [7 empty] | Document Number |  | : 201-TDD-H1005MB051-23 | [5 empty] | WEIGHT EST. (KG) |  | 8319 | [5 empty] | DRAWING | RELEASE
[9 empty] | WEIGHT CALCULATION | [7 empty] | Date of Issue |  | : JANUARI 2023 | [5 empty] | PROGRESS TOTAL |  | 0% |  |  |  |  | PDR | 48 | 37 | 77.08%
[9 empty] | TC 2 | [7 empty] | Revision |  | : 0 | [12 empty] | IDR | 8 | 5 | 62.5%
[17 empty] | Page |  | : | [12 empty] | FDR | 46 | 16 | 34.78%
[17 empty] | Car Type |  | : TC2 | [13 empty] | 102 | 58
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK (SOW) | WEIGHT EST. (KG) | Tanggal Pengambilan Berat |  | WEIGHT EST. (KG) |  |  |  | TAHAPAN DESAIN
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7
1 | 201-BRM-H1005MB051-23 | [7 empty] | BOM RAW MATERIAL |  | • | [10 empty] | RELEASE
2 | 203-BRM-H1005MB051-23 | [7 empty] | BOM PIECE PART |  | • | • | • | • | • | • | [5 empty] | RELEASE
3 | 000E1210100 | [7 empty] | GA TEC E12 KCI 2022 |  | •
4 |  | 000E1202000 | [6 empty] | TRAILLER BOGIE ASSEMBLY |  | •
5 |  | 002E1270200 | [6 empty] | CARBODY SET (TC2) | 1 | •
6 |  |  | 200E1270100 | [5 empty] | CARBODY SHEEL (TC2) | 1 | •
7 |  |  |  | 210E1270100 |  |  |  |  | UNDERFRAME ARRANGEMENT (TC2) | 1 | •
8 |  |  |  |  | 210E1210200 |  |  |  | MAIN CONSTRUCTION OF UNDERFRAME TC1&TC2 | 1 | • | [10 empty] | RELEASE |  |  | 4570 | 2023-09-12 |  | 4570 |  |  | 2023-09-12 | PDR | RELEASE
9 | [5 empty] | 211E1210100 |  |  | FRONT PART ASSEMBLY | 1 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
10 | [6 empty] | 211E1210200 |  | END BEAM FRONT TC | 1 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
11 | [6 empty] | 212E1210100 |  | BOLSTER | 1 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
12 | [5 empty] | 211E1200100 |  |  | END PART ASSEMBLY | 1 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
13 | [6 empty] | 211E1200200 |  | END BEAM | 1 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
14 | [6 empty] | 212E1200100 |  | BOLSTER | 1 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
15 | [5 empty] | 211E1210300 |  |  | ANTI CLIMBER 01 | 1 | • | [10 empty] | RELEASE | [9 empty] | PDR | RELEASE
16 | [5 empty] | 211E1200300 |  |  | ANTI CLIMBER 02 | 2 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
17 | [5 empty] | 213E1210100 |  |  | MIDDLE PART ASSY | 1 | • | [10 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
18 | [5 empty] | 213E1210200 |  |  | BACKING MIDDLE PART ASSY | 1 | • | [10 empty] | RELEASE | [9 empty] | PDR | RELEASE
19 | [5 empty] | 213K5600200 |  |  | JACKING PAD | 4 | • | • | • | • | • | • | [5 empty] | RELEASE | [8 empty] | 2023-09-12 | PDR | RELEASE
20 |  |  |  |  | 214E1210100 |  |  |  | FLOOR CONSTRUCTION TC1 & TC2 | 1 | • | [13 empty] | 0 |  |  | 0 |  |  |  |  | 0
21 | [5 empty] | 214E1210200 |  |  | ARRG FLOOR ON PASSENGER ROOM | 1 | • | [20 empty] | PDR | 0
22 | [5 empty] | 214E1210300 |  |  | ARR FLOOR PLATE ON CAB | 1 | • | [20 empty] | PDR | 0
23 |  |  |  |  | 215E1210100 |  |  |  | ARR SUPORTING FRAME FOR FLOOR TC1 & TC2 | 1 | • | [13 empty] | 0 |  |  | 0 |  |  |  |  | 0
24 | [5 empty] | 215E1210200 |  |  | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | 1 | • | [20 empty] | PDR | 0
25 | [5 empty] | 215E1210300 |  |  | BRACKET SUPPORT FLOOR ON CAB | 1 | • | [20 empty] | PDR | 0
26 | [5 empty] | 215E1210400 |  |  | DRAIN PIPE AND SUPPORT | 1 | • | [20 empty] | PDR | 0
27 | [5 empty] | 215E1210500 |  |  | TAPPING STRIP | 1 | • | [20 empty] | PDR | 0
28 | [5 empty] | 215E1210600 |  |  | TAPPING FOR DRIVER AND PASSENGER SEAT ON FLOOR | 1 | • | [20 empty] | IDR | 0
29 | [5 empty] | 215E1210700 |  |  | TAPPING FOR DOOR POCKET & INTERIOR CABINET | 1 | • | [20 empty] | IDR | 0
30 | [5 empty] | 215E1210800 |  |  | TAPPING STRIP FOR EVACUATION LINE |  | • | [20 empty] | IDR | 0
31 | [5 empty] | 215E1210900 |  |  | HOLE FOR DRAIN SUPPORT | 1 | • | [20 empty] | IDR | RELEASE
32 |  |  |  |  | 218E1270100 |  |  |  | ARRANGEMENT BRACKET & FRAME ON U/F TC2 | 1 | • | [13 empty] | 0 |  |  | 0 |  |  |  |  | 0
33 | [5 empty] | 218E1210200 |  |  | BRACKET FOR GROUNDING INTER CAR | 1 | • | [20 empty] | FDR | 0
34 | [5 empty] | 218E1200300 |  |  | BRACKET FOR LEVELING VALVE | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
35 | [5 empty] | 218E1210400 |  |  | BRACKET FOR COUPLER SUPPORT | 1 | • | [10 empty] | RELEASE | [9 empty] | IDR | RELEASE
36 | [5 empty] | 218E1270500 |  |  | BRACKET FOR CABLE DUCT | 1 | • | [9 empty] | KAFI | [10 empty] | FDR | 0
37 | [5 empty] | 218E1270600 |  |  | BRACKET FOR PNEUMATIC PIPING | 1 | • | [20 empty] | FDR | 0
38 | [5 empty] | 218E1270700 |  |  | BRACKET OF BATTERY BOX | 1 | • | [20 empty] | FDR | 0
39 | [5 empty] | 218E1270800 |  |  | BRACKET OF RECTIFIER BOX | 1 | • | [20 empty] | FDR | 0
40 | [5 empty] | 218E1270900 |  |  | BRACKET OF ELECTRIC CONTROL PANEL | 1 | • | [20 empty] | FDR | 0
41 | [5 empty] | 218E1271000 |  |  | BRACKET FOR LADDER | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
42 | [5 empty] | 218E1271100 |  |  | BRACKET OF AUX SWITCH | 1 | • | [20 empty] | FDR | 0
43 | [5 empty] | 218E1271200 |  |  | BRACKET OF TERMINAL BOX | 1 | • | [20 empty] | FDR | 0
44 | [5 empty] | 218E1271300 |  |  | BRACKET OF LGS (GROUND SWITCH) | 1 | • | [20 empty] | FDR | 0
45 | [5 empty] | 218E1271400 |  |  | BRACKET OF AIR RESERVOIR | 1 | • | [20 empty] | FDR | 0
46 | [5 empty] | 218E1271500 |  |  | BRACKET OF TRANSFORMER FILTER BOX | 1 | • | [20 empty] | FDR | 0
47 | [5 empty] | 218E1271600 |  |  | BRACKET OF COWCATCHER | 1 | • | [20 empty] | FDR | 0
48 | [5 empty] | 218E1271700 |  |  | BRACKET OF JUNCTION COUPLER ELECTRIC | 1 | • | [20 empty] | FDR | 0
49 | [5 empty] | 218E1271800 |  |  | BRACKET OF PNEUMATIC HORN MODULE | 1 | • | [20 empty] | FDR | 0
50 | [5 empty] | 218E1271900 |  |  | BRACKET OF APS BOX | 1 | • | [20 empty] | FDR | 0
51 | [5 empty] | 218E1272000 |  |  | BRACKET OF IVHB | 1 | • | [20 empty] | FDR | 0
52 | [5 empty] | 218E1272100 |  |  | BRACKET OF BATTERY CONTROL PANEL | 1 | • | [20 empty] | FDR | 0
53 | [5 empty] | 218E1272200 |  |  | BRACKET OF BRAKE CONTROL UNIT | 1 | • | [20 empty] | FDR | 0
54 | [5 empty] | 218E1272300 |  |  | BRACKET OF HGS (GROUND SWITCH) | 1 | • | [20 empty] | FDR | 0
55 | [5 empty] | 218E1272400 |  |  | BRACKET OF GROUNDING PLATE | 1 | • | [20 empty] | FDR | 0
56 | [5 empty] | 218E1272500 |  |  | CABLE DIRECTOR ON UNDERFRAME | 1 | • | [20 empty] | FDR | 0
57 |  |  |  | 220E1210100 |  |  |  |  | SIDEWALL ARRANGEMENT TC1 & TC2 | 1 | • | [21 empty] | 0
58 |  |  |  |  | 221E1210200 |  |  |  | MAIN CONSTRUCTION OF SIDEWALL TC1 & TC2 | 1 | • | [10 empty] | RELEASE |  |  | 1805.7 | 2023-09-13 |  | 1805.7 |  |  | 2023-09-13 | PDR | RELEASE
59 | [5 empty] | 221E1200300 |  |  | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 241.8 | 120.9 | 2023-09-13 | PDR | RELEASE
60 | [5 empty] | 221E1200400 |  |  | MIDDLE SIDEWALL 2 | 2 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 247 | 123.5 | 2023-09-13 | PDR | RELEASE
61 | [5 empty] | 221E1200500 |  |  | END SIDEWALL 1 --> (LEFT) | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 71.7 | 71.7 | 2023-09-13 | PDR | RELEASE
62 | [5 empty] | 221E1200700 |  |  | PASSENGER ENTRANCE | 8 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 464.8 | 58.1 | 2023-09-13 | PDR | RELEASE
63 | [5 empty] | 221E1201000 |  |  | FRAME DOOR SUPPORT 1 | 2 | • | [10 empty] | RELEASE | [6 empty] | 40 | 20 | 2023-09-13 | PDR | RELEASE
64 | [5 empty] | 221E1201100 |  |  | FRAME DOOR SUPPORT 2 | 2 | • | [10 empty] | RELEASE | [6 empty] | 39.6 | 19.8 | 2023-09-13 | PDR | RELEASE
65 | [5 empty] | 221E1201200 |  |  | FRAME DOOR SUPPORT 2 | 2 | • | [10 empty] | RELEASE | [6 empty] | 39.6 | 19.8 | 2023-09-13 | PDR | RELEASE
66 | [5 empty] | 221E1210800 |  |  | MIDDLE SIDEWALL 3 --> (TC ONLY, SHORT LENGTH) | 2 | • | [10 empty] | RELEASE | [6 empty] | 165.8 | 82.9 | 2023-09-13 | PDR | RELEASE
67 | [5 empty] | 221E1210900 |  |  | BEHIND CAB SIDEWALL 1 --> (LEFT) | 1 | • | [10 empty] | RELEASE | [6 empty] | 38.5 | 38.5 | 2023-09-13 | PDR | RELEASE
68 | [5 empty] | 221E1211000 |  |  | BEHIND CAB SIDEWALL 2 --> (RIGHT) | 1 | • | [10 empty] | RELEASE | [6 empty] | 38.5 | 38.5 | 2023-09-13 | PDR | RELEASE
69 | [5 empty] | 221E1211100 |  |  | DRIVER CAB ENTRANCE | 2 | • | [10 empty] | RELEASE | [6 empty] | 137 | 68.5 | 2023-09-13 | PDR | RELEASE
70 | [5 empty] | 221E1211200 |  |  | ARR GUSSET ON SIDEWALL TC1 & TC2 | 1 | • | [10 empty] | RELEASE | [6 empty] | 66.3 | 66.3 | 2023-09-13 | PDR | RELEASE
71 | [5 empty] | 221E1211300 |  |  | CABIN SIDEWALL 1 --> (LEFT) | 1 | • | [10 empty] | RELEASE | [6 empty] | 51.9 | 51.9 | 2023-09-13 | PDR | RELEASE
72 | [5 empty] | 221E1211400 |  |  | CABIN SIDEWALL 2 --> (RIGHT) | 1 | • | [10 empty] | RELEASE | [6 empty] | 51.9 | 51.9 | 2023-09-13 | PDR | RELEASE
73 | [5 empty] | 221E1211600 |  |  | END SIDEWALL 2 --> (RIGHT TC) | 1 | • | [10 empty] | RELEASE | [6 empty] | 71.7 | 71.7 | 2023-09-13 | PDR | RELEASE
74 | [5 empty] | 221E1211700 |  |  | FRAME DOOR SUPPORT 3 --> (RIGHT TC) | 1 | • | [10 empty] | RELEASE | [6 empty] | 19.8 | 19.8 | 2023-09-13 | PDR | RELEASE
75 | [5 empty] | 221E1211800 |  |  | FRAME DOOR SUPPORT 4 --> (LEFT TC) | 1 | • | [10 empty] | RELEASE | [6 empty] | 19.8 | 19.8 | 2023-09-13 | PDR | RELEASE
76 |  |  |  |  | 228E1210100 |  |  |  | ARR BRACKET ON SIDE WALL TC1 & TC2 | 1 | • | [13 empty] | 0 |  |  | 0 |  |  |  |  | 0
77 | [5 empty] | 228E1210200 |  |  | ARRANGEMENT ADAPTER ON SIDEWALL | 1 | • | [10 empty] | RELEASE | [9 empty] | IDR | RELEASE
78 | [5 empty] | 228E1210300 |  |  | BRACKET FOR CURTAIN | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
79 | [5 empty] | 228E1210400 |  |  | BRACKET FOR DOOR ENGINE ENTRANCE | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
80 | [5 empty] | 228E1210500 |  |  | BRACKET FOR LUGGAGE RACK | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
81 | [5 empty] | 228E1210600 |  |  | BRACKET EMERGENCY DOOR RELEASE | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
82 | [5 empty] | 228E1210700 |  |  | BRACKET FOR RUNNING TEXT | 1 | • | [5 empty] | PRE-RELEASE | PRE-RELEASE |  |  |  | RELEASE | [7 empty] | 0 |  | FDR | RELEASE
83 | [5 empty] | 228E1210800 |  |  | BRACKET FOR AC PANEL | 1 | • | [10 empty] | FOR REVIEW | [9 empty] | FDR | FOR REVIEW
84 | [5 empty] | 228E1200900 |  |  | BRACKET FOR FOLDING SEAT | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
85 | [5 empty] | 228E1211000 |  |  | BRACKET FOR GUTTER PIPE AT CABIN | 1 | • | [10 empty] | RELEASE
86 | [5 empty] | 228E1201100 |  |  | BRACKET FOR ROLL FILTER PANEL | 1 | • | [10 empty] | FOR REVIEW
87 | [5 empty] | 228E1211200 |  |  | HOLE FOR INDICATOR LAMP ON SIDEWALL | 1 | • | [10 empty] | RELEASE
88 | [5 empty] | 228E1211300 |  |  | STIFFENER ON TAPPING SIDEWALL | 1 | • | [10 empty] | RELEASE
89 | [5 empty] | 228E1211400 |  |  | CABLE DIRECTOR ON SIDEWALL | 1 | • | [10 empty] | RELEASE
90 |  |  |  | 230E1210100 |  |  |  |  | ENDWALL ARRANGEMENT TC1 & TC2 | 1 | • | [20 empty] | FDR | 0
91 |  |  |  |  | 231E1200100 |  |  |  | MAIN CONSTRUCTION OF ENDWALL | 1 | • | [10 empty] | RELEASE |  |  | 167.4 | 2023-09-13 |  | 167.4 |  |  | 2023-09-13 |  | RELEASE
92 | [5 empty] | 231E1200200 |  |  | END FRAMING | 1 | • | • | • | • | • | [6 empty] | RELEASE | [6 empty] | 101.9 | 101.9 | 2023-09-13 | PDR | RELEASE
93 | [5 empty] | 231E1200300 |  |  | END SHEETING | 1 | • | • | • | • | • | [6 empty] | RELEASE | [6 empty] | 65.5 | 65.5 | 2023-09-13 | PDR | RELEASE
94 |  |  |  |  | 238E1210100 |  |  |  | ARR BRACKET ON ENDWALL TC1 & TC2 | 1 | • | [13 empty] | 0 | [6 empty] | PDR | 0
95 | [5 empty] | 238E1200200 |  |  | ARRANGEMENT ADAPTER ON ENDWALL | 1 | • | [10 empty] | RELEASE | [10 empty] | RELEASE
96 | [5 empty] | 238E1200300 |  |  | BRACKET FOR DOOR CLOSER | 1 | • | [10 empty] | RELEASE | [9 empty] | IDR | RELEASE
97 | [5 empty] | 238E1200400 |  |  | BRACKET ENDWALL PANEL | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
98 | [5 empty] | 238E1200500 |  |  | DIRECTOR CABLE ON ON ENDWALL | 1 | • | [10 empty] | 0 | [9 empty] | FDR | 0
99 | [5 empty] | 238E1210600 |  |  | TAPPING FOR FALLING PROTECTOR | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
100 |  |  |  | 240E1210100 |  |  |  |  | DRIVER CAB ARRANGEMENT | 1 | • | [20 empty] | FDR | 0
101 |  |  |  |  | 241E1210100 |  |  |  | MAIN CONSTRUCTION OF MASKARA | 1 | • | [10 empty] | RELEASE |  |  | 209 | 2023-09-13 |  | 209 |  |  | 2023-09-13 |  | RELEASE
102 | [5 empty] | 241E1210200 |  |  | SHEATING MASKARA | 1 | • | [10 empty] | CANCELED | [6 empty] | 79.9 | 79.9 |  | PDR | CANCELED
103 | [5 empty] | 241E1210300 |  |  | FRAME MASKARA | 1 | • | [10 empty] | CANCELED | [6 empty] | 129.1 | 129.1 |  | PDR | CANCELED
104 | [5 empty] | 241E1210400 |  |  | SHEATING MASKARA | 1 | • | [10 empty] | RELEASE
105 | [5 empty] | 241E1210500 |  |  | FRAME MASKARA | 1 | • | [10 empty] | RELEASE
106 |  |  |  |  | 245E1210100 |  |  |  | ARR CEILING FRAME ON CAB TC1 & TC2 | 1 | • | [13 empty] | 0 | [6 empty] | PDR | 0
107 | [5 empty] | 245E1210100 |  |  | CEILING FRAME ON CAB | 1 | • | [10 empty] | RELEASE | [10 empty] | RELEASE
108 | [5 empty] | 245E1210200 |  |  | DIRECTOR CABLE ON CEILING FRAME CAB | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
109 |  |  |  |  | 248E1210100 |  |  |  | ARR BRACKET WELDED ON CAB TC1 & TC2 | 1 | • | [13 empty] | 0 | [6 empty] | FDR | 0
110 | [5 empty] | 248E1210200 |  |  | BRACKET FOR RUNNING TEXT | 1 | • | [10 empty] | FOR REVIEW | [10 empty] | FOR REVIEW
111 | [5 empty] | 248E1210300 |  |  | INTERIOR LINNING FRAME ON CAB | 1 | • | [10 empty] | RELEASE | [10 empty] | RELEASE
112 | [5 empty] | 248E1210400 |  |  | DIRECTOR CABLE ON CAB | 1 | • | [10 empty] | RELEASE
113 |  |  |  | 250E12101000 |  |  |  |  | ROOF ARRANGEMENT TC1 & TC2 | 1 | • | [20 empty] | FDR | 0
114 |  |  |  |  | 251E1210100 |  |  |  | MAIN CONSTRUCTION OF ROOF TC1 & TC2 | 1 | • | [10 empty] | RELEASE |  |  | 1566.9 | 2023-09-13 |  | 1566.9 |  |  | 2023-09-13 | FDR | RELEASE
115 | [5 empty] | 251E1200200 |  |  | ROOF FRAMING TC1 & TC2 | 1 | • | • | • | • | • | • | [5 empty] | RELEASE | [6 empty] | 298.8 | 298.8 | 2023-09-13 |  | RELEASE
116 | [5 empty] | 251E1210300 |  |  | ROOF SHEATING TC1 & TC2 | 1 | • | [10 empty] | RELEASE | [6 empty] | 388.1 | 388.1 | 2023-09-13 | PDR | RELEASE
117 | [5 empty] | 251E1200400 |  |  | ROOF FRAMING AC | 1 | • | [10 empty] | RELEASE | [6 empty] | 717 | 717 | 2023-09-13 | PDR | RELEASE
118 | [5 empty] | 251E1210500 |  |  | ARR GUSSET ON ROOF TC1 & TC2 | 1 | • | [10 empty] | RELEASE | [6 empty] | 15.9 | 15.9 | 2023-09-13 | PDR | RELEASE
119 | [5 empty] | 251E1210600 |  |  | RAIN GUTTER TC1 & TC2 | 1 | • | [10 empty] | RELEASE | [6 empty] | 147.1 | 147.1 | 2023-09-13 | PDR | RELEASE
120 |  |  |  |  | 255E1210100 |  |  |  | ARRG CEILING FRAME | 1 | • | [13 empty] | 0 | [6 empty] | PDR | 0
121 | [5 empty] | 255E1210200 |  |  | CEILING FRAME PASSANGER ROOM (DUCTING+HANDGRIP) | 1 | • | [10 empty] | RELEASE |  |  | 0 | [6 empty] | PDR | RELEASE
122 | [5 empty] | 255E1200400 |  |  | BRACKET FOR ROLL FILTER | 1 | • | [10 empty] | RELEASE
123 |  |  |  |  | 258E1210100 |  |  |  | ARR BRACKET ON ROOF | 1 | • | [13 empty] | 0 | [7 empty] | 0
124 | [5 empty] | 258E1210200 |  |  | ARRANGEMENT ADAPTER ON ROOF | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
125 | [5 empty] | 258E1210300 |  |  | CABLE DIRECTOR ON ROOF | 1 | • | [10 empty] | RELEASE | [10 empty] | RELEASE
126 | [5 empty] | 258E1210400 |  |  | BRACKET FOR EXTERIOR SPEAKER | 1 | • | [10 empty] | RELEASE | [9 empty] | IDR | RELEASE
127 | [5 empty] | 258E1210500 |  |  | BRACKET FOR DOOR POCKET | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
128 | [5 empty] | 258E1210600 |  |  | BRACKET FOR ELECTRICAL CABINET | [12 empty] | RELEASE | [9 empty] | FDR | RELEASE
129 | [5 empty] | 258E1210700 |  |  | BRACKET FOR DOOR CONTROL UNIT | 1 | • | [10 empty] | RELEASE | [9 empty] | FDR | RELEASE
130 | [5 empty] | 258E1210800 |  |  | BRACKET AND PIPE FOR CABLE ANTENNA | 1 | • | [10 empty] | FOR REVIEW | [9 empty] | FDR | FOR REVIEW
131 | [5 empty] | 258E1210900 |  |  | CABLE DIRECTOR ON CABIN AND REAR ROOF FRAME | 1 | • | [10 empty] | RELEASE
[9 empty] | BATASBAWAH | [22 empty] | FDR | 0
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023 | [8 empty] | FDR | 0
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Fathur Rokhman Hidayat) | [9 empty] | (Hernawan Prasanto) | [12 empty] | ( Kristanto)
[7 empty] | No | BOBOT CATEGORY | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy)
[7 empty] | 1 |  | BOM RAW MATERIAL | 2 |  | 2 |  | 100% |  |  |  |  | BOBOT % DARI TOTAL DRAWING
[7 empty] | 1 | MAIN | MAIN CONSTRUCTION OF UNDERFRAME TC1&TC2 | 12 |  | 12 |  | 100% | [5 empty] | MAIN | 60%
[7 empty] | 2 | MAIN | MAIN CONSTRUCTION OF SIDEWALL TC1 & TC2 | 18 |  | 18 |  | 100%
[7 empty] | 3 | MAIN | MAIN CONSTRUCTION OF ENDWALL | 3 |  | 3 |  | 100% | [5 empty] | BKT | 40% | floor, interior SW/RF/EW, big komp
[7 empty] | 4 | MAIN | MAIN CONSTRUCTION OF MASKARA | 3 |  | 1 |  | 33.33% | [7 empty] | cable director, small komp.
[7 empty] | 5 | MAIN | MAIN CONSTRUCTION OF ROOF TC1 & TC2 | 6 |  | 6 |  | 100%
[9 empty] | GREEN CAR | 42 |  | 40 |  | 57.14%
[7 empty] | 1 | BKT | FLOOR CONSTRUCTION TC1 & TC2 | 3 |  | 0 |  | 0%
[7 empty] | 2 | BKT | ARR SUPORTING FRAME FOR FLOOR TC1 & TC2 | 8 |  | 0 |  | 0%
[7 empty] | 3 | BKT | ARRANGEMENT BRACKET & FRAME ON U/F TC2 | 24 |  | 3 |  | 12.5%
[7 empty] | 4 | BKT | ARR BRACKET ON SIDE WALL TC1 & TC2 | 8 |  | 7 |  | 87.5%
[7 empty] | 5 | BKT | ARR BRACKET ON ENDWALL TC1 & TC2 | 5 |  | 4 |  | 80%
[7 empty] | 6 | BKT | ARR CEILING FRAME ON CAB TC1 & TC2 | 2 |  | 2 |  | 100%
[7 empty] | 7 | BKT | ARR BRACKET WELDED ON CAB TC1 & TC2 | 2 |  | 1 |  | 50%
[7 empty] | 8 | BKT | ARRG CEILING FRAME | 1 |  | 1 |  | 100%
[7 empty] | 9 | BKT | ARR BRACKET ON ROOF | 7 |  | 6 |  | 85.71%
[9 empty] | BRACKET AND SUPPORT | 60 |  | 24 |  | 24%
[9 empty] | TOTAL DRAWING | 102 |  | 64
[9 empty] | PROGRESS TOTAL |  |  |  |  | 81.14%
62.75%
DRAWING UNTUK KEBUTUHAN CARBODY ASSY
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | SCOPE OF WORK
[8 empty] | 1 | CARBODY SHEEL (TC2) | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 2 | SIDEWALL ARRANGEMENT TC1 & TC2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 3 | ENDWALL ARRANGEMENT TC1 & TC2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 4 | DRIVER CAB ARRANGEMENT | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 5 | ROOF ARRANGEMENT TC1 & TC2 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[9 empty] | TOTAL DRAWING INKA | 5 |  | 0
[9 empty] | PROGRESS INKA |  |  |  |  | 0%
INKA

## RESUME (hidden)
NO | ITEM | APPROVAL PT. KCI | TC1 |  | M1 |  | M2 |  | T1 |  | T2 |  | T3 |  | TC2 |  | TARGET
|  |  | 3D | 2D | 3D | 2D | 3D | 2D | 3D | 2D | 3D | 2D | 3D | 2D | 3D | 2D
1 | UNDERFRAME
| ARR. (TC1&TC2) 21.0-E12102 | SUBMIT 7-8-23 | 70% | 10% | [10 empty] | 70% | 10% | 31/08/2023
| ARR.(M1&M2) 21.0-E12202 | SUBMIT 7-8-23 |  |  | 70% | 10% | 70% | 10% | [8 empty] | 31/08/2023
| ARR. (T1,T2&T3) 21.0-E12402 | SUBMIT 7-8-23 | [6 empty] | 70% | 10% | 70% | 10% | 70% | 10% |  |  | 31/08/2023
2 | SIDEWALL
| ARR. (TC1&TC2) 22.1-E12102 | SUBMIT 7-8-23 | 70% | 10% | [10 empty] | 70% | 10% | 31/08/2023
| ARR. (M1&M2) 22.1-E12202 | SUBMIT 7-8-23 |  |  | 60% | 10% | 60% | 10% | [8 empty] | 31/08/2023
| ARR. (T1,T2&T3) 22.1-E12402 | SUBMIT 7-8-23 | [6 empty] | 60% | 10% | 60% | 10% | 60% | 10% |  |  | 31/08/2023
3 | ROOF
| ARR. (M2,T1,T2,T3) 25.1-E12001 | SUBMIT 7-8-23 |  |  |  |  | 80% | 20% | 80% | 20% | 80% | 20% | 80% | 20% |  |  | 31/08/2023
| ARR. (TC1,TC2) 25.1-E12101 | SUBMIT 7-8-23 | 80% | 20% | [10 empty] | 80% | 20% | 31/08/2023
| ARR. (M1) 25.1-E12201 | SUBMIT 7-8-23 |  |  | 50% | 5% | [10 empty] | 31/08/2023
4 | ENDWALL
| ARR. (TC1,TC2, T1,T2,T3,M2) 23.1-E12001 | SUBMIT 7-8-23 | 70% | 10% |  |  | 70% | 10% | 70% | 10% | 70% | 10% | 70% | 10% | 70% | 10% | 31/08/2023
| ARR. (M1) 23.1-E12201 | SUBMIT 7-8-23 |  |  | 70% | 10% | [10 empty] | 31/08/2023
5 | CABIN
| ARR. (TC1)) 24.1-E12101 | NO SUBMIT | 20% | 0% | [12 empty] | 31/08/2023

## DAFTAR GAMBAR TOTAL REAL
[12 empty] | TOTAL PROGRESS | TOTAL PRELIMINARY DESIGN | TOTAL INTERMIEDIATE DESIGN | TOTAL FINAL DESGIN | RESUME TOTAL PROGRESS
No | DW NUMBER | Title | Car Type | [6 empty] | STATUS | REMARKS |  |  |  |  | JENIS KERETA | TOTAL DD | RELEASE | % TOTAL | PRELIMINARY DESIGN (PDR) |  |  | INTERMEDIATE DESIGN (IDR) |  |  | FINAL DESIGN (FDR) |  |  | TOTAL PROGRESS |  |  | FDR
|  |  | TC1 | M1 | M2 | T1 | T2 | T3 | TC2 |  |  | 86.88% | 100% | 97.14% | 50.54% |  |  |  |  | DD TOTAL | RELEASE | %-TASE | DD TOTAL | RELEASE | %-TASE | DD TOTAL | RELEASE | %-TASE | PDR + IDR |  | 0.7 | 0.3
1 | 210E1210100 | UNDERFRAME ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d |  |  |  |  | TC1 | 102 | 86 | 84.31% | 48 | 48 | 100% | 8 | 8 | 100% | 46 | 30 | 65.22% | 56 | 56 | 70%
2 | 210E1220100 | UNDERFRAME ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d |  |  |  |  | M1 | 88 | 74 | 84.09% | 36 | 36 | 100% | 6 | 6 | 100% | 46 | 30 | 65.22% | 42 | 42 | 70%
3 | 210E1230100 | UNDERFRAME ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d |  |  |  |  | M2 | 76 | 60 | 78.95% | 32 | 32 | 100% | 5 | 4 | 80% | 39 | 24 | 61.54% | 37 | 36 | 68.11%
4 | 210E1240100 | UNDERFRAME ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d |  |  |  |  | T1 | 75 | 50 | 66.67% | 30 | 30 | 100% | 2 | 2 | 100% | 43 | 18 | 41.86% | 32 | 32 | 70%
5 | 210E1250100 | UNDERFRAME ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d |  |  |  |  | T2 | 69 | 50 | 72.46% | 30 | 30 | 100% | 2 | 2 | 100% | 37 | 18 | 48.65% | 32 | 32 | 70%
6 | 210E1260100 | UNDERFRAME ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d |  |  |  |  | T3 | 65 | 34 | 52.31% | 30 | 30 | 100% | 2 | 2 | 100% | 33 | 2 | 6.061% | 32 | 32 | 70%
7 | 210E1270100 | UNDERFRAME ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d |  |  |  |  | TC2 | 102 | 86 | 84.31% | 48 | 48 | 100% | 8 | 8 | 100% | 46 | 30 | 65.22% | 56 | 56 | 70%
8 | 220E1210100 | SIDEWALL ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d | [19 empty] | 69.73% | 15.16% | 84.89%
9 | 220E1220100 | SIDEWALL ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d
10 | 220E1230100 | SIDEWALL ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d
11 | 220E1240100 | SIDEWALL ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d
12 | 220E1250100 | SIDEWALL ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d
13 | 220E1260100 | SIDEWALL ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d
14 | 220E1270100 | SIDEWALL ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
15 | 230E1210100 | ENDWALL ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d
16 | 230E1220100 | ENDWALL ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d
17 | 230E1230100 | ENDWALL ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d
18 | 230E1240100 | ENDWALL ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d
19 | 230E1250100 | ENDWALL ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d
20 | 230E1260100 | ENDWALL ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d
21 | 230E1270100 | ENDWALL ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
22 | 240E1210100 | CABIN ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d
23 | 240E1270100 | CABIN ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
24 | 230E1210100 | ROOF ARRANGEMENT TC1 | • | [7 empty] | ONLY FOR 3d
25 | 230E1220100 | ROOF ARRANGEMENT M1 | [8 empty] | ONLY FOR 3d
26 | 230E1230100 | ROOF ARRANGEMENT M2 |  | • | [6 empty] | ONLY FOR 3d
27 | 230E1240100 | ROOF ARRANGEMENT T1 |  |  | • | [5 empty] | ONLY FOR 3d
28 | 230E1250100 | ROOF ARRANGEMENT T2 |  |  |  | • |  |  |  |  | ONLY FOR 3d
29 | 230E1260100 | ROOF ARRANGEMENT T3 |  |  |  |  | • |  |  |  | ONLY FOR 3d
30 | 230E1270100 | ROOF ARRANGEMENT TC2 | [5 empty] | • |  |  | ONLY FOR 3d
1 | 210E1210200 | MAIN CONSTRUCTION OF UNDERFRAME TC1&TC2 | • | [5 empty] | • | RELEASE
2 | 210E1220200 | MAIN COSTRUCTION OF UNDERFRAME M1, M2 |  | • | • |  |  |  |  | RELEASE
3 | 210E1240200 | MAIN COSTRUCTION OF UNDERFRAME T |  |  |  | • | • | • |  | RELEASE
4 | 211E1210100 | FRONT PART ASSEMBLY | • | [5 empty] | • | RELEASE
5 | 211E1210200 | END BEAM FRONT TC | • | [5 empty] | • | RELEASE
6 | 211E1200100 | END PART ASSEMBLY | • | • | • | • | • | • | • | RELEASE
7 | 211E1200200 | END BEAM | • | • | • | • | • | • | • | RELEASE
8 | 211E1210400 | ANTI CLIMBER | • | [5 empty] | • | RELEASE
9 | 212E1200100 | BOLSTER | • | • | • | • | • | • | • | RELEASE
10 | 213E1210100 | MIDDLE PART ASSY TC | • | [5 empty] | • | RELEASE
11 | 213E1200100 | MIDDLE PART ASSY M |  | • | • |  |  |  |  | RELEASE
12 | 213K5600200 | JACKING PAD | • | • | • | • | • | • | • | RELEASE
13 | 221E1210200 | MAIN CONSTRUCTION OF SIDEWALL TC1 & TC2 | • | [5 empty] | • | RELEASE
14 | 221E1220200 | MAIN CONSTRUCTION OF SIDEWALL M1, M2 |  | • | • |  |  |  |  | RELEASE
15 | 221E1240200 | MAIN CONSTRUCTION OF SIDEWALL T |  |  |  | • | • | • | • | RELEASE
16 | 221E1200300 | MIDDLE SIDEWALL 1 --> (RUNNING TEXT) | • | • | • | • | • | • | • | RELEASE
17 | 221E1200400 | MIDDLE SIDEWALL 2 | • | • | • | • | • | • | • | RELEASE
18 | 221E1200500 | END SIDEWALL 1 --> (LEFT) | • | • | • | • | • | • | • | RELEASE
19 | 221E1200600 | END SIDEWALL 2 --> (RIGHT) |  | • | • | • | • | • |  | RELEASE
20 | 221E1200700 | PASSENGER ENTRANCE | • | • | • | • | • | • | • | RELEASE
21 | 221E1200800 | ARR GUSSET ON SIDEWALL T |  |  |  | • | • | • |  | RELEASE
22 | 221E1201000 | FRAME DOOR SUPPORT 1 | • | • | • | • | • | • | • | RELEASE
23 | 221E1201100 | FRAME DOOR SUPPORT 2 | • | • | • | • | • | • | • | RELEASE
24 | 221E1201200 | FRAME DOOR SUPPORT 2 | • | • | • | • | • | • | • | RELEASE
25 | 221E1210800 | MIDDLE SIDEWALL 3 --> (TC ONLY, SHORT LENGTH) | • | [5 empty] | • | RELEASE
26 | 221E1210900 | BEHIND CAB SIDEWALL 1 --> (LEFT) | • | [5 empty] | • | RELEASE
27 | 221E1211000 | BEHIND CAB SIDEWALL 2 --> (RIGHT) | • | [5 empty] | • | RELEASE
28 | 221E1211100 | DRIVER CAB ENTRANCE | • | [5 empty] | • | RELEASE
29 | 221E1211200 | ARR GUSSET ON SIDEWALL TC1 & TC2 | • | [5 empty] | • | RELEASE
30 | 221E1211300 | CABIN SIDEWALL 1 --> (LEFT) | • | [5 empty] | • | RELEASE
31 | 221E1211400 | CABIN SIDEWALL 2 --> (RIGHT) | • | [5 empty] | • | RELEASE
32 | 221E1211600 | END SIDEWALL 2 --> (RIGHT TC) | • | [5 empty] | • | RELEASE
33 | 221E1211700 | FRAME DOOR SUPPORT 3 --> (RIGHT TC) | • | [5 empty] | • | RELEASE
34 | 221E1211800 | FRAME DOOR SUPPORT 4 --> (LEFT TC) | • | [5 empty] | • | RELEASE
35 | 221E1220300 | MIDDLE SIDEWALL 2 --> (DUCT MOTOR) |  | • | • |  |  |  |  | RELEASE
36 | 221E1220400 | END SIDEWALL 3 --> (DUCT MOTOR) |  | • | • |  |  |  |  | RELEASE
37 | 221E1220800 | ARR GUSSET ON SIDEWALL M1,M2 |  | • | • |  |  |  |  | RELEASE
38 | 231E1200100 | MAIN CONSTRUCTION OF ENDWALL ALL | • | • | • | • | • | • | • | RELEASE
39 | 231E1200200 | END FRAMING | • | • | • | • | • | • | • | RELEASE
40 | 231E1200300 | END SHEETING | • | • | • | • | • | • | • | RELEASE
41 | 231E1200100 | MAIN CONSTRUCTION OF FRONT ENDWALL M1 |  | • | [5 empty] | RELEASE
42 | 231E1200400 | MAIN CONSTRUCTION OF REAR ENDWALL M1 |  | • | [5 empty] | RELEASE
43 | 231E1220200 | END FRAMING FRONT |  | • | [5 empty] | RELEASE
44 | 231E1220500 | END FRAMING REAR |  | • | [5 empty] | RELEASE
45 | 241E1210100 | MAIN CONSTRUCTION OF MASKARA | • | [5 empty] | • | RELEASE
46 | 241E1210200 | SHEATING MASKARA | • | [5 empty] | • | RELEASE
47 | 241E1210300 | FRAME MASKARA | • | [5 empty] | • | RELEASE
48 | 251E1210100 | MAIN CONSTRUCTION OF ROOF TC1 & TC2 | • | [5 empty] | • | RELEASE
49 | 251E1220100 | MAIN CONSTRUCTION OF ROOF M1 |  | • | [5 empty] | RELEASE
50 | 251E1200100 | MAIN CONSTRUCTION OF ROOF M2 & T |  |  | • | • | • | • |  | RELEASE
51 | 251E1210200 | ROOF FRAMING TC1 & TC2 | • | [5 empty] | • | RELEASE
52 | 251E1210300 | ROOF SHEATING TC1 & TC2 | • | [5 empty] | • | RELEASE
53 | 251E1200400 | ROOF FRAMING AC | • | • | • | • | • | • | • | RELEASE
54 | 251E1210500 | ARR GUSSET ON ROOF TC1 & TC2 | • | [5 empty] | • | RELEASE
55 | 251E1210600 | RAIN GUTTER TC1 & TC2 | • | [5 empty] | • | RELEASE
56 | 251E1220200 | ROOF FRAMING M1 |  | • | [5 empty] | RELEASE
57 | 251E1220300 | ROOF SHEATING M1 |  | • | [5 empty] | RELEASE
58 | 251E1220500 | ARR GUSSET ON ROOF M1 |  | • | [5 empty] | RELEASE
59 | 251E1220800 | ROOF FRAMING PANTOGRAPH |  | • | [5 empty] | RELEASE
60 | 251E1200200 | ROOF FRAMING M2,T |  |  | • | • | • | • |  | RELEASE
61 | 251E1200300 | ROOF SHEATING M2,T |  |  | • | • | • | • |  | RELEASE
62 | 251E1200500 | ARR GUSSET ON ROOF M2,T |  |  | • | • | • | • |  | RELEASE
63 | 251E1200600 | RAIN GUTTER M, T | • | • | • | • | • | • | • | RELEASE
63 | [9 empty] | 63 |  | 70% |  | 0.7
1 | 214E1210200 | ARRG FLOOR ON PASSENGER ROOM | • | [5 empty] | • | RELEASE
2 | 214E1210300 | ARR FLOOR PLATE ON CAB | • | [5 empty] | • | RELEASE
3 | 214E1220200 | ARRG FLOOR ON PASSENGER ROOM M1,M2 |  | • | • |  |  |  |  | RELEASE
4 | 214E1240200 | ARRG FLOOR ON PASSENGER ROOM |  |  |  | • | • | • |  | RELEASE
5 | 215E1210200 | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | • | [5 empty] | • | RELEASE
6 | 215E1210300 | BRACKET SUPPORT FLOOR ON CAB | • | [5 empty] | • | RELEASE
7 | 215E1210400 | DRAIN PIPE AND SUPPORT | • | [5 empty] | • | RELEASE
8 | 215E1210500 | TAPPING STRIP | • | [5 empty] | • | RELEASE
9 | 215E1210600 | TAPPING FOR DRIVER AND PASSENGER SEAT ON FLOOR | • | [5 empty] | • | RELEASE
10 | 215E1210700 | TAPPING FOR DOOR POCKET & INTERIOR CABINET | • | [5 empty] | • | RELEASE
11 | 215E1210800 | TAPPING FOR DRIVER DESK | • | [5 empty] | • | RELEASE | SIAP RELEASE
12 | 215E1220200 | BRACKET SUPPORT FLOOR ON PASSENGER ROOM |  | • | • |  |  |  |  | RELEASE
13 | 215E1220300 | DRAIN PIPE AND SUPPORT |  | • | • |  |  |  |  | RELEASE
14 | 215E1220400 | TAPPING STRIP |  | • | • |  |  |  |  | RELEASE
15 | 215E1220500 | TAPPING FOR PASSENGER SEAT ON FLOOR |  | • | • |  |  |  |  | RELEASE
16 | 215E1220600 | TAPPING FOR DOOR POCKET &INTERIOR CABINET |  | • | • |  |  |  |  | RELEASE
17 | 215E1240200 | BRACKET SUPPORT FLOOR ON PASSENGER ROOM |  |  |  | • | • | • |  | RELEASE
18 | 215E1240300 | DRAIN PIPE AND SUPPORT |  |  |  | • | • | • |  | RELEASE
19 | 215E1240400 | TAPPING STRIP |  |  |  | • | • | • |  | RELEASE
20 | 215E1240500 | TAPPING FOR PASSENGER SEAT ON FLOOR |  |  |  | • | • | • |  | RELEASE | BUTUH CEK
21 | 215E1240600 | TAPPING FOR INTERIOR CABINET |  |  |  | • | • | • |  | RELEASE | BUTUH CEK
22 | 218E1200200 | BRACKET FOR GROUNDING INTER CAR |  | • | • | • | • | • |  | FOR REVIEW
23 | 218E1200300 | BRACKET FOR LEVELING VALVE | • | • | • | • | • | • | • | RELEASE
24 | 218E1200400 | BRACKET FOR COUPLER SUPPORT |  | • | • | • | • | • |  | RELEASE | BUTUH CEK
25 | 218E1200500 | BRACKET FOR LADDER |  | • | • | • | • | • |  | RELEASE
26 | 218E1210200 | BRACKET FOR GROUNDING INTER CAR | • | [5 empty] | • | FOR REVIEW | INPUTAN BELUM FIX
27 | 218E1200300 | BRACKET FOR LEVELING VALVE | [7 empty] | RELEASE
28 | 218E1210400 | BRACKET FOR COUPLER SUPPORT | • | [5 empty] | • | RELEASE | BUTUH CEK
29 | 218E1210500 | BRACKET FOR CABLE DUCT | • | [6 empty] | FOR REVIEW | BUTUH CEK
30 | 218E1210600 | BRACKET FOR PNEUMATIC PIPING | • | [6 empty] | FOR REVIEW | BUTUH CEK
31 | 218E1210700 | HOLE FOR BATTERY BOX | • | [6 empty] | FOR REVIEW | BUTUH CEK
32 | 218E1210800 | BRACKET OF RECTIFIER BOX | • | [6 empty] | RELEASE
33 | 218E1210900 | BRACKET OF ELECTRIC CONTROL PANEL | • | [6 empty] | RELEASE
34 | 218E1211000 | BRACKET FOR LADDER | • | [6 empty] | RELEASE
35 | 218E1211100 | BRACKET OF AUX SWITCH | • | [6 empty] | RELEASE
36 | 218E1211400 | BRACKET OF AIR RESERVOIR | • | [6 empty] | RELEASE
37 | 218E1211500 | BRACKET OF TRANSFORMER FILTER BOX | • | [6 empty] | RELEASE | BUTUH CEK
38 | 218E1211600 | BRACKET OF COWCATCHER | • | [6 empty] | WORKING | INPUTAN BELUM FIX
39 | 218E1211700 | BRACKET OF JUNCTION COUPLER ELECTRIC | • | [6 empty] | 0 | INPUTAN BELUM FIX
40 | 218E1211800 | BRACKET OF PNEUMATIC HORN MODULE | • | [6 empty] | FOR REVIEW | REF. 30.1-E12117
41 | 218E1211900 | BRACKET OF APS BOX | • | [6 empty] | RELEASE
42 | 218E1212000 | BRACKET OF IVHB | • | [6 empty] | RELEASE
43 | 218E1212200 | HOLE FOR BRAKE CONTROL UNIT | • | [6 empty] | RELEASE
44 | 218E1212300 | BRACKET OF HGS (GROUND SWITCH) | • | [6 empty] | REVISI
45 | 218E1212400 | BRACKET OF GROUNDING PLATE | • | [6 empty] | FOR REVIEW | 0
46 | 218E1212500 | CABLE DIRECTOR ON UNDERFRAME | • | [6 empty] | FOR REVIEW | INPUTAN BELUM FIX
47 | 218E1220600 | BRACKET VVVF |  | • | • |  |  |  |  | RELEASE | 30.1-E12012
48 | 218E1220700 | BRACKET ELECTRIC CONTROL PANEL |  | • | • |  |  |  |  | RELEASE | 30.1-E12213
49 | 218E1220800 | BRACKET BRAKE RESISTOR |  | • | • |  |  |  |  | RELEASE | 30.1-E12010
50 | 218E1220900 | BRACKET CHOPPER BOX |  | • | • |  |  |  |  | RELEASE | 30.1-E12012
51 | 218E1221000 | BRACKET CHOPPER REACTOR |  | • | • |  |  |  |  | RELEASE
52 | 218E1221100 | BRACKET OF AIR RESEVOIR (100L) |  | • | • |  |  |  |  | RELEASE
53 | 218E1221200 | BRACKET OF BRACKET CONTROL MODULE |  | • | • |  |  |  |  | RELEASE | 30.1-E12203
54 | 218E1221300 | BRACKET FOR CABLE DUCT |  | • | • |  |  |  |  | FOR REVIEW | 30.1-E12015
55 | 218E1221400 | BRACKET FOR PNEUMATIC PIPING |  | • | • |  |  |  |  | FOR REVIEW | 30.1-E12220
56 | 218E1221500 | BRACKET MAIN SWITCH |  | • | [5 empty] | RELEASE
57 | 218E1221600 | BRACKET FILTER REACTOR |  | • | [5 empty] | FOR REVIEW | 30.1-E12207
58 | 218E1221700 | BRACKET HSCB BOX |  | • | [5 empty] | RELEASE
59 | 218E1221800 | BRACKET JUNCTION COUPLER ELECTRIC |  | • | [5 empty] | 0 | INPUTAN BELUM FIX
60 | 218E1221900 | BRACKET OF PANTOGRAPH CONTROL MODULE |  | • | [5 empty] | FOR REVIEW | 30.1-E12217
61 | 218E1222000 | BRACKET OF PANTOGRAPH DISCONNECTOR SWITCH |  | • | [5 empty] | RELEASE | 30.1-E12210
62 | 218E1222100 | BRACKET OF BUS FUSE |  | • | [5 empty] | RELEASE | 30.1-E12211
63 | 218E1222300 | BRACKET OF TRACTION MOTOR JUNCTION BOX |  | • | [5 empty] | WORKING | 30.1-E12212
64 | 218E1222400 | BRACKET OF GROUNDING PLATE |  | • | [5 empty] | FOR REVIEW | 0
65 | 218E1222500 | CABLE DIRECTOR ON UNDERFRAME |  | • | [5 empty] | FOR REVIEW | INPUTAN BELUM FIX
66 | 218E1231500 | BRACKET AIR RESEVOIR (150L) |  |  | • |  |  |  |  | RELEASE
67 | 218E1231600 | BRACKET OF FILTER REACTOR |  |  | • |  |  |  |  | WORKING
68 | 218E1231700 | BRACKET OF COMPRESSOR |  |  | • |  |  |  |  | WORKING
69 | 218E1231800 | BRACKET OF COMPRESSOR CONTROL PANEL |  |  | • |  |  |  |  | WORKING
70 | 218E1231900 | BRACKET OF EXPANSION BOX |  |  | • |  |  |  |  | WORKING
71 | 218E1232200 | BRACKET OF GROUNDING PLATE |  |  | •
72 | 218E1222300 | BRACKET OF TRACTION MOTOR JUNCTION BOX |  | • | • |  |  |  |  | WORKING
73 | 218E1232400 | CABLE DIRECTOR ON UNDERFRAME | [7 empty] | WORKING
74 | 218E1240400 | BRACKET FOR COUPLER SUPPORT |  |  |  | • | • | • |  | FOR REVIEW
75 | 218E1240600 | BRACKET OF ELECTRIC CONTROL PANEL |  |  |  | • | • | • |  | FOR REVIEW
76 | 218E1240700 | BRACKET OF BRAKE CONTROL UNIT |  |  |  | • | • | • |  | FOR REVIEW
77 | 218E1240800 | BRACKET OF AIR RESEVOIR (100L) |  |  |  | • | • | • |  | RELEASE
78 | 218E1241000 | BRACKET OF CABLE DUCTING |  |  |  | • | • | • |  | FOR REVIEW
79 | 218E1241100 | BRACKET OF PNEUMATIC PIPING |  |  |  | • | • | • |  | FOR REVIEW
80 | 218E1241200 | BRACKET OF TRANSFORMER FILTER BOX |  |  |  | • |  |  |  | WORKING
81 | 218E1241300 | BRACKET OF APS BOX |  |  |  | • |  |  |  | WORKING
82 | 218E1241400 | BRACKET OF RECTIFIER BOX |  |  |  | • |  |  |  | WORKING
83 | 218E1241500 | BRACKET OF AUXILIARY SWITCH |  |  |  | • |  |  |  | WORKING
84 | 218E1241600 | BRACKET OF IVHB |  |  |  | • |  |  |  | FOR REVIEW
85 | 218E1241700 | BRACKET OF BATTERY BOX |  |  |  | • |  |  |  | WORKING
86 | 218E1241900 | BRACKET OF HGS (GROUND SWITCH) |  |  |  | • |  |  |  | WORKING
87 | 218E1242000 | BRACKET OF EXPANSION BOX |  |  |  | • |  |  |  | FOR REVIEW
88 | 218E1242200 | BRACKET OF GROUNDING PLATE |  |  |  | • |  |  |  | WORKING
89 | 218E1242300 | CABLE DIRECTOR ON UNDERFRAME |  |  |  | • |  |  |  | WORKING
90 | 218E1251000 | BRACKET OF CABLE DUCTING | [7 empty] | FOR REVIEW
91 | 218E1251100 | BRACKET OF PNEUMATIC PIPING | [7 empty] | FOR REVIEW
92 | 218E1251300 | BRACKET OF AIR RESEVOIR (150L) |  |  |  |  | • |  |  | PRE-RELEASE
93 | 218E1251400 | BRACKET OF AIR SUPPLY |  |  |  |  | • |  |  | FOR REVIEW
94 | 218E1251600 | BRACKET OF GROUNDING PLATE |  |  |  |  | • |  |  | WORKING
95 | 218E1251700 | CABLE DIRECTOR ON UNDERFRAME |  |  |  |  | • |  |  | WORKING
96 | 218E1261200 | BRACKET OF GROUNDING PLATE | [5 empty] | • |  | WORKING
97 | 218E1261300 | CABLE DIRECTOR ON UNDERFRAME | [5 empty] | • |  | WORKING
98 | 218E1270500 | BRACKET FOR CABLE DUCT | [6 empty] | •
99 | 218E1270600 | BRACKET FOR PNEUMATIC PIPING | [6 empty] | •
100 | 218E1270700 | BRACKET OF BATTERY BOX | [6 empty] | •
101 | 218E1270800 | BRACKET OF RECTIFIER BOX | [6 empty] | •
102 | 218E1270900 | BRACKET OF ELECTRIC CONTROL PANEL | [6 empty] | •
103 | 218E1271000 | BRACKET FOR LADDER | [6 empty] | •
104 | 218E1271100 | BRACKET OF AUX SWITCH | [6 empty] | •
105 | 218E1271200 | BRACKET OF TERMINAL BOX | [6 empty] | •
106 | 218E1271300 | BRACKET OF LGS (GROUND SWITCH) | [6 empty] | •
107 | 218E1271400 | BRACKET OF AIR RESERVOIR | [6 empty] | •
108 | 218E1271500 | BRACKET OF TRANSFORMER FILTER BOX | [6 empty] | •
109 | 218E1271600 | BRACKET OF COWCATCHER | [6 empty] | •
110 | 218E1271700 | BRACKET OF JUNCTION COUPLER ELECTRIC | [6 empty] | •
111 | 218E1271800 | BRACKET OF PNEUMATIC HORN MODULE | [6 empty] | •
112 | 218E1271900 | BRACKET OF APS BOX | [6 empty] | •
113 | 218E1272000 | BRACKET OF IVHB | [6 empty] | •
114 | 218E1272100 | BRACKET OF BATTERY PANEL | [6 empty] | •
115 | 218E1272200 | BRAKE OF CONTROL MODULE | [6 empty] | •
116 | 218E1272300 | BRACKET OF HGS (GROUND SWITCH) | [6 empty] | •
117 | 218E1272400 | BRACKET OF GROUNDING PLATE | [6 empty] | •
118 | 218E1272500 | CABLE DIRECTOR ON UNDERFRAME | [6 empty] | •
119 | 228E1210200 | ARRANGEMENT ADAPTER ON SIDEWALL | • | [5 empty] | • | RELEASE
120 | 228E1210300 | BRACKET FOR CURTAIN | • | [5 empty] | • | RELEASE
121 | 228E1210400 | BRACKET FOR DOOR ENGINE ENTRANCE | • | [5 empty] | • | RELEASE
122 | 228E1210500 | BRACKET FOR LUGGAGE RACK | • | [5 empty] | • | RELEASE
123 | 228E1210600 | BRACKET EMERGENCY DOOR RELEASE | • | [5 empty] | • | RELEASE | BUTUH CEK
124 | 228E1211000 | BRACKET FOR GUTTER PIPE AT CABIN | • | [5 empty] | • | RELEASE
125 | 228E1220200 | ARRANGEMENT OF ADAPTER ON SIDEWALL |  | • | • |  |  |  |  | RELEASE
126 | 228E1200300 | BRACKET FOR CURTAIN |  | • | • | • | • | • |  | RELEASE
127 | 228E1200400 | BRACKET FOR DOOR ENGINE ENTRANCE |  | • | • | • | • | • |  | RELEASE
128 | 228E1200500 | BRACKET FOR LUGGAGE RACK |  | • | • | • | • | • |  | RELEASE
129 | 228E1200600 | BRACKET FOR EMERGENCY DOOR RELEASE |  | • | • | • | • | • |  | RELEASE | BUTUH CEK
130 | 228E1200700 | BRACKET FOR RUNNING TEXT | • | • | • | • | • | • | • | RELEASE
131 | 228E1200900 | BRACKET FOR FOLDING SEAT | • | • | • | • | • | • | • | RELEASE
132 | 228E1200100 | BRACKET FOR INTERIOR PANEL FRONT END |  | • | • | • | • | • |  | RELEASE
133 | 228E1240200 | ARRANGEMENT OF ADAPTER ON SIDEWALL |  |  |  | • | • | • |  | RELEASE
134 | 238E1210200 | ARRANGEMENT ADAPTER ON ENDWALL | • | [5 empty] | • | RELEASE
135 | 238E1210300 | BRACKET FOR DOOR CLOSER | • | [5 empty] | • | RELEASE
136 | 238E1210400 | BRACKET ENDWALL PANEL | • | [5 empty] | • | RELEASE | 0
137 | 238E1210600 | BRACKET OF FALLING PROTECTOR | • | [5 empty] | • | RELEASE
138 | 238E1220200 | ARRANGEMENT ADAPTER ON ENDWALL |  | • | [5 empty] | RELEASE | 0
139 | 238E1220300 | BRACKET FOR DOOR CLOSER |  | • | [5 empty] | RELEASE
140 | 238E1220400 | BRACKET ENDWALL PANEL |  | • | [5 empty] | RELEASE
141 | 238E1200200 | ARRANGEMENT ADAPTER ON ENDWALL |  |  | • | • | • | • |  | RELEASE
142 | 238E1200300 | BRACKET FOR DOOR CLOSER |  |  | • | • | • | • |  | RELEASE
143 | 238E1200400 | BRACKET ENDWALL PANEL |  |  | • | • | • | • |  | RELEASE
144 | 238E1200600 | BRACKET OF FALLING PROTECTOR |  |  | • | • | • | • |  | RELEASE
145 | 238E1220600 | BRACKET OF FALLING PROTECTOR |  | • | [5 empty] | RELEASE
146 | 238E1220700 | BRACKET FOR CABLE AND PIPE PANTOGRAPH |  | • | [5 empty] | RELEASE
147 | 245E1210200 | CEILING FRAME ON CAB | • | [5 empty] | • | RELEASE | 0
148 | 245E1210300 | DIRECTOR CABLE ON CEILING FRAME CAB | • | [5 empty] | • | RELEASE | BUTUH CEK
149 | 248E1210200 | INTERIOR LINNING FRAME ON CAB | • | [5 empty] | • | RELEASE | BUTUH CEK
150 | 248E1210300 | DIRECTOR CABLE ON CAB | • | [5 empty] | • | RELEASE | BUTUH CEK
151 | 255E1210200 | CEILING FRAME PASSENGER ROOM (DUCTING+HANDGRIP) | • | [5 empty] | • | RELEASE | SIAP RELEASE
152 | 255E1220200 | CEILING FRAME PASSANGER ROOM (DUCTING+HANDGRIP) |  | • | [5 empty] | RELEASE
153 | 255E1200200 | CEILLING FRAMING PASSENGER ROOM (T) |  |  | • | • | • | •
154 | 258E1210200 | ARRANGEMENT ADAPTER ON ROOF | • | [5 empty] | • | RELEASE
155 | 258E1210300 | CABLE DIRECTOR ON ROOF | • | [5 empty] | • | RELEASE
156 | 258E1200400 | BRACKET FOR EXTERIOR SPEAKER | • | • | • | • | • | • | • | RELEASE
157 | 258E1210500 | BRACKET FOR DOOR POCKET | • | [6 empty] | RELEASE
158 | 258E1210600 | BRACKET FOR ELECTRICAL CABINET PANEL | • | [6 empty] | RELEASE
159 | 258E1210700 | BRACKET FOR DOOR CONTROL UNIT | • | [5 empty] | • | RELEASE
160 | 258E1210800 | BRACKET AND PIPE FOR CABLE ANTENNA | • | [6 empty] | FOR REVIEW | BUTUH CEK
161 | 258E1210900 | CABLE DIRECTOR ON CABIN AND REAR ROOF FRAME | • | [6 empty] | RELEASE
162 | 258E1220200 | ARRANGEMENT ADAPTER ON ROOF |  | • | [5 empty] | RELEASE
163 | 258E1220300 | CABLE DIRECTOR ON ROOF |  | • | [5 empty] | RELEASE
164 | 258E1220500 | BRACKET FOR DOOR POCKET |  | • | [5 empty] | RELEASE
165 | 258E1200600 | BRACKET FOR ELECTRICAL CABINET ON ENDWALL |  | • | • | • | • | • |  | RELEASE
166 | 258E1220700 | BRACKET FOR DOOR CONTROL UNIT |  | • | [5 empty] | RELEASE
167 | 258E1220800 | BRACKET OF SURGE ARRESTER |  | • | [5 empty] | RELEASE
168 | 258E1220900 | BRACKET OF MANUAL HOOK RELEASE |  | • | [5 empty] | FOR REVIEW
169 | 258E1221000 | BRACKET OF CABLE DUCT PANTOGRAPH |  | • | [5 empty] | 0
170 | 258E1221100 | BRACKET OF RISE DETECTION BOX |  | • | [5 empty] | RELEASE
171 | 258E1221200 | BRACKET OF PIPING PANTOGRAPH |  | • | [5 empty] | 0
172 | 258E1221300 | CABLE DIRECTOR ON REAR ROOF FRAME |  | • | [5 empty] | RELEASE
173 | 258E1200200 | ARRANGEMENT ADAPTER ON ROOF |  |  | • | • | • | • |  | RELEASE
174 | 258E1200300 | CABLE DIRECTOR ON ROOF |  |  | • | • | • | • |  | FOR REVIEW
175 | 258E1200500 | BRACKET FOR DOOR POCKET |  |  | • | • | • | • |  | RELEASE
176 | 258E1200700 | BRACKET FOR DOOR CONTROL UNIT |  |  | • | • | • | • |  | PRE-RELEASE
176 | [9 empty] | 99 |  | 16.88% |  | 0.3
239

## FEM ANALISIS
[17 empty] | Project |  | : 16 TS KRL KCI (E12) | [5 empty] | WEIGHT LIMIT (KG) : |  | 8000
[17 empty] | Document Number |  | : | [5 empty] | WEIGHT EST. (KG) |  | 0
[9 empty] | LIST DOKUMEN | [7 empty] | Date of Issue |  | : | 2024-07-24 |  |  |  |  | PROGRESS TOTAL |  | #REF!
[9 empty] | FEM ANALYSIS | [7 empty] | Revision |  | : 0
[17 empty] | Page |  | :
[17 empty] | Car Type |  | : ALL
Detail Berat (kg)
No. | DRAWING NUMBER | [7 empty] | TITLE | QTY | CAR TYPE | [5 empty] | MONITORING PROGRESS |  |  |  |  | STATUS DD | REVISI | REMARK (SOW) | WEIGHT EST. (KG) | Tanggal Pengambilan Berat |  | WEIGHT EST. (KG)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1&2 | M1 | M2 | T1 | T2 | T3 | 3D | 2D | SHRINKWARP | EO | DRAFTER |  |  |  | LVL 7 |  |  | LVL 5 | LVL 6 | LVL7
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Tanggal : JANUARI 2023 | [9 empty] | Tanggal : JANUARI 2023 | [12 empty] | Tanggal : JANUARI 2023
Disiapkan oleh : Staf Desain Bogie & Carbody | [9 empty] | Diperiksa oleh: Manager Desain Bogie & Carbody | [12 empty] | Disahkan oleh: Senior Manager Desain Mekanik
(Fathur Rokhman Hidayat) | [9 empty] | (Hernawan Prasanto) | [12 empty] | ( Kristanto)
[7 empty] | No | BOBOT CATEGORY | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy)
[7 empty] | 1 |  | 0 | 1 |  | 0 |  | 0% |  |  |  |  | BOBOT % DARI TOTAL DRAWING
[7 empty] | 1 | MAIN | #REF! | 0 |  | 0 |  | #DIV/0! | [5 empty] | MAIN | 60%
[7 empty] | 2 | MAIN | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 3 | MAIN | #REF! | 0 |  | #REF! |  | #REF! | [5 empty] | BKT | 40% | floor, interior SW/RF/EW, big komp
[7 empty] | 4 | MAIN | #REF! | 0 |  | #REF! |  | #REF! | [7 empty] | cable director, small komp.
[7 empty] | 5 | MAIN | #REF! | 0 |  | #REF! |  | #REF!
[9 empty] | GREEN CAR | 0 |  | 35 |  | #DIV/0!
[7 empty] | 1 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 2 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 3 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 4 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 5 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 6 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 7 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 8 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 9 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[7 empty] | 10 | BKT | #REF! | 0 |  | #REF! |  | #REF!
[9 empty] | BRACKET AND SUPPORT | 0 |  | 20 |  | 20%
[9 empty] | TOTAL DRAWING | 0 |  | 55
[9 empty] | PROGRESS TOTAL |  |  |  |  | #DIV/0!
#DIV/0!
DRAWING UNTUK KEBUTUHAN CARBODY ASSY
[8 empty] | No | Title (Judul Sub Assy) | Total (Total Drawing per sub Assy) |  | Release (Jumlah Status Release Drawing per sub Assy) |  | %-tase (besaran % tase per sub assy) |  | SCOPE OF WORK
[8 empty] | 1 | 0 | 1 |  | 0 |  | 0% |  | INKA 3D+2D
[8 empty] | 2 | #REF! | 0 |  | #REF! |  | #REF! |  | INKA 3D+2D
[8 empty] | 3 | #REF! | 0 |  | #REF! |  | #REF! |  | INKA 3D+2D
[8 empty] | 4 | #REF! | 0 |  | #REF! |  | #REF! |  | INKA 3D+2D
[8 empty] | 5 | #REF! | 0 |  | #REF! |  | #REF! |  | INKA 3D+2D
[9 empty] | TOTAL DRAWING INKA | 1 |  | #REF!
[9 empty] | PROGRESS INKA |  |  |  |  | #REF!
INKA