## DRAWING LIST
[5 empty] | PROJECT |  |  |  | : 16 TS KCI | PROCESS INSTRUCTION LIST 16 TS KCI
[5 empty] | REVISION |  |  |  | : 00
[5 empty] | DATE |  |  |  | : 21 JULI 2024
Total Items | [8 empty] | Revision Item | [25 empty] | DD ELECTRIC |  | DD FABRICATION |  |  | DD MECHANICAL |  | PI FINISHING | [5 empty] | Tingkat | Lama Pengerjaan (Hari) | Jumlah Dokumen | % Tingkatan Dokumen | Lama Pengerjaan
Tingkat 1
Closed Items | [8 empty] | Progressing Item | [25 empty] | PI ELECTRIC |  | PI FABRICATION |  |  | PI MECHANICAL SYSTEM |  | Rev JO | [5 empty] | Tingkat 2
Tingkat 3
PI | [8 empty] | PI | [25 empty] | DD BOGIE |  | DD SPECIAL PROCESS |  |  | DD INTERIOR | [7 empty] | Total
PRE & INTER | [8 empty] | FINAL DESIGN
[35 empty] | PI BOGIE |  | PI SPECIAL PROCESS |  |  | PI INTERIOR |  | JO
No | DD NUMBER | DOC PROSES NUMBER | [6 empty] | Title | KPI | Car Type | [6 empty] | Paper |  | DD | Rev | Revisi | [7 empty] | PI |  | Rev Drawing |  | DD STATUS |  | PRE & INT | FINAL DESIGN | PT STATUS | REMARKS | PIC | AUTHOR INITIAL |  |  | Tingkatan | Jumlah Hari | Start Date | Estimasi Finish |  |  | TABEL BANTU |  |  | PG Cons | PP Cons | PP Cons * Sheet | Bobot Rev | PP Cons * Sheet
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | TC1 | M1 | M2 | T1 | T2 | T3 | TC2 | Size | Sheet |  |  | Rev 0 | Rev A | Rev B | Rev C | Rev D | Rev E | Rev F | Rev G | Planning | Finish date | Start Date | Due date | RELEASE DATE | STATUS | [5 empty] | DW | CK | APV | [6 empty] | Tingkat | Jumlah hari
BOGIE
|  |  | FC | MB112203010001 |  |  |  |  | BOGIE FRAME ASSY MB) | Bogie | ● | ● | ● | ● | ● |  |  | A1 | 3 |  | A | 2023-10-26 | 2024-07-02 |  |  |  |  | TURUN ULANG |  | ARU | YUK |  |  |  |  | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | TB162203020101 |  |  |  |  | BOGIE FRAME ASSY TB) | Bogie | ● | ● | ● | ● | ● |  |  | A1 | 3 |  | A |  | 2024-07-02 | [12 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | TB1622-03.2-00001 |  |  |  |  | TRANSOM ASSY | Bogie | ● | ● | ● | ● | ● |  |  | A1 | 2 |  | B |  | 2023-10-26 | 2024-02-12 |  |  |  | TURUN ULANG |  | ARU | YUK |  |  |  |  | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | TB1622-03.1-00001 |  |  |  |  | SIDE FRAME ASSY | Bogie | ● | ● | ● | ● | ● |  |  | A1 | 3 |  | A | 2023-10-26 | 2024-02-12 |  |  |  |  | TURUN ULANG |  | ARU | YUK |  |  |  |  | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI | MB1122-03.0-100 |  |  |  |  | BOGIE FRAME ASSY MB | Bogie | ● | ● | ● | ● | ● |  |  | A3 | 5 |  | 0 | 2023-10-27 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI | MB1122-10.0-101 |  |  |  |  | SERVICE BRAKE PIPING 01 MB | Bogie |  | ● | ● |  |  |  |  | A3 | 3 |  | 0 | [13 empty] | Open | [5 empty] | EPP | APK | EKN
|  |  | PI | MB1122-10.0-102 |  |  |  |  | SERVICE BRAKE PIPING 02 MB | Bogie |  | ● | ● |  |  |  |  | A3 | 3 |  | 0 | 2024-04-24 | [13 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | MB1122-11.0-120 |  |  |  |  | BRACKET FOR GROUNDING CABLE ASSEMBLY | Bogie |  | ● | ● |  |  |  |  | A3 | 3 |  | 0 | 2024-08-03 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | MB1122-12.0-200 |  |  |  |  | LETTERING & SIGN ASSY MB | Bogie |  | ● | ● |  |  |  |  | A3 | 2 |  | 0 | 2023-12-29 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622038200 |  |  |  |  | BOGIE FRAME ASSY TB | Bogie | ● | ● | ● | ● | ● |  |  | A3 | 5 |  | 0 | 2023-10-27 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI | TB1622-02.0-005 |  |  |  |  | GROUND EARTHING ASSEMBLY | Bogie |  | ● | ● |  |  |  |  | A3 | 5 |  | 0 | 2024-01-03 | [13 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | TB1622-02.0-200 |  |  |  |  | AXLE BOX ASSEMBLY | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 6 |  | 0 | 2024-01-09 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622-02.0-300 |  |  |  |  | SPEED SENSOR ASSEMBLY | Bogie | ● | [5 empty] | ● | A3 | 5 |  | 0 | 2024-01-02 | [13 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | TB1622-03.0-20102 |  |  |  |  | PROSEDUR INSTALASI KEBOCORAN FRAME | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 5 |  | 0 | 2024-10-25 | [13 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | TB1622-05.0-100 |  |  |  |  | RAIL GUARD ASSEMBLY | Bogie | ● | [5 empty] | ● | A3 | 3 |  | 0 | 2024-12-19 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622-07.0-000 |  |  |  |  | SECONDARY SUSPENSION ARRANGEMENT | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 5 |  | 0 | 2024-06-09 | [13 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  |  | 070E11002 |  |  |  |  | ANTI ROLL TORSION BAR ASSEMBLY | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 5 |  | 0 | 2024-07-11 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622-08.0-200 |  |  |  |  | ASSEMBLY BRAKING TB | Bogie | ● |  |  | ● | ● | ● | ● | A3 | 4 |  | 0 | 2024-09-01 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622-08.0-220 |  |  |  |  | MANUAL RELEASE ASSEMBLY | Bogie | ● |  |  | ● | ● | ● | ● | A3 | 4 |  | 0 | 2024-01-25 | [13 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | PI TB162208000101 |  |  |  |  | TEST BRAKE BOGIE | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 2 |  | 0 | [13 empty] | Open | [5 empty] | EPP | APK | EKN
|  |  | PI | TB1622-10.0-101 |  |  |  |  | SERVICE BRAKE PIPING 01 | Bogie | ● |  |  | ● | ● | ● | ● | A3 | 3 |  | 0 | 2024-04-29 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622-10.0-102 |  |  |  |  | SERVICE BRAKE PIPING 02 | Bogie | ● |  |  | ● | ● | ● | ● | A3 | 3 |  | 0 | 2024-04-24 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622-10.0-202 |  |  |  |  | PARKING BRAKE PIPING (TB) | Bogie | ● |  |  | ● | ● | ● | ● | A3 | 3 |  | 0 | 2024-01-06 | [13 empty] | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | TB1622-10.0-220 |  |  |  |  | BALANCING VALVE HOSE ASSY | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 3 |  | 0 | 2024-04-29 | 2024-01-30 | [12 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | TB1622-11.0-130 |  |  |  |  | BRACKET FOR SPEED SENSOR CABLE | Bogie | ● | [5 empty] | ● | A3 | 4 |  | 0 | 2024-02-22 | [13 empty] | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | TB1622-11.0-131 |  |  |  |  | INSTALLATION OF LIFTING CABLE EQUIPED | Bogie | ● |  |  | ● | ● | ● | ● | A3 | 3 |  | 0 | 2024-01-30 | [7 empty] | DRY | YUK |  |  |  | CLOSED | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  | PI | 06.0-E12000 |  |  |  |  | FITTING PRIMARY SUSPENSION | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 18 |  | 0 | 2024-02-02 | [7 empty] | DRY | YUK |  |  |  | CLOSED | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  | PI | 07.0-E12002 |  |  |  |  | ANTI ROLL TORSION BAR ASSEMBLY | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 4 | A3 | 0 | 2024-05-27 | [7 empty] | DRY | YUK |  |  |  | CLOSED | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  |  | MB1122050100 |  |  |  |  | INSTALLATION OF MOTOR & GEARBOX | Bogie |  | ● | ● |  |  |  |  | A3 | 4 |  | 0 | 2024-05-27 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  |  | MB1122100101 |  |  |  |  | SERVICE BRAKE PIPING MB 01 | Bogie |  | ● | ● |  |  |  |  | A3 | 4 |  | 0 | 2024-05-27 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | EPP | APK | EKN
|  |  |  | MB1122100102 |  |  |  |  | SERVICE BRAKE PIPING MB 02 | Bogie |  | ● | ● |  |  |  |  | A4 | 4 |  | 0 | 2024-04-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
|  |  |  | TB1622-13.0-00001 |  |  |  |  | BOGIE TO CARBODY CONNECTION | Bogie | ● | ● | ● | ● | ● | ● | ● | A3 | 4 | A3 | 0 | 2024-07-11 | [7 empty] | DRY | YUK |  |  |  | CLOSED | CLOSED | CLOSED |  |  |  | DRY | APK | EKN
Fabrication
|  |  | FC | 200E1210101 |  |  |  |  | CARBODY ASSY | Fabrication | ● | [6 empty] | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 200E1220101 |  |  |  |  | CARBODY ASSY | Fabrication |  | ● | [5 empty] | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 200E1230101 |  |  |  |  | CARBODY ASSY | Fabrication |  |  | ● |  |  |  |  | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 200E1240101 |  |  |  |  | CARBODY ASSY | Fabrication |  |  |  | ● |  |  |  | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 200E1250101 |  |  |  |  | CARBODY ASSY | Fabrication |  |  |  |  | ● |  |  | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 200E1260101 |  |  |  |  | CARBODY ASSY | Fabrication | [5 empty] | ● |  | A1 | 1 |  | A | 2023-10-26 | 2024-01-26 | [12 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 210E1210101 |  |  |  |  | UNDERFRAME | Fabrication | ● | [6 empty] | A1 | [17 empty] | CANCELLED | CANCELLED |  |  |  | ARU | YUK | EKN
|  |  | FC | 210E1210201 |  |  |  |  | MAIN CONSTRUCTION OF UNDERFRAME (TC1 & TC2) | Fabrication | ● | [6 empty] | A1 | 2 |  | A | 2023-10-26 | 2024-06-27 | [12 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 210E1220101 |  |  |  |  | UNDERFRAME | Fabrication |  | ● | ● |  |  |  |  | A1 | [17 empty] | CANCELLED | CANCELLED |  |  |  | ARU | YUK | EKN
|  |  | FC | 210E1220201 |  |  |  |  | MAIN CONSTRUCTION OF UNDERFRAME (M1 & M2) | Fabrication |  | ● | ● |  |  |  |  | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 210E1240101 |  |  |  |  | UNDERFRAME | Fabrication |  |  |  | ● | ● |  |  | A1 | [17 empty] | CANCELLED | CANCELLED |  |  |  | ARU | YUK | EKN
|  |  | FC | 210E1240201 |  |  |  |  | MAIN CONSTRUCTION OF UNDERFRAME T1, T2, T3 | Fabrication |  |  |  | ● | ● | ● |  | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 211E1200101 |  |  |  |  | END PART ASSEMBLY (M1 & M2) | Fabrication | ● |  |  | ● | ● | ● |  | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 211E1210101 |  |  |  |  | FRONT PART ASSEMBLY (TC) | Fabrication | ● | [6 empty] | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 211E1220101 |  |  |  |  | END PART ASSEMBLY (M1 & M2) | Fabrication |  | ● | ● |  |  |  |  | A1 | 1 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 212E1200101 |  |  |  |  | BOLSTER ASSY | Fabrication | [7 empty] | A1 | 2 |  | A | 2023-10-30 | 2024-06-27 | [12 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | 221E1210201 |  |  |  |  | MAIN CONSTRUCTION OF SIDEWALL CONSTRUCTION (TC1 & TC2) | Fabrication | ● | [6 empty] | A1 | 21 |  | 0 | 2023-11-06 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 221E1220201 |  |  |  |  | MAIN CONSTRUCTION OF SIDEWALL CONSTRUCTION (M1 & M2) | Fabrication |  | ● | ● |  |  |  |  | A1 | 8 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 221E1240201 |  |  |  |  | MAIN CONSTRUCTION OF SIDEWALL CONSTRUCTION (T1, T2 & T3) | Fabrication |  |  |  | ● | ● | ● |  | A1 | 12 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | FC | 231E1210101 |  |  |  |  | MAIN CONSTRUCTION OF ENDWALL TC1, TC2, M2, T1, T2 & T3 | Fabrication | ● |  | ● | ● | ● | ● |  | A1 | 2 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | 231E1220101 |  |  |  |  | MAIN CONSTRUCTION OF ENDWALL M1 | Fabrication |  | ● | [5 empty] | A1 | 2 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | 241E1210101 |  |  |  |  | MAIN CONSTRUCTION OF MASKARA | Fabrication | ● | [6 empty] | A1 | 3 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | 251E1200101 |  |  |  |  | MAIN CONSTRUCTION OF ROOF T1 T2 T3 & M2 | Fabrication |  |  | ● | ● | ● | ● |  | A1 | 4 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | 251E1210101 |  |  |  |  | MAIN CONSTRUCTION OF ROOF TC1 & TC2 | Fabrication | ● | [6 empty] | A1 | 4 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | 251E1220101 |  |  |  |  | MAIN CONSTRUCTION OF ROOF M1 | Fabrication |  | ● | [5 empty] | A1 | 4 |  | 0 | 2023-10-26 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | FC | 311E12101001 |  |  |  |  | COWCATCHER ASSEMBLY | Fabrication | ● | [5 empty] | ● | A1 | 3 |  | 0 | 2024-06-27 | [13 empty] | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI200E12101 | [5 empty] | CARBODY ASSY | Fabrication | ● | [6 empty] | A3 | 11 |  | A | 2024-05-03 | 2024-06-28 | [13 empty] | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI200E12201 | [5 empty] | CARBODY ASSY | Fabrication |  | ● | [5 empty] | A3 | 11 |  | A | 2024-04-19 | 2024-06-28 | [13 empty] | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI200E12301 | [5 empty] | CARBODY ASSY | Fabrication |  |  | ● |  |  |  |  | A3 | [18 empty] | OPEN |  |  |  | ARU | YUK | EKN
|  |  | PI200E12401 | [5 empty] | CARBODY ASSY | Fabrication |  |  |  | ● |  |  |  | A3 | [22 empty] | ARU | YUK | EKN
|  |  | PI200E12501 | [5 empty] | CARBODY ASSY | Fabrication |  |  |  |  | ● |  |  | A3 | [22 empty] | ARU | YUK | EKN
|  |  | PI200E12601 | [5 empty] | CARBODY ASSY | Fabrication | [5 empty] | ● |  | A3 | [22 empty] | ARU | YUK | EKN
|  |  | PI21021002 | [5 empty] | STANDART MARKING CENTER LINE AREA FABRIKASI | Fabrication | ● | ● | ● | ● | ● | ● |  | A3 | 3 |  | 0 | 2023-09-09 | [13 empty] | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
A3
|  |  | 214E1210200 | [5 empty] | ARRG ON FLOOR PASSENGER ROOM | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DIM | YUK
|  |  | 214E1210300 | [5 empty] | ARR FLOOR ON CAB | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DIM | YUK
|  |  | 214E1220200 | [5 empty] | ARRG FLOOR ON PASSENGER ROOM M1,M2 | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DIM | YUK
|  |  | 214E1240200 | [5 empty] | ARRG FLOOR ON PASSENGER ROOM | Fabrication |  |  |  | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DIM | YUK
|  |  | 215E1210200 | [5 empty] | BRACKET SUPPORT FLOOR ON PASSANGER ROOM | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED
|  |  | 215E1210300 | [5 empty] | BRACKET SUPPORT FLOOR ON CAB | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  | PRIORITY 2 | DIM | YUK | EKN
|  |  | 215E1210400 | [5 empty] | DRAIN PIPE AND SUPPORT | Fabrication | ● | [5 empty] | ● | A3 | 5 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI215E12105 | [5 empty] | TAPPING STRIP | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | 215E1210600 | [5 empty] | TAPPING FOR DRIVER AND PASSENGER SEAT ON FLOOR | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1210700 | [5 empty] | TAPPING FOR DOOR POCKET & INTERIOR CABINET | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | CLOSED | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1210800 | [5 empty] | TAPPING STRIP FOR EVACUATION LINE | Fabrication | ● | [6 empty] | A3
|  |  | PI215E12109 | [5 empty] | HOLE FOR DRAIN SUPPORT | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-02-02 | [12 empty] | CLOSED |  | CLOSED
|  |  | 215E1220100 | [5 empty] | ARR SUPORTING FRAME FOR FLOOR M1 | Fabrication |  | ● | ●
|  |  | 215E1220200 | [5 empty] | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | Fabrication |  | ● | ● |  |  |  |  | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1220300 | [5 empty] | DRAIN PIPE AND SUPPORT | Fabrication |  | ● | ● |  |  |  |  | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1220400 | [5 empty] | TAPPING STRIP | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1220500 | [5 empty] | TAPPING FOR PASSENGER SEAT ON FLOOR | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | B | B | 2024-01-24 |  | 2024-06-27 | [10 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1220600 | [5 empty] | TAPPING FOR INTERIOR CABINET | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1220700 | [5 empty] | TAPPING STRIP FOR EVACUATION LINE | Fabrication |  | ● | ●
|  |  | 215E1240100 | [5 empty] | ARR SUPORTING FRAME FOR FLOOR | Fabrication
|  |  | 215E1240200 | [5 empty] | BRACKET SUPPORT FLOOR ON PASSENGER ROOM | Fabrication |  |  |  | ● | ● | ● |  | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1240300 | [5 empty] | DRAIN PIPE AND SUPPORT | Fabrication |  |  |  | ● | ● | ● |  | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1240400 | [5 empty] | TAPPING STRIP | Fabrication |  |  |  | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1240500 | [5 empty] | TAPPING FOR PASSENGER SEAT ON FLOOR | Fabrication |  |  |  | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1240600 | [5 empty] | TAPPING FOR INTERIOR CABINET | Fabrication |  |  |  | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-07-03 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 215E1240700 | [5 empty] | TAPPING STRIP FOR EVACUATION LINE | Fabrication
|  |  | 217E1210200 | [5 empty] | SUPPORT FOR WELDED DUCT ON CABIN | Fabrication | ● | [6 empty] | A3
|  |  | 218E1200200 | [5 empty] | BRACKET FOR GROUNDING INTER CAR | Fabrication |  | ● | ● | ● | ● | ● |  | A3
|  |  | PI218E12003 | [5 empty] | BRACKET FOR LEVELING VALVE | Fabrication | ● | ● | ● | ● | ● | ● | ● | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | 218E1200400 | [5 empty] | BRACKET FOR COUPLER SUPPORT | Fabrication |  | ● | ● | ● | ● | ● |  | A3
|  |  | 218E1200500 | [5 empty] | BRACKET FOR LADDER | Fabrication |  | ● | ● | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1210300 | [5 empty] | BRACKET OF RECTIFIER BOX | Fabrication | ● | [6 empty] | A3
|  |  | 218E1210400 | [5 empty] | BRACKET FOR COUPLER SUPPORT | Fabrication | ● | [6 empty] | A3
|  |  | 218E1210600 | [5 empty] | BRACKET FOR PNEUMATIC PIPING | Fabrication | ● | [6 empty] | A3
|  |  | 218E1210700 | [5 empty] | BRACKET OF BATTERY BOX | Fabrication | ● | [6 empty] | A3
|  |  | PI218E12108 | [5 empty] | BRACKET OF RECTIFIER BOX | Fabrication | ● | [6 empty] | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | 218E1210900 | [5 empty] | BRACKET OF ELECTRIC CONTROL PANEL | Fabrication | ● | [6 empty] | A3
|  |  | 218E1211000 | [5 empty] | BRACKET FOR LADDER | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-01-05 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1211100 | [5 empty] | BRACKET OF AUX SWITCH | Fabrication | ● | [6 empty] | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1211200 | [5 empty] | BRACKET OF TERMINAL BOX | Fabrication | ● | [6 empty] | A3
|  |  | 218E1211300 | [5 empty] | BRACKET OF LGS (GROUND SWITCH) | Fabrication | ●
|  |  | PI218E12114 | [5 empty] | BRACKET OF AIR RESERVOIR | Fabrication | ● | [6 empty] | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI218E12115 | [5 empty] | BRACKET OF TRANSFORMER FILTER BOX | Fabrication | ● | [6 empty] | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1211600 | [5 empty] | BRACKET OF COWCATCHER | Fabrication | ●
|  |  | 218E1211700 | [5 empty] | BRACKET OF JUNCTION COUPLER ELECTRIC | Fabrication | ●
|  |  | 218E1211800 | [5 empty] | BRACKET OF PNEUMATIC HORN MODULE | Fabrication | ●
|  |  | 218E1211900 | [5 empty] | BRACKET OF APS BOX | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI218E12120 | [5 empty] | BRACKET OF IVHB | Fabrication | ● | [6 empty] | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | 218E1212100 | [5 empty] | BRACKET OF BATTERY PANEL | Fabrication | ●
|  |  | 218E1212200 | [5 empty] | BRAKE OF CONTROL MODULE | Fabrication | ●
|  |  | PI218E12123 | [5 empty] | BRACKET OF HGS (GROUND SWITCH) | Fabrication | ● | [6 empty] | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | 218E1212400 | [5 empty] | BRACKET OF GROUNDING PLATE | Fabrication | ●
|  |  | 218E1212500 | [5 empty] | CABLE DIRECTOR ON UNDERFRAME | Fabrication | ●
|  |  | 218E1220100 | [5 empty] | ARRANGEMENT BRACKET & FRAME ON U/F M1 | Fabrication |  | ●
|  |  | 218E1220600 | [5 empty] | BRACKET VVVF | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-07-04 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1220700 | [5 empty] | BRACKET ELECTRIC CONTROL PANEL | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-07-04 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1220800 | [5 empty] | BRACKET BRAKE RESISTOR | Fabrication |  | ● | ●
|  |  | 218E1220900 | [5 empty] | BRACKET CHOPPER BOX | Fabrication |  | ● | ●
|  |  | 218E1221000 | [5 empty] | BRACKET CHOPPER REACTOR | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1221100 | [5 empty] | BRACKET OF AIR RESEVOIR (100L) | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1221200 | [5 empty] | BRACKET OF BRAKE CONTROL MODULE | Fabrication |  | ● | ● |  |  |  |  | A3 | 3 | 0 | 0 | 2024-07-02 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1221300 | [5 empty] | BRACKET FOR CABLE DUCT | Fabrication |  | ● | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1221400 | [5 empty] | BRACKET FOR PNEUMATIC PIPING | Fabrication |  | ● | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1221500 | [5 empty] | BRACKET MAIN SWITCH | Fabrication |  | ● | [5 empty] | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1221600 | [5 empty] | BRACKET FILTER REACTOR | Fabrication |  | ● | [22 empty] | OPEN |  | OPEN
|  |  | 218E1221700 | [5 empty] | BRACKET HSCB BOX | Fabrication |  | ● | [5 empty] | A3 | 3 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1221800 | [5 empty] | BRACKET JUNCTION COUPLER ELECTRIC | Fabrication |  | ● | [22 empty] | OPEN |  | OPEN
|  |  | PI218E12219 | [5 empty] | BRACKET OF PANTOGRAPH CONTROL MODULE | Fabrication |  | ● | [22 empty] | OPEN |  | OPEN
|  |  | PI218E12220 | [5 empty] | BRACKET OF PANTOGRAPH DISCONNECTOR SWITCH | Fabrication |  | ● | [5 empty] | A3 | 3 | 0 | 0 | 2024-07-02 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 218E1230100 | [5 empty] | ARRANGEMENT BRACKET & FRAME ON U/F M2 | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1231500 | [5 empty] | BRACKET AIR RESEVOIR (150L) | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1231600 | [5 empty] | BRACKET OF FILTER REACTOR | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1231700 | [5 empty] | BRACKET OF COMPRESSOR | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1231800 | [5 empty] | BRACKET OF COMPRESSOR CONTROL PANEL | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1231900 | [5 empty] | BRACKET OF EXPANSION BOX | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1232000 | [5 empty] | BRACKET OF LGS (GROUND SWITCH) | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1232100 | [5 empty] | BRACKET OF TERMINAL BOX | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1232200 | [5 empty] | BRACKET OF GROUNDING PLATE | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1232300 | [5 empty] | CABLE DIRECTOR ON UNDERFRAME | Fabrication |  |  | ● | [21 empty] | OPEN |  | OPEN
|  |  | 218E1240100 | [5 empty] | ARRANGEMENT BRACKET & FRAME ON U/F T1 | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1240600 | [5 empty] | BRACKET OF ELECTRIC CONTROL PANEL | Fabrication |  |  |  | ● | ● | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1240700 | [5 empty] | BRACKET OF BRAKE CONTROL MODUL | Fabrication |  |  |  | ● | ● | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1240800 | [5 empty] | BRACKET OF AIR RESEVOIR (100L) | Fabrication |  |  |  | ● | ● | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1240900 | [5 empty] | BRACKET OF LGS (GROUND SWITCH) | Fabrication |  |  |  | ● | ● | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1241000 | [5 empty] | BRACKET OF CABLE DUCTING | Fabrication |  |  |  | ● | ● | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1241100 | [5 empty] | BRACKET OF PNEUMATIC PIPING | Fabrication |  |  |  | ● | ● | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1241200 | [5 empty] | BRACKET OF TRANSFORMER FILTER BOX | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1241300 | [5 empty] | BRACKET OF APS BOX | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1241400 | [5 empty] | BRACKET OF RECTIFIER BOX | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1241500 | [5 empty] | BRACKET OF AUXILIARY SWITCH | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1241600 | [5 empty] | BRACKET OF IVHB | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1241700 | [5 empty] | BRACKET OF BATTERY BOX | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1241800 | [5 empty] | BRACKET OF BATTERY PANEL | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1241900 | [5 empty] | BRACKET OF HGS (GROUND SWITCH) | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1242000 | [5 empty] | BRACKET OF EXPANSION BOX | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1242100 | [5 empty] | BRACKET OF TERMINAL BOX | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1242200 | [5 empty] | BRACKET OF GROUNDING PLATE | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1242300 | [5 empty] | CABLE DIRECTOR ON UNDERFRAME | Fabrication |  |  |  | ● | [20 empty] | OPEN |  | OPEN
|  |  | 218E1250100 | [5 empty] | ARRANGEMENT BRACKET & FRAME ON U/F T2 | Fabrication |  |  |  |  | ● | [19 empty] | OPEN |  | OPEN
|  |  | 218E1251200 | [5 empty] | BRACKET OF COMPRESSOR CONTROL PANEL | Fabrication |  |  |  |  | ● | [19 empty] | OPEN |  | OPEN
|  |  | 218E1251300 | [5 empty] | BRACKET OF AIR RESEVOIR (150L) | Fabrication |  |  |  |  | ● | [19 empty] | OPEN |  | OPEN
|  |  | 218E1251400 | [5 empty] | BRACKET OF COMPRESSOR | Fabrication |  |  |  |  | ● | [19 empty] | OPEN |  | OPEN
|  |  | 218E1251500 | [5 empty] | BRACKET OF TERMINAL BOX | Fabrication |  |  |  |  | ● | [19 empty] | OPEN |  | OPEN
|  |  | 218E1251600 | [5 empty] | BRACKET OF GROUNDING PLATE | Fabrication |  |  |  |  | ● | [19 empty] | OPEN |  | OPEN
|  |  | 218E1251700 | [5 empty] | CABLE DIRECTOR ON UNDERFRAME | Fabrication |  |  |  |  | ● | [19 empty] | OPEN |  | OPEN
|  |  | 218E1260100 | [5 empty] | ARRANGEMENT BRACKET & FRAME ON U/F T3 | Fabrication | [5 empty] | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1261200 | [5 empty] | BRACKET OF GROUNDING PLATE | Fabrication | [5 empty] | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1261300 | [5 empty] | CABLE DIRECTOR ON UNDERFRAME | Fabrication | [5 empty] | ● | [18 empty] | OPEN |  | OPEN
|  |  | 218E1270100 | [5 empty] | ARRANGEMENT BRACKET & FRAME ON U/F TC2 | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1270500 | [5 empty] | BRACKET FOR CABLE DUCT | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1270600 | [5 empty] | BRACKET FOR PNEUMATIC PIPING | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1270700 | [5 empty] | BRACKET OF BATTERY BOX | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1270800 | [5 empty] | BRACKET OF RECTIFIER BOX | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1270900 | [5 empty] | BRACKET OF ELECTRIC CONTROL PANEL | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271000 | [5 empty] | BRACKET FOR LADDER | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271100 | [5 empty] | BRACKET OF AUX SWITCH | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271200 | [5 empty] | BRACKET OF TERMINAL BOX | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271300 | [5 empty] | BRACKET OF LGS (GROUND SWITCH) | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271400 | [5 empty] | BRACKET OF AIR RESERVOIR | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271500 | [5 empty] | BRACKET OF TRANSFORMER FILTER BOX | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271600 | [5 empty] | BRACKET OF COWCATCHER | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271700 | [5 empty] | BRACKET OF JUNCTION COUPLER ELECTRIC | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271800 | [5 empty] | BRACKET OF PNEUMATIC HORN MODULE | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1271900 | [5 empty] | BRACKET OF APS BOX | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1272000 | [5 empty] | BRACKET OF IVHB | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1272100 | [5 empty] | BRACKET OF BATTERY PANEL | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1272200 | [5 empty] | BRAKE OF CONTROL MODULE | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1272300 | [5 empty] | BRACKET OF HGS (GROUND SWITCH) | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1272400 | [5 empty] | BRACKET OF GROUNDING PLATE | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | 218E1272500 | [5 empty] | CABLE DIRECTOR ON UNDERFRAME | Fabrication | [6 empty] | ● | [17 empty] | OPEN |  | OPEN
|  |  | PI228E12004 | [5 empty] | BRACKET FOR DOOR ENGINE ENTRANCE | Fabrication | ● | ● | ● | ● | ● | ● | ● | A3 | 4 | A | A | 2024-02-19 | 2024-07-02 | [11 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI228E12006 | [5 empty] | BRACKET EMERGENCY DOOR RELEASE | Fabrication |  | ● | ● | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI228E12007 | [5 empty] | BRACKET FOR RUNNING TEXT | Fabrication | ● | ● | ● | ● | ● | ● | ● | A3 | 4 | 0 | 0 | 2024-02-19 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 228E1210200 | [5 empty] | ARRANGEMENT ADAPTER ON SIDEWALL | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 228E1210300 | [5 empty] | BRACKET FOR CURTAIN & INTERIOR PANEL | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-02-19 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 228E1210400 | [5 empty] | BRACKET FOR DOOR ENGINE ENTRANCE | Fabrication | ● | [5 empty] | ● | A3 | 4 | A | A | 2024-02-12 | 2024-07-02 | [11 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI228E12105 | [5 empty] | BRACKET FOR LUGGAGE RACK | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-02-19 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI228E12106 | [5 empty] | BRACKET EMERGENCY DOOR RELEASE | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-06-24 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI238E12110 | [5 empty] | BRACKET FOR GUTTER PIPE AT CABIN | Fabrication | ● | [5 empty] | ● | A3 | 3 | A | A | 2024-02-20 | 2024-06-27 | [11 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 228E1220200 | [5 empty] | ARRANGEMENT ADAPTER ON SIDEWALL | Fabrication |  | ● | ● |  |  |  |  | A3 | 4 | 0 | 0 | 2024-01-26 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI238E12006 | [5 empty] | TAPPING FOR FALLING PROTECTOR | Fabrication |  |  | ● | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-02-20 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 238E1210200 | [5 empty] | BRACKET ENDWALL PANEL | Fabrication | ● | [6 empty] | A3 | [16 empty] | OPEN |  | OPEN |  |  | PRORITY 1
|  |  | 238E1210300 | [5 empty] | DIRECTOR CABLE ON ON ENDWALL | Fabrication | ● | [6 empty] | A3 | [16 empty] | OPEN |  | OPEN
|  |  | PI238E12106 | [5 empty] | TAPPING FOR FALLING PROTECTOR TC1 & TC2 | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-02-20 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
FIN
|  |  | PI245E12102 | [5 empty] | CEILING FRAME ON CAB | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI245E12103 | [5 empty] | CABLE DIRECTOR ON CEILING FRAME CAB | Fabrication | ● | [5 empty] | ● | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
A3
|  |  | PI248E12103 | [5 empty] | INTERIOR LINNING FRAME ON CAB | Fabrication | ● | [5 empty] | ● | A3 | 0 | 0 | 3 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI248E12104 | [5 empty] | DIRECTOR CABLE ON CAB | Fabrication | ● | [5 empty] | ● | A3 | 0 | 0 | 3 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI250A1700102 | [5 empty] | METODE TES KEBOCORAN | Fabrication | ● | ● | ● | ● | ● | ● | ● | A3 | 2 |  | 0 | 2023-09-09 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI250K7200105 | [5 empty] | STRACING AREA SHEATING ROOF AC | Fabrication | ● | ● | ● | ● | ● | ● | ● | A3 | 3 |  | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | 251E12106 | [5 empty] | RAIN GUTTER | Fabrication | ● | [5 empty] | ● | A3 | 3 | A | A |  | 2024-01-24 | [11 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI255E12004 | [5 empty] | BRACKET FOR ROLL FILTER | Fabrication | ● | ● | ● | ● | ● | ● | ● | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI255E12102 | [5 empty] | CEILING FRAME PASSANGER ROOM | Fabrication | ● | [5 empty] | ● | A3 | 5 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12004 | [5 empty] | BRACKET FOR EXTERIOR SPEAKER | Fabrication | ● | ● | ● | ● | ● | ● | ● | A3 | 3 | A | A |  | 2024-06-27 | [11 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12006 | [5 empty] | BRACKET FOR ELECTRICAL CABINET ON ENDWALL | Fabrication |  | ● | ● | ● | ● | ● |  | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | 258E1210200 | [5 empty] | BRACKET OF DOOR POCKET, DOOR ENGINE | Fabrication | ● | [6 empty] | A3 | [16 empty] | OPEN |  | OPEN
|  |  | PI258E12103 | [5 empty] | CABLE DIRECTOR ON ROOF | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | ARU | YUK | EKN
|  |  | PI258E12106 | [5 empty] | BRACKET ELECTRICAL CABINET ON CABIN & ENDWALL | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12107 | [5 empty] | BRACKET FOR DOOR CONTROL UNIT | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
PI258E12108
|  |  | PI258E12109 | [5 empty] | CABLE DIRECTOR ON CABIN & REAR ROOF FRAME | Fabrication | ● | [5 empty] | ● | A3 | 4 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12202 | [5 empty] | CEILING FRAME PASSENGER ROOM | Fabrication |  | ● | [5 empty] | A3 | 4 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12203 | [5 empty] | CABLE DIRECTOR ON ROOF | Fabrication |  | ● | [5 empty] | A3 | 4 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12207 | [5 empty] | BRACKET FOR DOOR CONTROL UNIT | Fabrication |  | ● | [5 empty] | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12208 | [5 empty] | BRACKET OF SURGE ARRESTER | Fabrication |  | ● | [5 empty] | A3 | 3 | 0 | 0 | 2024-02-20 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
|  |  | PI258E12213 | [5 empty] | CABLE DIRECTOR ON REAR ROOF FRAME | Fabrication |  | ● | [5 empty] | A3 | 3 | 0 | 0 | 2024-06-27 | [12 empty] | CLOSED |  | CLOSED |  |  |  | DIM | YUK | EKN
A3
[9 empty] | Prepared By, | [8 empty] | Checked By, | [10 empty] | Approved By,
[9 empty] | Andri DC | [8 empty] | Yudha K | [10 empty] | Eko N
Finishing
|  |  | FP 000E1210102 | [5 empty] | FLOW PROSES TC1 & TC2 | Finishing | ● | [5 empty] | ● | A1 | 1 | - | 0 | 2023-11-28 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | FP 000E1220102 | [5 empty] | FLOW PROSES M1 & M2 | Finishing |  | ● | ● |  |  |  |  | A1 | 1 | - | 0 | 2023-11-28 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | FP 000E1240102 | [5 empty] | FLOW PROSES T1, T2, T3 & T1' | Finishing |  |  |  | ● | ● | ● |  | A1 | 1 | - | 0 | 2023-11-28 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | FP 000E1250102 | [5 empty] | FLOW PROSES TC1 PRESERIES | Finishing | ● | [6 empty] | A1 | 1 | - | 0 | 2023-04-30 | [13 empty] | CLOSED |  | N/A |  |  | EPP | APK | EKN
|  |  | FP 000E1260102 | [5 empty] | FLOW PROSES M1 PRESERIES | Finishing |  | ● | [5 empty] | A1 | 1 | - | 0 | 2023-04-30 | [13 empty] | CLOSED |  | N/A |  |  | EPP | APK | EKN
|  |  | TD E1210301 | [5 empty] | TACK DETAIL 1 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1210302 | [5 empty] | TACK DETAIL 2 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1210303 | [5 empty] | TACK DETAIL 3 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1210304 | [5 empty] | TACK DETAIL 4 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1210305 | [5 empty] | TACK DETAIL 5 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1210306 | [5 empty] | TACK DETAIL 6 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1210307 | [5 empty] | TACK DETAIL 7 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1210308 | [5 empty] | TACK DETAIL 8 | Finishing | ● | [5 empty] | ● | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220301 | [5 empty] | TACK DETAIL 1 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220302 | [5 empty] | TACK DETAIL 2 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220303 | [5 empty] | TACK DETAIL 3 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220304 | [5 empty] | TACK DETAIL 4 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220305 | [5 empty] | TACK DETAIL 5 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220306 | [5 empty] | TACK DETAIL 6 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220307 | [5 empty] | TACK DETAIL 7 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1220308 | [5 empty] | TACK DETAIL 8 | Finishing |  | ● | ● |  |  |  |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240301 | [5 empty] | TACK DETAIL 1 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240302 | [5 empty] | TACK DETAIL 2 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240303 | [5 empty] | TACK DETAIL 3 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240304 | [5 empty] | TACK DETAIL 4 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240305 | [5 empty] | TACK DETAIL 5 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240306 | [5 empty] | TACK DETAIL 6 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240307 | [5 empty] | TACK DETAIL 7 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
|  |  | TD E1240308 | [5 empty] | TACK DETAIL 8 | Finishing |  |  |  | ● | ● | ● |  | A4 |  |  |  | 2023-11-06 | [13 empty] | CLOSED | CLOSED | N/A |  |  | ARG | APK | EKN
TINJAUAN PROSES
[9 empty] | Bogie | Finishing | ● | ● | ● | ● | ● | ● | ● |  |  |  |  | 2024-06-07 | [14 empty] | CLOSED | N/A
[9 empty] | Interior | Finishing | ● | ● | ● | ● | ● | ● | ● |  |  |  |  | 2024-06-06 | [14 empty] | CLOSED | N/A
[9 empty] | Mekanik | Finishing | ● | ● | ● | ● | ● | ● | ● |  |  |  |  | 2024-06-06 | [14 empty] | CLOSED | N/A
[9 empty] | Special Process | Finishing | ● | ● | ● | ● | ● | ● | ● |  |  |  |  | 2024-06-07 | [14 empty] | CLOSED | N/A
Mechanical System
|  | 301E12101 - PI | [6 empty] | ARRANGMENT EQUIPMENT OF BENEATH UNDERFRAME (TC1) | Mechanical System | • | [6 empty] | A4 | 1 |  |  | 2024-04-18 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 301E12201- PI | [6 empty] | ARRANGMENT EQUIPMENT OF BENEATH UNDERFRAME (M1) | Mechanical System |  | • | [5 empty] | A4 | 1 |  |  | 2024-04-18 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 301E12301- PI | [6 empty] | ARRANGMENT EQUIPMENT OF BENEATH UNDERFRAME (M2) | Mechanical System |  |  | • |  |  |  |  | A4 | 1 |  |  | 2024-04-18 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 301E12401- PI | [6 empty] | ARRANGMENT EQUIPMENT OF BENEATH UNDERFRAME (T1) | Mechanical System |  |  |  | • |  |  |  | A4 | 1 |  |  | 2024-04-18 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 301E12501- PI | [6 empty] | ARRANGMENT EQUIPMENT OF BENEATH UNDERFRAME (T2) | Mechanical System |  |  |  |  | • |  |  | A4 | 1 |  |  | 2024-04-18 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 301E12601- PI | [6 empty] | ARRANGMENT EQUIPMENT OF BENEATH UNDERFRAME (T3) | Mechanical System | [5 empty] | • |  | A4 | 1 |  |  | 2024-04-18 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 301E12701- PI | [6 empty] | ARRANGMENT EQUIPMENT OF BENEATH UNDERFRAME (TC2) | Mechanical System | [6 empty] | • | A4 | 1 |  |  | 2024-04-18 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  | 30.1-E12001 - PI | [5 empty] | FITTING OF DRAFT GEAR STOPPER | Mechanical System | • | • | • | • | • | • | • | A3 | 1 |  |  | 2024-03-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED | Pindah CBD |  | MRN | APK | EKN
|  |  |  | 31.0-E12052 |  |  |  |  | DRAFT GEAR STOPPER | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12002 - PI | [5 empty] | FITTING OF AUTOMATIC TIGHT LOCK COUPLER (MANUAL UNCOUPLING) | Mechanical System | • | • | • | • | • | • | • | A3 |  | 0 | 0 | 2024-03-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 31.0-E12007 |  |  |  |  | AUTOMATIC TIGHT LOCK COUPLER (MANUAL UNCOUPLING) | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12009 |  |  |  |  | FRAME JOINT | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12010 |  |  |  |  | LATERAL PIN | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12011 |  |  |  |  | VERTICAL PIN | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12051 |  |  |  |  | DRAFT GEAR | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12003 |  |  |  |  | BODY SUPPORT DEVICE (NO STOPPER) | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12022 |  |  |  |  | UPPER DRAFT GEAR SUPPORT | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12053 |  |  |  |  | LOWER DRAFT GEAR SUPPORT | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12102 - PI | [5 empty] | FITTING OF AUTOMATIC TIGHT LOCK COUPLER (AUTOMATIC UNCOUPLING) | Mechanical System | • | [5 empty] | • | A3 | 1 |  |  | 2024-03-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 31.0-E12006 |  |  |  |  | AUTOMATIC TIGHT LOCK COUPLER (AUTOMATIC UNCOUPLING) | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12005 |  |  |  |  | BODY SUPPORT DEVICE (STOPPER TYPE) | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12022 |  |  |  |  | UPPER DRAFT GEAR SUPPORT | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12053 |  |  |  |  | LOWER DRAFT GEAR SUPPORT | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12202 - PI | [5 empty] | FITTING OF SEMI-PERMANENT COUPLER | Mechanical System |  | • | • |  |  |  |  | A3 | 2 | 0 | 0 | 2024-03-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 31.0-E12008 |  |  |  |  | SEMI-PERMANENT COUPLER | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12103 - PI | [5 empty] | FITTING OF BRAKE CONTROL UNIT | Mechanical System | • |  |  | • | • | • |  | A3 |  | 0 | 0 | 2024-01-13 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 31.0-E12046 |  |  |  |  | GB1 TYPE BRAKE CONTROL UNIT | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12203 - PI | [5 empty] | FITTING OF BRAKE CONTROL UNIT | Mechanical System |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2024-01-13 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 30.1-E12104 - PI | [5 empty] | FITTING OF AIR RESERVOIR | Mechanical System | • |  |  | • | • | • |  | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 31.0-E12044 |  |  |  |  | AIR RESERVOIR | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12204 - PI | [5 empty] | FITTING OF AIR RESERVOIR | Mechanical System |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 30.1-E12005 - PI | [5 empty] | FITTING OF LADDER | Mechanical System | • | • | • | • | • | • | • | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  |  | 31.1-E12019 |  |  |  |  | LADDER | Mechanical System | [6 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12105 - PI | [5 empty] | FITTING OF COWCATCHER | Mechanical System | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-04-25 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  |  | 31.1-E12101 |  |  |  |  | COWCATCHER ASSEMBLY | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12006 - PI | [5 empty] | FITTING OF VVVF INVERTER | Mechanical System |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  |  | 33.0-E12010 |  |  |  |  | VVVF INVERTER | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12106 - PI | [5 empty] | FITTING OF AUXILIARY POWER SYSTEM (TC1,T1) | Mechanical System | • |  |  | • |  |  |  | A3 |  | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  |  | 33.0-E12002 |  |  |  |  | AUXILIARY POWER SYSTEM | Mechanical System | • |  |  | • |  |  | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12706 - PI | [5 empty] | FITTING OF AUXILIARY POWER SYSTEM | Mechanical System | [6 empty] | •
|  |  | 30.1-E12007 - PI | [5 empty] | FITTING OF FILTER REACTOR (M2) | Mechanical System |  |  | •
|  |  | 30.1-E12107 - PI | [5 empty] | FITTING OF TRANSFORMER FILTER BOX (TC1,T1) | Mechanical System | • |  |  | • |  |  |  | A3 |  | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  |  | 33.0-E12003 |  |  |  |  | TRANSFORMER FILTER BOX | Mechanical System | • |  |  | • | [20 empty] | CLOSED |  | CLOSED
|  |  | 30.1-E12707 - PI | [5 empty] | FITTING OF TRANSFORMER FILTER BOX | Mechanical System | [6 empty] | •
|  |  | 30.1-E12207 - PI | [5 empty] | FITTING OF FILTER REACTOR (M1) | Mechanical System |  | •
|  |  |  | 33.0-E12011 |  |  |  |  | FILTER REACTOR | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12108 - PI | [5 empty] | FITTING OF BATTERY BOX | Mechanical System | • | [6 empty] | A3 |  | 0 | 0 | 2023-12-26 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 31.1-E12002 |  |  |  |  | BATTERY BOX | Mechanical System | • |  |  | • |  |  | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12708 - PI | [5 empty] | FITTING OF BATTERY BOX | Mechanical System | [6 empty] | •
|  |  | 30.1-E12208 - PI | [5 empty] | FITTING OF MAIN SWITCH BOX | Mechanical System |  | • | [5 empty] | A3 | 2 | 0 | 0 | 2024-04-18 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  |  | 33.0-E12208 |  |  |  |  | MAIN SWITCH BOX | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12408 - PI | [5 empty] | FITTING OF BATTERY BOX | Mechanical System |  |  |  | •
|  |  | 30.1-E12109 - PI | [5 empty] | FITTING OF BATTERY CONTROL PANEL (TC1,T1) | Mechanical System | • |  |  | • |  |  |  | A3 |  | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED | need cancel |  | APR | APK | EKN
|  |  | 30.1-E12409 - PI | [5 empty] | FITTING OF BATTERY CONTROL PANEL | Mechanical System |  |  | •
|  |  | 30.1-E12709 - PI | [5 empty] | FITTING OF BATTERY CONTROL PANEL | Mechanical System | [6 empty] | •
|  |  |  | 31.1-E12015 |  |  |  |  | BATTERY CONTROL PANEL | Mechanical System | • |  | • | • |  |  | • | [17 empty] | CANCELED
|  |  | 30.1-E12209 - PI | [5 empty] | FITTING OF HSCB BOX | Mechanical System |  | • | [5 empty] | A3 |  | 0 | 0 | 2024-01-12 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 33.0-E12209 |  |  |  |  | HSCB BOX | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12010 - PI | [5 empty] | FITTING OF BRAKE RESISTOR | Mechanical System |  | • | • |  |  |  |  | A3
|  |  |  | 33.0-E12012 |  |  |  |  | BRAKE RESISTOR | Mechanical System |  | • | •
|  |  | 30.1-E12110 - PI | [5 empty] | FITTING OF AUXILIARY SWITCH BOX | Mechanical System | • |  |  | • |  |  |  | A3 |  | 0 | 0 | 2023-12-29 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 33.0-E12004 |  |  |  |  | AUXILIARY SWITCH BOX | Mechanical System | • |  |  | • |  |  | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12710 - PI | [5 empty] | FITTING OF AUXILIARY SWITCH BOX | Mechanical System | [6 empty] | •
|  |  | 30.1-E12210 - PI | [5 empty] | FITTING OF PANTOGRAPH DISCONNECTOR SWITCH | Mechanical System |  | • | [5 empty] | A3 | 3 | 0 | 0 | 2024-03-26 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  |  | 33.0-E12210 |  |  |  |  | PANTOGRAPH DISCONNECTOR SWITCH (PDS) | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12011 - PI | [5 empty] | FITTING OF BRAKE CHOPPER REACTOR | Mechanical System |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 33.0-E12013 |  |  |  |  | BRAKE CHOPPER REACTOR | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12111 - PI | [5 empty] | FITTING OF IvHB BOX | Mechanical System | • | [6 empty] | A3 |  | 0 | 0 | 2024-01-03 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 33.0-E12005 |  |  |  |  | IvHB BOX | Mechanical System | • |  |  | • |  |  | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12411 - PI | [5 empty] | FITTING OF IvHB BOX | Mechanical System |  |  |  | •
|  |  | 30.1-E12711 - PI | [5 empty] | FITTING OF IvHB BOX | Mechanical System | [6 empty] | •
|  |  | 30.1-E12211 - PI | [5 empty] | FITTING OF BUS FUSE (M1) | Mechanical System |  | • | [5 empty] | A3 |  | 0 | 0 | 2024-02-06 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 33.0-E12211 |  |  |  |  | BUSE FUSE | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12012 - PI | [5 empty] | FITTING OF BRAKE CHOPPER BOX | Mechanical System |  | • | • |  |  |  |  | A3 | 2 | 0 | 0 | 2024-04-18 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  |  | 33.0-E12014 |  |  |  |  | BRAKE CHOPPER BOX | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12112 - PI | [5 empty] | FITTING OF RECTIFIER BOX (TC1,T1) | Mechanical System | • |  |  | • |  |  |  | A3 |  | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 33.0-E12006 |  |  |  |  | RECTIFIER BOX | Mechanical System | • |  |  | • |  | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12212 - PI | [5 empty] | FITTING OF TRACTION MOTOR JUNCTION BOX (M1, M2) | Mechanical System |  | • | • |  |  |  |  | A3 | 2 | A3 | A | 2024-02-12 | 2024-05-24 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 31.1-E12202 |  |  |  |  | TRACTION MOTOR JUNCTION BOX | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12712 - PI | [5 empty] | FITTING OF RECTIFIER BOX | Mechanical System | [6 empty] | •
|  |  | 30.1-E12113 - PI | [5 empty] | FITTING OF ELECTRONIC CONTROL PANEL BOX (TC & T) | Mechanical System | • |  |  | • |  |  | • | A3 |  | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 33.0-E12018 |  |  |  |  | ELECTRIC CONTROL PANEL BOX | Mechanical System | • |  |  | • |  |  | • | A3 | 4 | 0 | A | 2024-02-13 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 33.0-E12007 |  |  |  |  | ELECTRIC CONTROL PANEL BOX | Mechanical System |  | • | • |  | • | • |  | A3 | 4 | 0 | A | 2024-02-13 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 30.1-E12213 - PI | [5 empty] | FITTING OF ELECTRONIC CONTROL PANEL BOX (M1, M2, T2, T3) | Mechanical System |  | • | • |  | • | • |  | A3 | 4 | 0 | B | 2024-02-13 | 2024-03-25 | 2024-06-08 | [10 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  | 30.1-E12014 - PI | [5 empty] | FITTING OF TERMINAL BOX | Mechanical System |  | • | • | • | • | •
|  |  | 30.1-E12114 - PI | [5 empty] | FITTING OF TERMINAL BOX | Mechanical System | •
|  |  |  | 33.0-E12008 |  |  |  |  | TERMINAL BOX | Mechanical System | • | • | • | • | • | • | [21 empty] | N/A
|  |  | 30.1-E12015 - PI | [5 empty] | FITTING OF UNDERFRAME CABLE DUCT | Mechanical System |  | • | • |  | • | •
|  |  |  | 31.1-E12025 |  |  |  |  | UNDERFRAME CABLE DUCT | Mechanical System |  | • | • |  | • | • | [21 empty] | N/A
|  |  |  | 31.1-E12130 |  |  |  |  | WIRING BOX 1 | Mechanical System |  | • | • |  | • | • | [21 empty] | N/A
|  |  |  | 31.1-E12131 |  |  |  |  | WIRING BOX 2 | Mechanical System |  | • | • |  | • | • | [21 empty] | N/A
|  |  |  | 31.1-E12132 |  |  |  |  | WIRING BOX 3 | Mechanical System |  | • | • |  | • | • | [21 empty] | N/A
|  |  | 30.1-E12115 - PI | [5 empty] | FITTING OF UNDERFRAME CABLE DUCT | Mechanical System | • | [6 empty] | A3 |  | 0 | 0 | 2024-04-18 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 31.1-E12125 |  |  |  |  | UNDERFRAME CABLE DUCT | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 31.1-E12027 |  |  |  | CABLE DUCT 1 | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 31.1-E12128 |  |  |  | CABLE DUCT 2 | Mechanical System | • | [27 empty] | OPEN
|  |  |  | 31.1-E12126 |  |  |  |  | CLAMP & COVER OF UNDERFRAME CABLE DUCT (TC1) | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12030 |  |  |  |  | WIRING BOX 1 | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12031 |  |  |  |  | WIRING BOX 2 | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12128 |  |  |  |  | WIRING BOX 2 (TC) | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12129 |  |  |  |  | WIRING BOX 3 (TC) | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12034 |  |  |  |  | WIRING BOX SUPPORT | Mechanical System | •
|  |  |  | 31.1-E12134 |  |  |  |  | WIRING BOX SUPPORT (TC) | Mechanical System | •
|  |  |  | 31.1-E12035 |  |  |  |  | SUPPORT CLAMP - 01 | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12215 - PI | [5 empty] | FITTING OF UNDERFRAME CABLE DUCT | Mechanical System |  | • | [5 empty] | A3 | 1 | 0 | 0 | 2024-05-28 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | HAS | APK | EKN
|  |  | 30.1-E12315 - PI | [5 empty] | FITTING OF UNDERFRAME CABLE DUCT | Mechanical System |  |  | • |  |  |  |  | A3 | 1 | 0 | 0 | 2024-05-23 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 30.1-E12415 - PI | [5 empty] | FITTING OF UNDERFRAME CABLE DUCT | Mechanical System |  |  |  | • |  |  |  | A3 | 1 | 0 | 0 | 2024-06-16 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  | 30.1-E12715 - PI | [5 empty] | FITTING OF UNDERFRAME CABLE DUCT | Mechanical System | [6 empty] | • | A3 | 1 | 0 | 0 | 2024-06-16 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 30.1-E12016 - PI | [5 empty] | FITTING OF STOP BLOCK | Mechanical System | • | • | • | • | • | • | • | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 31.1-E12033 |  |  |  |  | STOP BLOCK | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12117 - PI | [5 empty] | FITTING OF HORN MODULE | Mechanical System | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-04-25 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 31.2-E12104 |  |  |  |  | PNEUMATIC HORN MODULE | Mechanical System | • | [5 empty] | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 31.3-E12103 |  |  |  | FRAMEWORK OF PNEUMATIC HORN MODULE | Mechanical System | • | [5 empty] | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 31.3-E12104 |  |  |  | MARKING OF PNEUMATIC HORN MODULE | Mechanical System | • | [5 empty] | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 30.1-E12217 - PI | [5 empty] | FITTING OF PANTOGRAPH CONTROL MODULE | Mechanical System |  | •
|  |  |  | 31.2-E12204 |  |  |  |  | PANTOGRAPH CONTROL MODULE | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12018 - PI | [5 empty] | FITTING OF CABLE TRAY | Mechanical System |  | • | • |  | • | •
|  |  |  | 31.1-E12134 |  |  |  |  | CABLE TRAY 1 | Mechanical System |  |  |  |  | • | •
|  |  |  | 31.1-E12135 |  |  |  |  | CABLE TRAY 2 | Mechanical System |  |  |  |  | • | •
|  |  |  | 31.1-E12136 |  |  |  |  | CABLE TRAY 3 | Mechanical System |  | • | • |  | • | •
|  |  |  | 31.1-E12137 |  |  |  |  | CABLE TRAY 4 | Mechanical System |  | • | • |  | • | •
|  |  |  | 31.1-E12234 |  |  |  |  | CABLE TRAY 1 | Mechanical System |  | •
|  |  |  | 31.1-E12235 |  |  |  |  | CABLE TRAY 2 | Mechanical System |  | •
|  |  |  | 31.1-E12334 |  |  |  |  | CABLE TRAY 1 | Mechanical System |  |  | •
|  |  |  | 31.1-E12335 |  |  |  |  | CABLE TRAY 2 | Mechanical System |  |  | •
|  |  |  | 31.1-E12138 |  |  |  |  | CABLE TRAY 5 | Mechanical System |  | • | • |  | • | •
|  |  | 30.1-E12118 - PI | [5 empty] | FITTING OF CABLE TRAY | Mechanical System | •
|  |  | 30.1-E12418 - PI | [5 empty] | FITTING OF CABLE TRAY | Mechanical System |  |  |  | •
|  |  | 30.1-E12718 - PI | [5 empty] | FITTING OF CABLE TRAY | Mechanical System | [6 empty] | •
|  |  | 30.1-E12019 - PI | [5 empty] | FITTING OF GROUNDING CABLE (INTER CAR) | Mechanical System | • | • | • | • | • | • | • | A3
|  |  |  | 33.0-E12009 |  |  |  |  | GROUNDING CABLE (INTER CAR) | Mechanical System | • | • | • | • | • | • | •
|  |  | 30.1-E12119 - PI | [5 empty] | FITTING OF SAFETY CHAIN | Mechanical System | • |  |  |  |  | • |  | A3 |  | A3 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 31.0-E12043 |  |  |  |  | SAFETY CHAIN | Mechanical System | • |  |  |  |  | • |  | A3 |  | A3 | 0 | [13 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 30.1-E12120 - PI | [5 empty] | FITTING OF CLAMP PNEUMATIC PIPING | Mechanical System | • | [6 empty] | A3 | 4 | A3 | 0 | 2024-06-15 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 30.1-E12020 - PI | [5 empty] | FITTING OF CLAMP PNEUMATIC PIPING | Mechanical System |  |  |  | • | • | • |  | A3 |  | A3 | 0 | 2024-07-01 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 30.1-E12220 - PI | [5 empty] | FITTING OF CLAMP PNEUMATIC PIPING | Mechanical System |  | • | [5 empty] | A3 | 4 | A3 | 0 | 2024-06-15 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 30.1-E12320 - PI | [5 empty] | FITTING OF CLAMP PNEUMATIC PIPING | Mechanical System |  |  | • |  |  |  |  | A3 | 4 | A3 | 0 | 2024-07-01 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 30.1-E12720 - PI | [5 empty] | FITTING OF CLAMP PNEUMATIC PIPING | Mechanical System
|  |  | 30.1-E12021 - PI | [5 empty] | FITTING MOTOR TRACTION MOTOR DUCTING | Mechanical System |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2024-02-13 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 31.1-E12020 |  |  |  |  | TRACTION MOTOR DUCTING (L) | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12021 |  |  |  |  | TRACTION MOTOR DUCTING (R) | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12022 |  |  |  |  | FLEXIBLE DUCTING | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.1-E12023 |  |  |  |  | FILTER BOX | Mechanical System |  | • | • | [24 empty] | N/A
|  |  |  | 31.1-E12024 |  |  |  |  | AIR FILTER | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12321- PI | [5 empty] | FITTING OF EXPANSION BOX (M2) | Mechanical System |  |  | • |  |  |  |  | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 30.1-E12421 - PI | [5 empty] | FITTING OF EXPANSION BOX (T1) | Mechanical System |  |  |  | • |  |  |  | A3 |  | 0 | 0 | 2023-12-20 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 33.0-E12015 |  |  |  |  | POWER FEEDING BOX/EXPANSION BOX | Mechanical System |  |  | • | • | [20 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12022 - PI | [5 empty] | FITTING OF AIR SUPPLY MODUL | Mechanical System |  |  | • |  | • |  |  | A3 | 3 | 0 | 0 | 2024-03-25 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  |  | 31.0-E12019 |  |  |  |  | AIR SUPPLY MODUL (COMPRESSOR) | Mechanical System |  |  | • |  | • |  |  | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 30.1-E12422 - PI | [5 empty] | FITTING OF EXPANSION BOX FOR T1' | Mechanical System |  |  |  | •
|  |  | 30.1-E12023 - PI | [5 empty] | FITTING OF MAIN AIR RESERVOIR | Mechanical System |  |  | • |  | •
|  |  |  | 31.0-E12045 |  |  |  |  | MAIN AIR RESERVOIR (150L) | Mechanical System |  |  | • |  | • | [19 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12024 - PI | [5 empty] | FITTING OF COMPRESSOR CONTROL BOX (M2, T2) | Mechanical System |  |  | • |  | • |  |  | A3 |  | 0 | 0 | 2024-02-06 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED | NEED CENCEL |  | EPP | APK | EKN
|  |  |  | 33.0-E12017 |  |  |  |  | COMPRESSOR CONTROL BOX | Mechanical System |  |  | • |  | • | [19 empty] | CANCELED |  |  | N/A
|  |  | 30.1-E12124 - PI | [5 empty] | FITTING OF AW-5 PNEUPHONIC HORN | Mechanical System | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-04-29 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 31.1-E12142 |  |  |  |  | AW-5 PNEUPHONIC HORN | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12027 - PI | [5 empty] | FITTING OF HIGH VOLTAGE GROUNDING SWITCH | Mechanical System | [6 empty] | •
|  |  | 30.1-E12127 - PI | [5 empty] | FITTING OF HIGH VOLTAGE GROUNDING SWITCH (TC1 & T1) | Mechanical System | • |  |  | • |  |  |  | A3 |  | 0 | 0 | 2024-02-06 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  |  | 33.0-E12016 |  |  |  |  | HIGH VOLTAGE GROUNDING SWITCH (HGS) | Mechanical System | • |  |  | • |  |  | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.1-E12129 - PI | [5 empty] | FITTING OF HVDC VOLTAGE SENSOR BOX | Mechanical System |  | • | [5 empty] | A4 | 1 | 0 | 0 | 2024-06-08 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 31.5-E12202 - PI | [5 empty] | PIPING OF PANTOGRAPH CONTROL MODULE | Mechanical System |  | • | [5 empty] | A3 | 3 | 0 | 0 | 2024-03-04 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | APR | APK | EKN
|  | 30.4-E12001 - PI | [6 empty] | ARRANGEMENT ROOF EQUIPMENT (M2, T1, T2, T3) | Mechanical System |  |  | • | • | • | • |  | A4 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | CLOSED | CLOSED | N/A |  |  | AZA | APK | EKN
|  | 30.4-E12101 - PI | [6 empty] | ARRANGEMENT ROOF EQUIPMENT (TC1, TC2) | Mechanical System | • | [5 empty] | • | A4 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | CLOSED | CLOSED | N/A |  |  | AZA | APK | EKN
|  | 30.4-E12201 - PI | [6 empty] | ARRANGEMENT ROOF EQUIPMENT (M1) | Mechanical System |  | • | [5 empty] | A4 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | CLOSED | CLOSED | N/A |  |  | AZA | APK | EKN
|  |  | 30.4-E12102 - PI | [5 empty] | FITTING OF RADIO LOCO ANTENNA | Mechanical System | • | [5 empty] | •
|  |  |  | 50.0-E12002 |  |  |  |  | RADIO LOCO ANTENNA | Mechanical System | • | [5 empty] | •
|  |  | 30.4-E12003 - PI | [5 empty] | FITTING OF AIR CONDITIONER | Mechanical System | • | • | • | • | • | • | • | A3 | 2 | 0 | A | 2023-12-20 | 2024-06-04 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 50.0-E12003 |  |  |  |  | AIR CONDITIONING UNIT | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.4-E12204 - PI | [5 empty] | FITTING OF PANTOGRAPH | Mechanical System |  | • | • |  |  |  |  | A3 | 2 | A3 | A | 2023-12-20 | 2024-06-09 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | DHE | APK | EKN
|  |  |  | 50.0-E12204 |  |  |  |  | PANTOGRAPH | Mechanical System |  | • | • | [21 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.4-E12205 - PI | [5 empty] | FITTING OF SURGE ARRESTER | Mechanical System |  | •
|  |  |  | 50.0-E12205 |  |  |  |  | SURGE ARRESTER | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  | 30.4-E12206 - PI | [5 empty] | MANUAL HOOK RELEASER | Mechanical System |  | • | [5 empty] | A3 | 3 | 0 | 0 | 2023-12-20 | 2024-05-21 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 50.0-E12206 |  |  |  |  | WIRE ROPE SLINGS 1 | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 50.0-E12207 |  |  |  |  | WIRE ROPE SLINGS 2 | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 50.0-E12208 |  |  |  |  | WIRE ROPE SLINGS 3 | Mechanical System |  | • | [22 empty] | CLOSED |  | CLOSED | N/A
|  | 30.5-E12002 - PI | [6 empty] | ARRANGEMENT OF ENDWALL EQUIPMENT (TC1, M2, T1, T2, T3) | Mechanical System | • |  | • | • | • | • |  | A3 |  | 0 | 0 | 2024-05-21 | [12 empty] | CLOSED |  | CLOSED | N/A |  |  | AZA | APK | EKN
|  | 30.5-E12002 - PI | [6 empty] | ARRANGEMENT OF ENDWALL EQUIPMENT (M1) | Mechanical System |  | • | [5 empty] | A3 |  | 0 | 0 | 2024-05-21 | [12 empty] | CLOSED |  | CLOSED | N/A |  |  | AZA | APK | EKN
|  |  | 35.2-E12001 - PI | [5 empty] | FITTING OF CORRUGATED BELLOW | Mechanical System | • | • | • | • | • | • | •
|  |  |  | 46.0-E12001 |  |  |  |  | CORRUGATED BELLOW | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 35.2-E12201 - PI | [5 empty] | FITTING OF ENDWALL LADDER | Mechanical System |  | • | [5 empty] | A3 |  | 0 | 0 | 2024-06-07 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 46.1-E12201 |  |  |  |  | LADDER 01 | Mechanical System |  | • | [5 empty] | A3 |  | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 46.1-E12202 |  |  |  |  | LADDER 02 | Mechanical System |  | • | [5 empty] | A3 |  | 0 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  | 35.2-E12002 - PI | [5 empty] | FITTING OF APPRON | Mechanical System | • | • | • | • | • | • | •
|  |  |  | 46.1-E12002 |  |  |  |  | APPRON | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 35.2-E12003 - PI | [5 empty] | FITTING OF FALLING PROTECTOR | Mechanical System | • | • | • | • | • | • | • | A3 |  | A3 | A | 2024-01-24 | 2024-07-14 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 46.1-E12003 |  |  |  |  | FALLING PROTECTOR | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 35.2-E12004 - PI | [5 empty] | RAIN GUTTER PIPING | Mechanical System |  | • | • | • | • | • |  | A3 |  | 0 | 0 | 2024-05-21 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  |  | 46.1-E12004 |  |  |  |  | PERFORATED BAND CLAMP | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 46.1-E12005 |  |  |  |  | RUBBER LINED CLAMP | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 46.1-E12006 |  |  |  |  | CLAMP FOR RAIN GUTTER PIPING | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 35.2-E12104 - PI | [5 empty] | RAIN GUTTER PIPING (TC) | Mechanical System | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-05-21 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 35.1-E12001 - PI | [5 empty] | FITTING OF AIR GRILL TRACTION MOTOR | Mechanical System | • | • | • | • | • | • | • | A3 |  | 0 | 0 | 2024-07-14 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 30.6-E12001 - PI | [6 empty] | ARRANGEMENT EQUIPMENT ON CEILING | Mechanical System
|  |  | 30.6-E12102 - PI | [5 empty] | FITTING OF AC DUCTING | Mechanical System | •
|  |  |  | 50.2-E12101 |  |  |  |  | AC DUCTING | Mechanical System | • | [26 empty] | N/A
|  |  |  | 50.9-E12001 |  |  |  |  | SUPPORT OF AC DUCTING | Mechanical System | • | • | • | [24 empty] | N/A
|  |  | 30.6-E12002 - PI | [5 empty] | FITTING OF AC DUCTING | Mechanical System |  | • | •
|  |  |  | 50.2-E12001 |  |  |  |  | AC DUCTING | Mechanical System |  | • | • | [24 empty] | N/A
|  |  | 30.6-E12003 - PI | [5 empty] | FITTING OF RETURN AIR DUCT | Mechanical System |  | • | • | • | • | • | • | A3 | 0 | A3 | 0 | 2024-06-06 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 50.2-E12002 |  |  |  |  | RETURN AIR DUCT | Mechanical System | • | • | • | • | • | • | • | [20 empty] | N/A
|  |  | 30.6-E12103 - PI | [5 empty] | FITTING OF RETURN AIR DUCT | Mechanical System | • | [24 empty] | N/A
| 56.0-E12101 - PI | [7 empty] | PIPING ARRANGEMENT | Mechanical System
|  | 56.1-E12101 - PI | [6 empty] | ARRANGEMENT OF PNEUMATIC PIPING | Mechanical System | •
|  | 56.1-E12201 - PI | [6 empty] | ARRANGEMENT OF PNEUMATIC PIPING | Mechanical System |  | •
|  | 56.1-E12301 - PI | [6 empty] | ARRANGEMENT OF PNEUMATIC PIPING | Mechanical System |  |  | •
|  | 56.1-E12701 - PI | [6 empty] | ARRANGEMENT OF PNEUMATIC PIPING | Mechanical System | [6 empty] | •
|  |  | 56.1-E12002 - PI | [5 empty] | MAIN PIPING (T1 & T3) | Mechanical System |  |  |  | • |  | • |  | A3 |  | 0 | A | 2024-02-06 | 2024-04-29 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  |  | 31.0-E12030 |  |  |  |  | M5070C MR STRAINER | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12034 |  |  |  |  | 12mm DRAIN BALL COCK | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12035 |  |  |  |  | 3/4 CHECK VALVE | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12036 |  |  |  |  | 3/4 BALL COCK | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12037 |  |  |  |  | 3/4 BALL COCK WITH SIDE VENT (D1) | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12038 |  |  |  |  | 3/4 BALL COCK WITH SIDE VENT (D2) | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12039 |  |  |  |  | 3/8 BALL COCK | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12040 |  |  |  |  | Y-3/8-MR STRAINER | Mechanical System |  |  |  | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  | 56.1-E12102 - PI | [5 empty] | MAIN PIPING (TC1) | Mechanical System | • | [6 empty] | A3 |  | 0 | A | 2024-02-15 | 2024-05-05 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  | 56.1-E12202 - PI | [5 empty] | MAIN PIPING (M1) | Mechanical System |  | • | [5 empty] | A3 |  | 0 | A | 2024-02-20 | 2024-05-05 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  | 56.1-E12302 - PI | [5 empty] | MAIN PIPING (M2) | Mechanical System |  |  | • |  |  |  |  | A3 |  | 0 | A | 2024-02-15 | 2024-05-27 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12502 - PI | [5 empty] | MAIN PIPING (T2) | Mechanical System |  |  |  |  | • |  |  | A3 |  | 0 | A | 2024-02-15 | 2024-05-27 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12702 - PI | [5 empty] | MAIN PIPING (TC2) | Mechanical System | [6 empty] | • | A3 |  | 0 | A | 2024-03-01 | 2024-05-05 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  |  | 31.0-E12031 |  |  |  |  | SPS-8WP PRESSURE SWITCH | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12032 |  |  |  |  | 3/8 BALL COCK WITH SIDE VENT | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12057 |  |  |  |  | HOSE PIPE (COUPLING) | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12055 |  |  |  |  | HOSE PIPE (AUTOMATIC TIGH LOCK) | Mechanical System | • | [23 empty] | CLOSED |  | CLOSED | N/A
|  |  | 56.1-E12103 - PI | [5 empty] | BRAKE PIPING (TC1) | Mechanical System | • | [6 empty] | A3 | 3 | 0 | 0 | 2024-02-15 | 2024-05-05 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  | 56.1-E12203 - PI | [5 empty] | BRAKE PIPING (M1 & M2) | Mechanical System |  | • | • |  |  |  |  | A3 | 3 | 0 | A | 2024-02-22 | 2024-05-21 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  | 56.1-E12703 - PI | [5 empty] | BRAKE PIPING (TC2) | Mechanical System | [6 empty] | • | A3 | 3 | 0 | A | 2024-03-04 | 2024-05-05 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  | 56.1-E12004 - PI | [5 empty] | BRAKE PIPING (T1, T2, T3) | Mechanical System |  |  |  | • | • | • |  | A3 | 3 | 0 | A | 2024-02-12 | 2024-04-29 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  |  | 31.4-G14036 |  |  |  |  | TEST FITTING R1/4 | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12021 |  |  |  |  | 1/2 BALL COCK WITH ELECTRICAL SWITCH | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12060 |  |  |  |  | HOSE PIPE (SERVICE BRAKE) | Mechanical System | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12061 |  |  |  |  | HOSE PIPE (PARKING BRAKE) | Mechanical System | • |  |  | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 56.1-E12104 - PI | [5 empty] | UNCOUPLING PIPING | Mechanical System | • | [5 empty] | • | A3 | 4 | 0 | 0 | 2024-07-09 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | HAS | APK | EKN
|  |  | 56.1-E12105 - PI | [5 empty] | AIR SUSPENSION PIPING (TC1) | Mechanical System | • | [6 empty] | A3 | 4 | A3 | B | 2024-02-18 | 2024-05-05 | 2024-07-09 | [10 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 56.1-E12005 - PI | [5 empty] | AIR SUSPENSION PIPING (T1, T2, T3) | Mechanical System |  | • | • | • | • | • |  | A3 |  | 0 | A | 2024-02-12 | 2024-05-21 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  |  | 31.0-E12024 |  |  |  |  | 3/4 BALL COCK | Mechanical System |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12025 |  |  |  |  | 3/8 CHOKE FITTING WITH STRAINER | Mechanical System |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12026 |  |  |  |  | 3/4 X 3/4 CHOKE FITTING | Mechanical System |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12041 |  |  |  |  | 3/8 BALL COCK WITH SIDE VENT | Mechanical System |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12042 |  |  |  |  | 3/8 BALL COCK WITH SIDE VENT | Mechanical System |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12027 |  |  |  |  | PRESSURE REGULATING VALVE WITH PIPE BRACKET | Mechanical System |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  | 56.1-E12205 - PI | [5 empty] | AIR SUSPENSION PIPING (M1, M2) | Mechanical System |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2024-02-12 | 2024-04-29 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12705 - PI | [5 empty] | AIR SUSPENSION PIPING (TC2) | Mechanical System | [6 empty] | • | A3 | 3 | 0 | A | 2024-03-04 | 2024-05-27 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12106 - PI | [5 empty] | PIPING ON CABIN | Mechanical System | • | [6 empty] | A3 |  | 0 | 0 | 2024-05-21 | 2024-06-04 | [11 empty] | CLOSED |  | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12706 - PI | [5 empty] | PIPING ON CABIN | Mechanical System | [6 empty] | •
|  |  |  | 31.0-E12028 |  |  |  |  | 3/8X10 TUBE UNION FITTING Ø1mm | Mechanical System | [6 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 31.0-E12029 |  |  |  |  | 3/8X10 TUBE UNION FITTING Ø6mm | Mechanical System | [6 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 56.1-E12207 - PI | [5 empty] | PANTOGRAPH PIPING | Mechanical System |  | • | [5 empty] | A3 |  | 0 | 0 | 2024-04-02 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12108 - PI | [5 empty] | HORN PIPING (TC) | Mechanical System | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-04-02 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12109 - PI | [5 empty] | PIPING OF LUBRICATION | Mechanical System | • | [5 empty] | • | A3 |  | 0 | 0 | 15/4/2024 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 56.1-E12308 - PI | [5 empty] | AIR SUPPLY PIPING (M2) | Mechanical System | [7 empty] | A3 |  | 0 | 0 | 2024-02-12 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 56.1-E12508 - PI | [5 empty] | AIR SUPPLY PIPING (T2) | Mechanical System |  |  | • |  | • |  |  | A3 |  | 0 | 0 | 2024-03-05 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | APR | APK | EKN
|  |  |  | 31.0-E12041 |  |  |  |  | HOSE PIPE (AIR SUPPLY) | Mechanical System |  |  | • |  | • | [22 empty] | N/A | salah no DD
|  | 30.7-E12101 - PI | [6 empty] | ARRANGEMENT EQUIPMENT ON CABIN | Mechanical System | [6 empty] | • | [20 empty] | N/A
|  |  | 57.2-E12124 - PI | [5 empty] | FITTING OF EMG. APPLIC. VALVE | Mechanical System | • | [5 empty] | •
|  |  |  | 57.2-E12025 |  |  |  |  | EMERGENCY APPLICATION VALVE | Mechanical System | • | [5 empty] | • | [20 empty] | N/A
|  |  | 57.2-E12126 - PI | [5 empty] | FITTING OF PRESSURE GAUGE | Mechanical System | • | [5 empty] | •
|  |  |  | 57.4-E12004 |  |  |  |  | 100mm X 1200kPa DOUBLE PRESSURE GAUGE | Mechanical System | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
Interior
| 28.0-E12100 - PI | [7 empty] | INTERIOR EXTERIOR (TC) | Interior | • | [5 empty] | •
| 28.0-E12200 - PI | [7 empty] | INTERIOR EXTERIOR (M) | Interior |  | • | •
| 28.0-E12400 - PI | [7 empty] | INTERIOR EXTERIOR (T) | Interior |  |  |  | • | • | •
| 28.0-E12101 - PI | [7 empty] | MARKING AND ACCESSORIES (TC) | Interior | • | [5 empty] | •
| 28.0-E12201 - PI | [7 empty] | MARKING AND ACCESSORIES (M) | Interior |  | • | •
| 28.0-E12401 - PI | [7 empty] | MARKING AND ACCESSORIES (T) | Interior |  |  |  | • | • | •
|  | 28.0-E12102 - PI | [6 empty] | COLOR SCHEME (TC) | Interior | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 28.0-E12202 - PI | [6 empty] | COLOR SCHEME (M) | Interior |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 28.0-E12402 - PI | [6 empty] | COLOR SCHEME (T) | Interior |  |  |  | • | • | •
|  | 28.1-E12101 - PI | [6 empty] | LAYOUT OUTSIDE MARKING (TC) | Interior | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  | 28.1-E12201 - PI | [6 empty] | LAYOUT OUTSIDE MARKING (M) | Interior |  | • | • |  |  |  |  | A3 |  | 0 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  | 28.1-E12401 - PI | [6 empty] | LAYOUT OUTSIDE MARKING (T) | Interior |  |  |  | • | • | •
|  |  | 28.1-A17001 | [5 empty] | BUILDERS PLATE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-A72202 | [5 empty] | MARKING OF DISABILITY | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-F11003 | [5 empty] | MARKING OF JACKING PAD | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-G13021 | [5 empty] | MARKING "DAHULUKAN PENUMPANG YANG TURUN" | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-K56005 | [5 empty] | MARKING EMERGENCY DOOR RELEASE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-E12001 | [5 empty] | NOMOR LAMBUNG | Interior | • | • | • | • | • | • | •
|  |  | 28.1-E12002 | [5 empty] | MARKING PRIORITY SEAT ACCESS | Interior | • | • | • | • | • | • | •
|  |  | 28.1-E12003 | [5 empty] | MARKING DISABILITY ACCESS | Interior | • | • | • | • | • | • | •
|  |  | 28.1-E12102 | [5 empty] | KODE SARANA (TC) | Interior | • | [5 empty] | •
|  | 28.2-E12101 - PI | [6 empty] | LAYOUT INSIDE MARKING (TC) | Interior | • | [5 empty] | •
|  | 28.2-E12201 - PI | [6 empty] | LAYOUT INSIDE MARKING (M) | Interior |  | • | •
|  | 28.2-E12401 - PI | [6 empty] | LAYOUT INSIDE MARKING (T) | Interior |  |  |  | • | • | •
|  |  | 28.1-E11008 | [5 empty] | MARKING OF DISTRIBUTION BOARD PANEL | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-E11009 | [5 empty] | MARKING OF RELAY PANEL | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-E11011 | [5 empty] | MARKING OF AC PANEL | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-E11012 | [5 empty] | MARKING OF ELECTRIC PANEL | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-E11013 | [5 empty] | MARKING OF FIRE EXTINGUISHER | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-E11204 | [5 empty] | MARKING OF AUDIO VIDEO PANEL | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-U03016 | [5 empty] | MARKING OF "NO SMOKING" | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-U03017 | [5 empty] | MARKING OF DOOR WARNING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-U03041 | [5 empty] | MARKING OF EMERGENCY WINDOW | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.2-A17004 | [5 empty] | MARKING OF PPPK | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.2-A17012 | [5 empty] | MARKING OF MAINTENANCE RUNNING TEXT | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.2-A73123 | [5 empty] | MARKING JANITOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.2-E12001 | [5 empty] | MARKING TRAIN NUMBER (INSIDE) | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12002 | [5 empty] | MARKING OF DISABILITY | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12003 | [5 empty] | MARKING PRIORITY SEAT (REFER MRT J) | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12004 | [5 empty] | MARKING EMERGENCY DOOR RELEASE (DOOR LINTEL) | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12005 | [5 empty] | MARKING OF EMERGENCY DOOR RELEASE (DOOR LINTEL) INSTRUCTION | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12006 | [5 empty] | MARKING EMERGENCY DOOR RELEASE (ENDWALL) | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12007 | [5 empty] | MARKING OF EMERGENCY DOOR RELEASE (ENDWALL) INSTRUCTION | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12008 | [5 empty] | MARKING EMERGENCY INTERCOM | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12009 | [5 empty] | MARKING EMERGENCY INTERCOM INSTRUCTION | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12010 | [5 empty] | MARKING EVACUATION ROUTE (REFER MRT J) | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12011 | [5 empty] | MARKING DOOR NUMBER | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12012 | [5 empty] | MARKING INHIBIT DOOR | Interior | • | • | • | • | • | • | •
|  |  | 28.2-E12102 | [5 empty] | MARKING EMERGENCY LADDER | Interior | • | [5 empty] | •
|  |  | 28.2-E12103 | [5 empty] | MARKING EMERGENCY LADDER INSTRUCTION (REFER MRT J) | Interior | • | [5 empty] | •
|  |  | 28.2-K56009 | [5 empty] | MARKING KEEP THE DOOR CLOSED | Interior | • | • | • | • | • | • | • | A3 | [16 empty] | CLOSED |  | CLOSED | N/A
|  | 28.5-E12101 - PI | [6 empty] | ARRANGEMENT ACCESSORIES (TC) | Interior | • | [5 empty] | •
|  | 28.5-E12001 - PI | [6 empty] | ARRANGEMENT ACCESSORIES (M&T) | Interior |  | • | • | • | • | •
|  |  | 28.1-A73111 | [5 empty] | BRACKET AND BOARD FOR DESTINATION BOARD | Interior | • | • | • | • | • | • | • | A3 | [16 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-A73112 | [5 empty] | BRACKET OF SIGNALING LAMP | Interior | • | • | • | • | • | • | • | A3 | [16 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-A73113 | [5 empty] | BRACKET FOR MARK BOARD OF PREPARATION | Interior | • | • | • | • | • | • | • | A3 | [16 empty] | CLOSED |  | CLOSED | N/A
|  |  | 28.1-A73114 | [5 empty] | BRACKET CLOSING MARK | Interior | • | • | • | • | • | • | • | A3 | [16 empty] | CLOSED |  | CLOSED | N/A
|  |  | 40.4-A17026 | [5 empty] | MARK PLATE AKHIRAN GERBONG | Interior | • | [5 empty] | • | A3 | [16 empty] | CLOSED |  | CLOSED | N/A
| 29.0-E12101 - PI | [7 empty] | ARRANGEMENT INSULATION (TC) | Interior | • | [5 empty] | •
| 29.0-E12201 - PI | [7 empty] | ARRANGEMENT INSULATION (M) | Interior |  | • | •
| 29.0-E12401 - PI | [7 empty] | ARRANGEMENT INSULATION (T) | Interior |  |  |  | • | • | •
|  | 29.1-E12101 - PI | [6 empty] | INSULATION OF UNDERFRAME & FLOOR (TC) | Interior | • | [5 empty] | •
|  | 29.1-E12201 - PI | [6 empty] | INSULATION OF UNDERFRAME & FLOOR (M) | Interior |  | • | •
|  | 29.1-E12401 - PI | [6 empty] | INSULATION OF UNDERFRAME & FLOOR (T) | Interior |  |  |  | • | • | •
|  | 29.2-E12101 - PI | [6 empty] | INSULATION OF BODY SIDE (TC) | Interior | • | [5 empty] | • | A3 | 3 | 0 |  | 2024-04-29 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  | 29.2-E12201 - PI | [6 empty] | INSULATION OF BODY SIDE (M) | Interior |  | • | • |  |  |  |  | A3 | 3 | 0 |  | 2024-05-17 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | HAS | APK | EKN
|  | 29.2-E12401 - PI | [6 empty] | INSULATION OF BODY SIDE (T) | Interior |  |  |  | • | • | • |  | A3 | 3 | 0 |  | 2024-05-21 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 29.3-E12001 - PI | [6 empty] | INSULATION OF BODY END | Interior | • | • | • | • | • | • | • | A3 | 3 | 0 |  | 2024-05-28 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 29.4-E12101 - PI | [6 empty] | INSULATION OF CABIN | Interior | • | [5 empty] | • | A3 | 3 | 0 |  | 2024-06-07 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  | 29.5-E12101 - PI | [6 empty] | INSULATION OF ROOF & CEILING (TC) | Interior | • | [5 empty] | • | A3 | 3 | 0 |  | 2024-06-07 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | HAS | APK | EKN
|  | 29.5-E12001 - PI | [6 empty] | INSULATION OF ROOF & CEILING (M&T) | Interior |  | • | • | • | • | • |  | A3 | 3 | 0 |  | 2024-05-17 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | KRS | APK | EKN
| 55.0-E12101- PI | [7 empty] | ARRANGEMENT CABIN AREA | Interior | • | [5 empty] | •
|  | 55.1-E12101 - PI | [6 empty] | ARRANGEMENT COMPONENT ON MASK OF CAR | Interior | • | [5 empty] | • | [20 empty] | N/A
|  |  | 55.1-E12102 - PI | [5 empty] | FITTING WIPER | Interior | • | [5 empty] | • | A3 | 1 | 0 |  | 2024-07-15 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 55.1-E12107 |  |  |  |  | WIPER | Interior | • | [5 empty] | • | A3 | 1 | 0 |  | 2024-01-29 | [12 empty] | CLOSED |  | CLOSED | N/A |  |  |  |  | EKN
|  |  | 55.1-E12103 - PI | [5 empty] | FITTING HEAD LAMP | Interior | • | [5 empty] | • | A3 | 2 | A3 | 0 | 2024-06-16 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | DHE | APK | EKN
|  |  |  | 55.1-E12108 |  |  |  |  | BRACKET HEAD LAMP | Interior | • | [5 empty] | • | [20 empty] | N/A
|  |  | 55.1-E12104 - PI | [5 empty] | FITTING FOG LAMP | Interior | • | [5 empty] | • | A3 | 2 | A3 | 0 | 2024-07-02 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 55.1-E12109 |  |  |  |  | BRACKET FOG LAMP | Interior | • | [5 empty] | • | [20 empty] | N/A
|  |  | 55.1-E12105 - PI | [5 empty] | FITTING FRONT SIGNAL LAMP | Interior | • | [5 empty] | • | A3 | 2 | A3 | 0 | 2024-06-16 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 55.1-E12110 |  |  |  |  | BRACKET FRONT SIGNAL LAMP | Interior | • | [5 empty] | • | [20 empty] | N/A
|  |  | 55.1-E12106 - PI | [5 empty] | FITTING FRONT DESTINATION DISPLAY | Interior | • | [5 empty] | • | A3 | 2 | A3 | 0 | 2024-06-16 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | DHE | APK | EKN
|  |  |  | 55.1-E12111 |  |  |  |  | BRACKET FRONT DESTINATION DISPLAY | Interior | • | [5 empty] | • | [20 empty] | N/A
|  |  | 55.1-E12112 - PI | [5 empty] | FITTING DRL LED | Interior | • | [5 empty] | •
|  |  |  | 55.1-E12113 |  |  |  |  | BRACKET DRL LED | Interior | • | [5 empty] | • | [20 empty] | N/A
|  | 55.3-E12101 - PI | [6 empty] | ARRANGEMENT COMPONENT ON CABIN | Interior | • | [5 empty] | • | A3 | 1 | A3 | 0 | 2024-05-27 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  | 55.3-E12102 - PI | [5 empty] | FITTING DRIVER SEAT | Interior | • | [5 empty] | •
|  |  |  | 55.4-H11018 |  |  |  |  | DRIVER SEAT | Interior | • | [5 empty] | • | A3 | 1 | 0 |  | 2024-01-29 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.3-E12103 - PI | [5 empty] | FITTING CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | A3 | 1 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  |  | 55.3-E12107 |  |  |  |  | CABIN ELECTRIC CABINET 1 | Interior | • | [5 empty] | • | A3 | 1 | 0 |  | 2024-01-29 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12115 |  |  |  | CROSS SECTION PARTITION PANEL HOLDER 1 | Interior | • | [5 empty] | • | A3 | 1 | 0 |  | 2024-01-29 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12116 |  |  |  | CROSS SECTION PARTITION PANEL HOLDER 2 | Interior | • | [5 empty] | • | A3 | 1 | 0 |  | 2024-01-29 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12117 |  |  |  | CROSS SECTION DOOR PANEL HOLDER | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12118 |  |  |  | CROSS SECTION HOLLOW PROFILE 30x20 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12119 |  |  |  | SIDE PANEL CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12120 |  |  |  | REAR PANEL CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12121 |  |  |  | FRAME & BRACKET CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12122 |  |  |  | DOOR PANEL 1 CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12123 |  |  |  | DOOR PANEL 2 CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12124 |  |  |  | TOP PANEL CABIN ELECTRIC CABINET 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12128 |  |  |  | TOP COVER CABIN ELECTRIC CABINET 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12129 |  |  |  | FRONT PANEL CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.3-E12108 |  |  |  |  | CABIN ELECTRIC CABINET 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  |  | N/A | OPEN
[5 empty] | 55.3-E12125 |  |  |  | DOOR PANEL 3 CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12126 |  |  |  | DOOR PANEL 4 CABIN ELECTRIC CABINET | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12127 |  |  |  | TOP COVER CABIN ELECTRIC CABINET 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.3-E12109 |  |  |  |  | MOULDING CABIN ELECTRIC CABINET 1 | Interior | • | [5 empty] | •
|  |  |  | 55.3-E12110 |  |  |  |  | MOULDING CABIN ELECTRIC CABINET 2 | Interior | • | [5 empty] | •
|  |  | 55.3-E12104 - PI | [5 empty] | FITTING WATER TANK WIPER | Interior | • | [5 empty] | •
|  |  |  | 55.3-E12111 |  |  |  |  | BRACKET WATER TANK WIPER | Interior | • | [5 empty] | •
|  |  | 55.3-E12105 - PI | [5 empty] | FITTING SUNVISOR | Interior | • | [5 empty] | • | A3 | 3 | A3 | 0 | 2024-06-16 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 55.3-E12112 |  |  |  |  | SUNVISOR | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.3-E12113 |  |  |  |  | BRACKET SUNVISOR | Interior | • | [5 empty] | • | [20 empty] | N/A
|  |  | 55.3-E12106 - PI | [5 empty] | FITTING FIRE EXTINGUISHER ON CABIN | Interior | • | [5 empty] | •
|  |  |  | 55.3-K56012 |  |  |  |  | BRACKET FIRE EXTINGUISHER | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.2-E12016 |  |  |  |  | FIRE EXTINGUISHER CO2 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.6-E12101 - PI | [5 empty] | FITTING OF DRIVER CABIN PANEL | Interior | • | [5 empty] | •
|  |  |  | 55.6-E12102 - PI |  |  |  |  | ARRANGEMENT DRIVER CABIN PANEL | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-11 | [12 empty] | CLOSED | CLOSED | CLOSED | CLOSED |  |  | IZA | APK | EKN
[5 empty] | 55.6-E12103 |  |  |  | DRIVER CABIN SIDEWALL PANEL 1 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12104 |  |  |  | DRIVER CABIN SIDEWALL PANEL 2 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12105 |  |  |  | DRIVER CABIN SIDEWALL PANEL 3 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12106 |  |  |  | DRIVER CABIN SIDEWALL PANEL 4 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12107 |  |  |  | DRIVER CABIN SIDEWALL PANEL 5 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12108 |  |  |  | DRIVER CABIN SIDEWALL PANEL 6 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12109 |  |  |  | DRIVER CABIN CEILING PANEL 1 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12110 |  |  |  | DRIVER CABIN CEILING PANEL 2 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12111 |  |  |  | DRIVER CABIN CEILING PANEL 3 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12112 |  |  |  | DRIVER CABIN CEILING PANEL 4 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12113 |  |  |  | DRIVER CABIN CEILING PANEL 5 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12114 |  |  |  | DRIVER CABIN CEILING PANEL 6 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12115 |  |  |  | DRIVER CABIN CEILING PANEL 7 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12116 |  |  |  | DRIVER CABIN CEILING PANEL 8 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12117 |  |  |  | DRIVER CABIN CEILING PANEL 9 | Interior | • | [5 empty] | • |  | 1 | A3 | A | 2024-01-30 | 2024-03-15 | [11 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12118 |  |  |  | CABIN MOULDING PANEL | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12123 |  |  |  | BRACKET CABIN CEILING PANEL 1 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12124 |  |  |  | BRACKET CABIN CEILING PANEL 2 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12125 |  |  |  | BRACKET CABIN CEILING PANEL 3 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12126 |  |  |  | BRACKET CABIN CEILING PANEL 4 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.6-E12127 |  |  |  | BRACKET CABIN CEILING PANEL 5 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-01-30 | [12 empty] | CLOSED |  | CLOSED | N/A
[9 empty] | DIFFUSER AC CABIN | Interior | • | [5 empty] | •
|  |  | 55.7-E12101 - PI | [5 empty] | ARRANGEMENT CABIN WINDOWS | Interior | • | [5 empty] | •
|  |  | 55.7-E12102 - PI | [5 empty] | FITTING FRONT WINDSHIELD | Interior | • | [5 empty] | • | A3 | 3 | A3 | A | 2024-03-13 | 2024-04-18 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 55.7-E12106 |  |  |  |  | FRONT WINDSHIELD | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.7-E12103 - PI | [5 empty] | FITTING SIDE WINDOW CABIN | Interior | • | [5 empty] | • | A3 | 3 | A3 | A | 2024-03-13 | 2024-04-18 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 55.7-E12107 |  |  |  |  | SIDE WINDOW CABIN | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.7-E12104 - PI | [5 empty] | FITTING TOP COVER GLASS | Interior | • | [5 empty] | • | A3 | 3 | A3 | A | 2024-03-13 | 2024-04-18 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 55.7-E12108 |  |  |  |  | TOP COVER GLASS | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.7-E12105 - PI | [5 empty] | FITTING BOTTOM COVER GLASS | Interior | • | [5 empty] | • | A3 | 3 | A3 | A | 2024-02-15 | 2024-04-18 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 55.7-E12109 |  |  |  |  | BOTTOM COVER GLASS | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.8-E12101 - PI | [5 empty] | ARRANGEMENT CABIN DOOR | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  | 55.8-E12102 - PI | [5 empty] | FITTING CABIN ENTRANCE DOOR | Interior | • | [5 empty] | • | A3 | 2 | A3 | A | 2024-02-01 | 2024-04-29 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | DHE | APK | EKN
|  |  |  | 55.8-E12105 |  |  |  |  | CABIN ENTRANCE DOOR 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.8-E12106 |  |  |  |  | CABIN ENTRANCE DOOR 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.8-E12112 |  |  |  | SLIDING WINDOW CABIN ENTRANCE DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[6 empty] | 65.1-L10019 |  |  | LOCKING DEVICE SWING DOOR | Interior | • | [5 empty] | • | [20 empty] | N/A
[5 empty] | 55.8-E12113 |  |  |  | MOULDING 1 SWING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[6 empty] | 65.1-A73004 |  |  | MOULDING EXTRUSI | Interior | • | [5 empty] | • | [20 empty] | N/A
[5 empty] | 55.8-E12118 |  |  |  | MOULDING 2 SWING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.8-E12119 |  |  |  | MOULDING 3 SWING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.8-E12114 |  |  |  | RUBBER 1 CABIN ENTRANCE DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.8-E12120 |  |  |  | RUBBER 2 CABIN ENTRANCE DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.8-E12115 |  |  |  | CROSS SECTION RUBBER SWING DOOR 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.8-E12103 - PI | [5 empty] | FITTING MOULDING CABIN ENTRANCE DOOR | Interior | • | [5 empty] | • | A3 | 1 | A3 | A | 2024-02-01 | 2024-05-05 | [11 empty] | CLOSED |  | CLOSED | CLOSED |  |  | DHE | APK | EKN
|  |  |  | 55.8-E12107 |  |  |  |  | MOULDING CABIN ENTRANCE DOOR 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 65.1-A17006 |  |  |  | EXTRUSION SILL PLATE | Interior | • | [5 empty] | • | [20 empty] | N/A
|  |  |  | 55.8-E12108 |  |  |  |  | MOULDING CABIN ENTRANCE DOOR 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.8-E12110 |  |  |  |  | SILL PLATE CABIN ENTRANCE DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.8-E12111 |  |  |  |  | RUBBER MOULDING CABIN ENTRANCE DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.8-K56013 |  |  |  |  | CROSS SECTION RUBBER SWING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.8-E12121 |  |  |  |  | LATCH SWING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.8-E12122 |  |  |  |  | HINGE SWING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 55.8-E12104 - PI | [5 empty] | FITTING SWING DOOR STOPPER | Interior | • | [5 empty] | • | A3 | 4 |  | 0 | 2024-01-24 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  |  | 55.8-K56008 |  |  |  |  | SWING DOOR STOPPER | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
| 57.0-E12101 - PI | [7 empty] | ARRANGEMENT DRIVER DESK | Interior | • | [5 empty] | •
|  | 57.1-E12101 - PI | [6 empty] | FITTING DRIVER DESK | Interior | • | [5 empty] | • | A3 | 1 | A3 | 0 | 2024-07-16 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  | 57.1-E12102 | [5 empty] | TOP DRIVER DESK | Interior | • | [5 empty] | •
|  |  |  | 57.1-E12110 |  |  |  |  | TOP TABLE DRIVER DESK 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12111 |  |  |  |  | COVER TOP DRIVER DESK 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12112 |  |  |  |  | COVER TOP DRIVER DESK 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12113 |  |  |  |  | COVER TOP DRIVER DESK 3 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12114 |  |  |  |  | COVER TOP DRIVER DESK 4 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12115 |  |  |  |  | TOP TABLE DRIVER DESK 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 57.1-E12103 | [5 empty] | BOTTOM DRIVER DESK | Interior | • | [5 empty] | •
|  |  |  | 57.1-E12119 |  |  |  |  | FRAME BOTTOM DRIVER DESK 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12120 |  |  |  |  | FRAME BOTTOM DRIVER DESK 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12122 |  |  |  |  | SHEETING BOTTOM DRIVER DESK 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12123 |  |  |  |  | SHEETING BOTTOM DRIVER DESK 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12124 |  |  |  |  | FOOT PLATE DRIVER DESK 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12125 |  |  |  |  | SHEETING BOTTOM DRIVER DESK 3 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12126 |  |  |  |  | SHEETING BOTTOM DRIVER DESK 4 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12127 |  |  |  |  | FOOT PLATE DRIVER DESK 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12128 |  |  |  |  | SHEETING BOTTOM DRIVER DESK 5 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12129 |  |  |  |  | MAINTENANCE DOOR DRIVER DESK 1 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12130 |  |  |  |  | MAINTENANCE DOOR DRIVER DESK 2 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12131 |  |  |  |  | MAINTENANCE DOOR DRIVER DESK 3 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 57.1-E12132 |  |  |  |  | BOX COVER DRIVER DESK | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 57.1-E12108 | [5 empty] | BRACKET SUPPORT DRIVER DESK | Interior | • | [5 empty] | •
|  | 57.2-E12101 - PI | [6 empty] | ARRANGEMENT COMPONENT ON DRIVER DESK | Interior | • | [5 empty] | • | A3 | 1 | A3 | 0 | 2024-05-22 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  | 57.2-E12102 - PI | [5 empty] | FITTING SWITCH PLATE DRIVER DESK | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12113 |  |  |  |  | BASE PLATE DRIVER DESK SWITCH PANEL 1 | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12114 |  |  |  |  | BASE PLATE DRIVER DESK SWITCH PANEL 2 | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12115 |  |  |  |  | BASE PLATE DRIVER DESK SWITCH PANEL 3 | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12116 |  |  |  |  | BASE PLATE DRIVER DESK SWITCH PANEL 4 | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12117 |  |  |  |  | BASE PLATE DRIVER DESK SWITCH PANEL 5 | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12118 |  |  |  |  | BASE PLATE DRIVER DESK SWITCH PANEL 6 | Interior | • | [5 empty] | •
|  |  | 57.2-E12103 - PI | [5 empty] | FITTING MASTER CONTROLLER | Interior | • | [5 empty] | •
|  |  | 57.2-E12104 - PI | [5 empty] | FITTING INTERCOM | Interior | • | [5 empty] | •
|  |  | 57.2-E12105 - PI | [5 empty] | FITTING HMI TCMS | Interior | • | [5 empty] | •
|  |  | 57.2-E12106 - PI | [5 empty] | FITTING HMI PIDS | Interior | • | [5 empty] | •
|  |  | 57.2-E12107 - PI | [5 empty] | FITTING CLIPBOARD ON CABIN | Interior | • | [5 empty] | •
|  |  | 57.2-E12108 - PI | [5 empty] | FITTING RADIO LOCO | Interior | • | [5 empty] | •
|  |  | 57.2-E12109 - PI | [5 empty] | FITTING PIS ANNOUNCER | Interior | • | [5 empty] | •
|  |  | 57.2-E12110 - PI | [5 empty] | FITTING EMERGENCY APPLICATION BRAKE | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12119 |  |  |  |  | EMERGENCY APPLICATION VALVE | Interior | • | [5 empty] | •
|  |  | 57.2-E12111 - PI | [5 empty] | FITTING UNCOUPLING COUPLER BUTTON | Interior | • | [5 empty] | •
|  |  |  | 57.2-E12120 |  |  |  |  | MAGNET VALVE PRESS BUTTON FOR UNCOUPLING COUPLER | Interior | • | [5 empty] | •
|  |  | 57.2-E12112 - PI | [5 empty] | FITTING PEDAL | Interior | • | [5 empty] | •
| 58.0-E12150 - PI | [7 empty] | ARRANGEMENT ELECTRIC EQUIPMENT ON CABIN | Interior | • | [5 empty] | •
|  | 58.1-E12150 - PI | [6 empty] | FITTING BASE PLATE CONTROL PANEL ON CABIN | Interior | • | [5 empty] | •
|  |  | 58.1-E12152 | [5 empty] | BASE PLATE CONTROL PANEL ON CABIN 1 | Interior | • | [5 empty] | •
|  |  | 58.1-E12153 | [5 empty] | BASE PLATE CONTROL PANEL ON CABIN 2 | Interior | • | [5 empty] | •
|  |  | 58.1-E12154 | [5 empty] | BASE PLATE CONTROL PANEL ON CABIN 3 | Interior | • | [5 empty] | •
|  |  | 58.1-E12155 | [5 empty] | BASE PLATE CONTROL PANEL ON CABIN 4 | Interior | • | [5 empty] | •
|  | 58.1-E12151 - PI | [6 empty] | FITTING SWITCH PLATE ON CABIN | Interior | • | [5 empty] | •
|  |  | 58.1-E12156 | [5 empty] | BASE PLATE SWITCH PANEL 1 | Interior | • | [5 empty] | •
|  |  | 58.1-E12157 | [5 empty] | BASE PLATE SWITCH PANEL 2 | Interior | • | [5 empty] | •
|  |  | 58.1-E12158 | [5 empty] | BASE PLATE SWITCH PANEL 3 | Interior | • | [5 empty] | •
|  |  | 58.1-E12159 | [5 empty] | BASE PLATE SWITCH PANEL 4 | Interior | • | [5 empty] | •
|  |  | 58.1-E12160 | [5 empty] | BASE PLATE SWITCH PANEL 5 | Interior | • | [5 empty] | •
|  |  | 58.1-E12161 | [5 empty] | BASE PLATE SWITCH PANEL 6 | Interior | • | [5 empty] | •
|  | 58.2-E12150 - PI | [6 empty] | FITTING LINE TRANSCEIVER UNIT BOX | Interior | • | [5 empty] | •
|  | 58-2-E12151 - PI | [6 empty] | FITTING CABIN LAMP | Interior | • | [5 empty] | •
|  | 58.2-E12152 - PI | [6 empty] | FITTING CABIN CCTV | Interior | • | [5 empty] | •
| 63.0-E12101 - PI | [7 empty] | ARRANGEMENT FLOOR (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | N/A |  |  | AZA | APK | EKN
| 63.0-E12201 - PI | [7 empty] | ARRANGEMENT FLOOR (M) | Interior |  | • | • |  |  |  |  | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | N/A |  |  | AZA | APK | EKN
| 63.0-E12401 - PI | [7 empty] | ARRANGEMENT FLOOR (T) | Interior |  |  |  | • | • | • |  | A3 | 4 | A3 | 0 | 2024-05-21 | [12 empty] | CLOSED |  | CLOSED | N/A |  |  | AZA | APK | EKN
|  | 63.1-E12101 - PI | [6 empty] | FLOOR COVERING (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 63.1-E12201 - PI | [6 empty] | FLOOR COVERING (M) | Interior |  | • | • |  |  |  |  | A3 | 4 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  | 63.1-E12401 - PI | [6 empty] | FLOOR COVERING (T) | Interior |  |  |  | • | • | • |  | A3 | 4 | A3 | 0 | 2024-05-21 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 63.2-E12011 | [5 empty] | FLOOR COVERING WHEELCHAIR AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 63.2-E12012 | [5 empty] | FLOOR COVERING ANTI SLIP ENTRANCE DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  | 63.1-E12102 - PI | [6 empty] | FITTING FLOOR PLANE RADIUS (TC) | Interior | • | [5 empty] | •
|  | 63.1-E12005 - PI | [6 empty] | FITTING FLOOR PLANE RADIUS (M &T) | Interior |  | • | • | • | • | •
|  |  | 63.1-E12001 | [5 empty] | FLOOR PLANE RADIUS 1 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 63.1-E12002 | [5 empty] | FLOOR PLANE RADIUS 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 63.1-E12104 | [5 empty] | FLOOR PLANE RADIUS 1 (TC) | Interior | • | • | • | • | • | • | •
|  |  |  | 63.1-K74006 |  |  |  |  | CROSS SECTION FLOOR PLANE RADIUS PROFILE | Interior | • | • | • | • | • | • | •
|  | 63.1-E12103 - PI | [6 empty] | FITTING MOULDING ALUMUNIUM (TC) | Interior | • | [5 empty] | •
|  | 63.1-E12006 - PI | [6 empty] | FITTING MOULDING ALUMUNIUM (M&T) | Interior |  | • | • | • | • | •
|  |  | 63.1-E12003 | [5 empty] | MOULDING 1 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 63.1-E12004 | [5 empty] | MOULDING 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 63.1-E12007 | [5 empty] | FLOOR PLANE RADIUS 3 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 63.2-F10021 |  |  |  |  | MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  | 63.2-E12001 - PI | [6 empty] | FLOOR LAYER | Interior | • | • | • | • | • | • | •
| 64.0-E12101 - PI | [7 empty] | LINNING OF SIDEWALL PANEL (TC) | Interior | • | [5 empty] | •
| 64.0-E12001 - PI | [7 empty] | LINNING OF SIDEWALL PANEL (M&T) | Interior |  | • | • | • | • | •
|  | 64.1-E12101 - PI | [6 empty] | FITTING SIDEWALL PANEL (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-12 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 64.1-E12019 - PI | [6 empty] | FITTING SIDEWALL PANEL (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-04 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 64.1-E12104 - PI | [5 empty] | ARRANGEMENT SIDEWALL PANEL (TC) | Interior | • | [5 empty] | •
|  |  | 64.1-E12022 - PI | [5 empty] | ARRANGEMENT SIDEWALL PANEL (M&T) | Interior |  | • | • | • | • | •
|  |  |  | 64.1-E12003 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 1 -> TOP | Interior |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12004 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 2 -> TOP | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12008 |  |  |  | MOULDING FOR DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[6 empty] | 64.1-E12011 |  |  | CROSS SECTION WINDOW MOULDING PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[6 empty] | 64.1-E12012 |  |  | CROSS SECTION SLOT COVER WINDOW MOULDING PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[6 empty] | 66.5-E12018 |  |  | CROSS SECTION MID PILLAR DOUBLE SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12030 |  |  |  | CROSS SECTION PANEL MOUNTING PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12009 |  |  |  | CROSS SECTION L PROFILE 20x20 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12015 |  |  |  | CROSS SECTION RUBBER SPACER WINDOW MOULDING PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12005 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 3 -> TOP | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12006 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 4 -> TOP | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12010 |  |  |  | MOULDING FOR SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12007 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 5 -> BOTTOM | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12018 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 6 -> BOTTOM | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12026 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 7 -> TOP | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12108 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 1 (TC) -> TOP | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12109 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 2 (TC) -> TOP | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12113 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 3 (TC) -> BOTTOM | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.2-G14051 |  |  |  | CROSS SECTION HOLLOW PROFILE 8x30 | Interior |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12027 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 8 -> TOP | Interior |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12028 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 9 -> TOP | Interior |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12029 |  |  |  |  | SIDEWALL PANEL PASSENGER AREA 10 -> BOTTOM | Interior |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  | 64.1-E12102 - PI | [6 empty] | FITTING INNER FRAMING SIDEWALL (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-12 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 64.1-E12020 - PI | [6 empty] | FITTING INNER FRAMING SIDEWALL (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-04 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 64.1-E12001 | [5 empty] | INNER FRAMING SIDEWALL 1 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.3-E12118 |  |  |  |  | CROSS SECTION HOLLOW PROFILE 30x20 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12031 |  |  |  |  | CROSS SECTION C PROFILE 66x40 | Interior | • | • | • | • | • | • | •
|  |  | 64.1-E12002 | [5 empty] | INNER FRAMING SIDEWALL 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.1-E12105 | [5 empty] | INNER FRAMING SIDEWALL 3 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.1-E12106 | [5 empty] | INNER FRAMING SIDEWALL 4 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.1-E12111 | [5 empty] | INNER FRAMING SIDEWALL 1 (TC) | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.1-E12112 | [5 empty] | INNER FRAMING SIDEWALL 2 (TC) | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  | 64.1-E12103 - PI | [6 empty] | FITTING PANEL HOLDER PROFILE (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-04 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 64.1-E12021 - PI | [6 empty] | FITTING PANEL HOLDER PROFILE (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-04 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 64.1-E12107 | [5 empty] | ARRANGEMENT PANEL HOLDER PROFILE (TC) | Interior | • | [5 empty] | •
|  |  | 64.1-E12025 | [5 empty] | ARRANGEMENT PANEL HOLDER PROFILE (M&T) | Interior |  | • | • | • | • | •
|  |  |  | 64.1-E12014 |  |  |  |  | PANEL HOLDER PROFILE 1 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12017 |  |  |  | CROSS SECTION PANEL HOLDER PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A | \
|  |  |  | 64.1-E12016 |  |  |  |  | PANEL HOLDER PROFILE 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12013 |  |  |  |  | PANEL HOLDER PROFILE 3 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12023 |  |  |  |  | PANEL HOLDER PROFILE 4 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.2-G14051 |  |  |  | CROSS SECTION HOLLOW PROFILE 8x30 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12110 |  |  |  |  | PANEL HOLDER PROFILE 1 (TC) | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12114 |  |  |  |  | PANEL HOLDER PROFILE 2 (TC) | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 67.1-E12020 |  |  |  | CROSS SECTION MOULDING GAP PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12023 |  |  |  |  | PANEL HOLDER PROFILE 5 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.1-E12023 |  |  |  |  | PANEL HOLDER PROFILE 6 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  | 64.2-E12101 - PI | [6 empty] | ARRANGEMENT INTERIOR COMPONENT ON SIDEWALL (TC) | Interior | • | [5 empty] | •
|  | 64.2-E12011 - PI | [6 empty] | ARRANGEMENT INTERIOR COMPONENT ON SIDEWALL (M&T) | Interior |  | • | • | • | • | •
|  |  | 64.2-E12102 - PI | [5 empty] | FITTING FOLDING SEAT (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 64.2-E12012 - PI | [5 empty] | FITTING FOLDING SEAT (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 64.2-E12003 |  |  |  |  | FOLDING SEAT | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 64.2-E12006 |  |  |  |  | BRACKET FOLDING SEAT | Interior | • | • | • | • | • | • | • | [20 empty] | N/A
|  |  |  | 64.2-E12007 |  |  |  |  | FRAME FOLDING SEAT | Interior | • | • | • | • | • | • | • | [20 empty] | N/A
|  |  |  | 64.2-E12008 |  |  |  |  | SPRING FOLDING SEAT | Interior | • | • | • | • | • | • | • | [20 empty] | N/A
|  |  |  | 64.2-E12009 |  |  |  |  | CUSHION FOLDING SEAT | Interior | • | • | • | • | • | • | • | [20 empty] | N/A
|  |  |  | 64.2-E12010 |  |  |  |  | COVER FOLDING SEAT | Interior | • | • | • | • | • | • | • | [20 empty] | N/A
|  |  | 64.2-E12001 - PI | [5 empty] | FITTING ROLLER BLIND 1 | Interior | • | • | • | • | • | • | • | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 64.2-E12004 |  |  |  |  | ROLLER BLIND 1 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.2-E12002 - PI | [5 empty] | FITTING ROLLER BLIND 2 | Interior | • | • | • | • | • | • | • | A3 | 4 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | FRA | APK | EKN
|  |  |  | 64.2-E12005 |  |  |  |  | ROLLER BLIND 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.2-E12103 - PI | [5 empty] | FITTING PECU (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.2-E12013 - PI | [5 empty] | FITTING PECU (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-07-02 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.2-E12104 - PI | [5 empty] | FITTING INTERIOR ENTRANCE HANDRAIL (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-04 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 64.2-E12014 - PI | [5 empty] | FITTING INTERIOR ENTRANCE HANDRAIL (M&T) | Interior |  | • | • | • | • | •
|  |  |  | 64.3-K56009 |  |  |  |  | ENTRANCE HANDRAIL | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.2-E12105 - PI | [5 empty] | FITTING FIRE EXTINGUISHER (TC) | Interior | • | [5 empty] | •
|  |  | 64.2-E12015 - PI | [5 empty] | FITTING FIRE EXTINGUISHER (M&T) | Interior |  | • | • | • | • | •
|  |  |  | 55.3-K56012 |  |  |  |  | BRACKET FIRE EXTINGUISHER | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.2-E12016 |  |  |  |  | FIRE EXTINGUISHER CO2 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.2-E12017 |  |  |  |  | BOX FIRE EXTINGUISHER | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.2-E12106 - PI | [5 empty] | FITTING EMERGENCY HAMMER (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-15 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.2-E12018 - PI | [5 empty] | FITTING EMERGENCY HAMMER (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-15 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  |  | 64.2-E12019 |  |  |  |  | EMERGENCY HAMMER | Interior | • | • | • | • | • | • | •
|  | 64.3-E12101 - PI | [6 empty] | ARRANGEMENT EXTERIOR COMPONENT ON SIDEWALL (TC) | Interior | • | [5 empty] | •
|  | 64.3-E12201 - PI | [6 empty] | ARRANGEMENT EXTERIOR COMPONENT ON SIDEWALL (M) | Interior |  | • | •
|  | 64.3-E12401 - PI | [6 empty] | ARRANGEMENT EXTERIOR COMPONENT ON SIDEWALL (T) | Interior |  |  |  | • | • | •
|  |  | 64.3-E12102 - PI | [5 empty] | FITTING SIDE VIEW CCTV (TC) | Interior | • | [5 empty] | •
|  |  | 64.3-E12103 - PI | [5 empty] | FITTING SIDE SIGNAL LAMP (TC) | Interior | • | [5 empty] | •
|  |  | 64.3-E12104 - PI | [5 empty] | FITTING RUNNING TEXT EXTERIOR (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-11 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 64.3-E12003 - PI | [5 empty] | FITTING RUNNING TEXT EXTERIOR (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-11 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 64.3-E12001 |  |  |  |  | BOX RUNNING TEXT EXTERIOR | Interior | •
|  |  | 64.3-E12105 - PI | [5 empty] | FITTING EXTERIOR HANDRAIL (TC) | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 64.3-E12004 - PI | [5 empty] | FITTING EXTERIOR HANDRAIL (M & T) | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-03-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 64.3-K56009 |  |  |  |  | ENTRANCE HANDRAIL | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.3-E12106 - PI | [5 empty] | FITTING CABIN ENTRANCE HANDRAIL | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-04 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 64.3-E12111 |  |  |  |  | CABIN ENTRANCE HANDRAIL | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 64.3-E12112 |  |  |  |  | COVER PLATE CABIN ENTRANCE HANDRAIL | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED |  | CLOSED | N/A
|  |  | 64.3-E12107 - PI | [5 empty] | FITTING EXTERIOR EMERGENCY DOOR RELEASE (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-11 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 64.3-E12005 - PI | [5 empty] | FITTING EXTERIOR EMERGENCY DOOR RELEASE (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-07-11 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 64.3-E12002 |  |  |  |  | COVER EXTERIOR EMERGENCY DOOR RELEASE | Interior | • | • | • | • | • | • | •
|  |  | 64.3-E12108 - PI | [5 empty] | FITTING EXTERIOR DOOR INDICATOR LAMP (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.3-E12006 - PI | [5 empty] | FITTING EXTERIOR DOOR INDICATOR LAMP (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.3-E12109 - PI | [5 empty] | FITTING EXTERIOR BUZZER INDICATOR LAMP (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.3-E12007 - PI | [5 empty] | FITTING EXTERIOR BUZZER INDICATOR LAMP (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.3-E12110 - PI | [5 empty] | FITTING EXTERIOR DOOR BUZZER (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | HAS | APK | EKN
|  |  | 64.3-E12008 - PI | [5 empty] | FITTING EXTERIOR DOOR BUZZER (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | HAS | APK | EKN
|  |  | 64.3-E12202 - PI | [5 empty] | FITTING EXTERIOR PROPULSION INDICATOR LAMP (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-15 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 64.3-E12203 - PI | [5 empty] | FITTING AIR GRILL TRACTION MOTOR (M) | Interior |  | • | •
|  |  |  | 64.3-E12204 |  |  |  |  | AIR GRILL TRACTION MOTOR | Interior |  | • | •
| 66.0-E12101 - PI | [7 empty] | ARRANGEMENT DOOR & WINDOW (TC) | Interior | • | [5 empty] | •
| 66.0-E12001 - PI | [7 empty] | ARRANGEMENT DOOR & WINDOW (M&T) | Interior |  | • | • | • | • | •
|  | 66.2-E12001 - PI | [6 empty] | FITTING SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | •
|  |  | 66.2-E12002 - PI | [5 empty] | FITTING DOOR ENGINE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.2-E12007 |  |  |  |  | DOOR ENGINE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.2-E12008 |  |  |  |  | ELECTRONIC DOOR CONTROL UNIT | Interior | • | • | • | • | • | • | •
|  |  |  | 66.2-E12009 |  |  |  |  | TERMINAL BOARD | Interior | • | • | • | • | • | • | •
|  |  |  | 66.2-E12010 |  |  |  |  | HANGING DEVICE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.2-E12011 |  |  |  |  | EMERGENCY EGRESS DEVICE (INTERNAL) | Interior | • | • | • | • | • | • | •
|  |  |  | 66.2-E12012 |  |  |  |  | DOOR ISOLATION DEVICE | Interior | • | • | • | • | • | • | •
|  |  | 66.2-E12003 | [5 empty] | SLIDING ENTRANCE DOOR 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 66.2-E12013 |  |  |  |  | GLASS ENTRANCE DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12014 |  |  |  |  | SLIDING ENTRANCE DOOR WINDOW OUTER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12020 |  |  |  | CROSS SECTION DOOR WINDOW OUTER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12015 |  |  |  |  | SLIDING ENTRANCE DOOR WINDOW INNER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12021 |  |  |  | CROSS SECTION DOOR WINDOW INNER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12016 |  |  |  |  | SLIDING ENTRANCE DOOR WINDOW RUBBER | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12022 |  |  |  | CROSS SECTION DOOR WINDOW RUBBER | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12017 |  |  |  |  | INBOW HANDLE SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12018 |  |  |  |  | BOTTOM GUIDE SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12019 |  |  |  |  | RUBBER SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | • | [21 empty] | OPEN
[5 empty] | 66.2-E12023 |  |  |  | CROSS SECTION RUBBER SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 55.3-E12118 |  |  |  |  | CROSS SECTION HOLLOW PROFILE 30x20 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12024 |  |  |  |  | CROSS SECTION DOOR RUBBER CLAMP PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 66.2-E12004 | [5 empty] | SLIDING ENTRANCE DOOR 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 66.2-E12005 | [5 empty] | HANGER SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | •
|  |  | 66.2-E12006 | [5 empty] | STOPPER SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | •
|  |  | 66.2-E12045 | [5 empty] | SPACER PLATE FOR BOLT | Interior | • | • | • | • | • | • | • | A3 | 4 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  | 66.2-E12101 - PI | [6 empty] | FITTING CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-11 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 66.2-E12103 | [5 empty] | CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12035 |  |  |  |  | GLASS CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12036 |  |  |  |  | CABIN SLIDING PARTITION DOOR WINDOW OUTER MOULDING | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12020 |  |  |  | CROSS SECTION DOOR WINDOW OUTER MOULDING | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12037 |  |  |  |  | CABIN SLIDING PARTITION DOOR WINDOW INNER MOULDING | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12021 |  |  |  | CROSS SECTION DOOR WINDOW INNER MOULDING | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12038 |  |  |  |  | CABIN SLIDING PARTITION DOOR WINDOW RUBBER | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12018 |  |  |  |  | BOTTOM GUIDE SLIDING ENTRANCE DOOR | Interior | • | [5 empty] | • | [21 empty] | OPEN
|  |  |  | 66.2-E12121 |  |  |  |  | RUBBER CABIN SLIDING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12043 |  |  |  | CROSS SECTION RUBBER CABIN SLIDING DOOR | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 65.1-L10040 |  |  |  |  | LOCKING DEVICE SLIDING DOOR | Interior | • | [5 empty] | •
|  |  |  | 55.3-E12118 |  |  |  |  | CROSS SECTION HOLLOW PROFILE 30x20 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12024 |  |  |  |  | CROSS SECTION DOOR RUBBER CLAMP PROFILE | Interior | • | [5 empty] | • | [21 empty] | OPEN
|  |  | 66.2-E12104 | [5 empty] | TOP RAIL CABIN SLIDING PARTITION DOOR (INCLUDE PART NO IGUS) | Interior | • | [5 empty] | •
|  |  | 66.2-E12105 | [5 empty] | TOP GUIDE CABIN SLIDING PARTITION DOOR (INCLUDE PART NO IGUS) | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12106 | [5 empty] | BOTTOM RAIL CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  | 66.2-E12107 | [5 empty] | STOPPER CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  | 66.2-E12108 | [5 empty] | HANGER CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  | 66.2-E12109 | [5 empty] | FOLLOWER PLATE CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  | 66.2-E12110 | [5 empty] | BRACKET TOP RAIL CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  | 66.2-E12111 | [5 empty] | MOULDING CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  |  | 66.2-E12122 |  |  |  |  | RUBBER MOULDING CABIN SLIDING DOOR | Interior | • | [5 empty] | •
|  |  | 66.2-E12112 | [5 empty] | RAIL HANGER CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  |  | 65.1-A72017 |  |  |  |  | ALUMUNIUM EXTRUSION 3 | Interior | • | [5 empty] | •
|  |  | 66.2-E12113 | [5 empty] | DOOR LINTEL CABIN SLIDING PARTITION DOOR | Interior | • | [5 empty] | •
|  |  |  | 65.1-A72018 |  |  |  |  | ALUMUNIUM EXTRUSION 4 | Interior | • | [5 empty] | •
|  |  | 66.2-K56012 | [5 empty] | DOOR CLOSER SLIDING PARTITION DOOR CONTROL ROOM | Interior | • | [5 empty] | •
|  | 66.2-E12125 - PI | [6 empty] | FITTING GANGWAY SLIDING DOOR (TC) | Interior | • | [5 empty] | • |  | 1 | A3 | A | 2024-03-04 | 2024-04-18 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 66.2-E12025 - PI | [6 empty] | FITTING GANGWAY SLIDING DOOR (M&T) | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-03-04 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 66.2-E12026 | [5 empty] | GANGWAY SLIDING DOOR 1 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12039 |  |  |  |  | GLASS GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12040 |  |  |  |  | GANGWAY SLIDING DOOR WINDOW OUTER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12020 |  |  |  | CROSS SECTION DOOR WINDOW OUTER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12041 |  |  |  |  | GANGWAY SLIDING DOOR WINDOW INNER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12021 |  |  |  | CROSS SECTION DOOR WINDOW INNER MOULDING | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12042 |  |  |  |  | GANGWAY SLIDING DOOR WINDOW RUBBER | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12018 |  |  |  |  | BOTTOM GUIDE SLIDING ENTRANCE DOOR | Interior | • | • | • | • | • | • | • | [21 empty] | OPEN
|  |  |  | 66.2-E12123 |  |  |  |  | RUBBER GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 66.2-E12043 |  |  |  | CROSS SECTION RUBBER CABIN SLIDING DOOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 65.1-L10040 |  |  |  |  | LOCKING DEVICE SLIDING DOOR | Interior | • | • | • | • | • | • | •
|  |  |  | 55.3-E12118 |  |  |  |  | CROSS SECTION HOLLOW PROFILE 30x20 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.2-E12024 |  |  |  |  | CROSS SECTION DOOR RUBBER CLAMP PROFILE | Interior | • | • | • | • | • | • | • | [21 empty] | OPEN
|  |  | 66.2-E12044 | [5 empty] | GANGWAY SLIDING DOOR 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  | 66.2-E12027 | [5 empty] | TOP RAIL GANGWAY SLIDING DOOR (INCLUDE PART NO IGUS) | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12105 | [5 empty] | TOP GUIDE CABIN SLIDING PARTITION DOOR (INCLUDE PART NO IGUS) | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12028 | [5 empty] | BOTTOM RAIL GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12029 | [5 empty] | STOPPER GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12030 | [5 empty] | HANGER GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12031 | [5 empty] | FOLLOWER PLATE GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12032 | [5 empty] | BRACKET TOP RAIL GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12033 | [5 empty] | MOULDING GANGWAY SLIDING DOOR | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-22 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | AZA | APK | EKN
|  |  |  | 66.2-E12124 |  |  |  |  | RUBBER MOULDING GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 66.2-E12034 | [5 empty] | DOOR CLOSER GANGWAY SLIDING DOOR | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  | 66.5-E12101 - PI | [6 empty] | FITTING SLIDING WINDOW (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 66.5-E12029 - PI | [6 empty] | FITTING SLIDING WINDOW (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 66.5-E12001 | [5 empty] | DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12003 |  |  |  |  | OUTER FRAME DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12015 |  |  |  | CROSS SECTION OUTER FRAME SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12004 |  |  |  |  | DOUBLE SLIDING WINDOW RAIL | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12016 |  |  |  | CROSS SECTION SLIDING WINDOW RAIL PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12005 |  |  |  |  | GLASS HOLDER DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12017 |  |  |  | CROSS SECTION GLASS HOLDER SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12028 |  |  |  | CROSS SECTION HANDLE GLASS HOLDER SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12006 |  |  |  |  | GLASS DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12007 |  |  |  |  | MID PILLAR DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12018 |  |  |  | CROSS SECTION MID PILLAR DOUBLE SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.5-E12008 |  |  |  |  | SPIRAL BALANCER (INCLUDE PART SPEC CALDWELL & RETAINER) | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12009 |  |  |  |  | DRAIN BOX DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12019 |  |  |  | DRAIN BOX PLATE DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12020 |  |  |  | DRAIN BOX COVER DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12021 |  |  |  | RAIL ON DRAIN BOX DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[6 empty] | 67.3-E12002 |  |  | CROSS SECTION SLOT FOR M8 BOLT | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12022 |  |  |  | RUBBER DRAIN BOX DOUBLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[6 empty] | 55.8-E12115 |  |  | CROSS SECTION RUBBER SWING DOOR 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12009 |  |  |  | CROSS SECTION L PROFILE 20x20 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.5-E12027 |  |  |  |  | BALL CATCHES (INCLUDE PART NO & SPEC MISUMI) | Interior | • | • | • | • | • | • | •
|  |  | 66.5-E12002 | [5 empty] | SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12010 |  |  |  |  | OUTER FRAME SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12015 |  |  |  | CROSS SECTION OUTER FRAME SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12011 |  |  |  |  | SINGLE SLIDING WINDOW RAIL | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12016 |  |  |  | CROSS SECTION SLIDING WINDOW RAIL PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12012 |  |  |  |  | GLASS HOLDER SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12017 |  |  |  | CROSS SECTION GLASS HOLDER SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12028 |  |  |  | CROSS SECTION HANDLE GLASS HOLDER SLIDING WINDOW PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12013 |  |  |  |  | GLASS SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12008 |  |  |  |  | SPIRAL BALANCER (INCLUDE PART SPEC CALDWELL & RETAINER) | Interior | • | • | • | • | • | • | •
|  |  |  | 66.5-E12014 |  |  |  |  | DRAIN BOX SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12023 |  |  |  | DRAIN BOX PLATE SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12024 |  |  |  | DRAIN BOX COVER SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12025 |  |  |  | RAIL ON DRAIN BOX SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[6 empty] | 67.3-E12002 |  |  | CROSS SECTION SLOT FOR M8 BOLT | Interior | • | • | • | • | • | • | •
[5 empty] | 66.5-E12026 |  |  |  | RUBBER DRAIN BOX SINGLE SLIDING WINDOW | Interior | • | • | • | • | • | • | •
[6 empty] | 55.8-E12115 |  |  | CROSS SECTION RUBBER SWING DOOR 2 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12009 |  |  |  | CROSS SECTION L PROFILE 20x20 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 66.5-E12027 |  |  |  |  | BALL CATCHES (INCLUDE PART NO & SPEC MISUMI) | Interior | • | • | • | • | • | • | •
| 67.0-E12101 - PI | [7 empty] | ARRANGEMENT CEILING PANEL (TC) | Interior | • | [5 empty] | •
| 67.0-E12001 - PI | [7 empty] | ARRANGEMENT CEILING PANEL (M&T) | Interior |  | • | • | • | • | •
|  | 67.1-E12101 - PI | [6 empty] | FITTING CEILING PANEL PASSENGER AREA (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 67.1-E12032 - PI | [6 empty] | FITTING CEILING PANEL PASSENGER AREA (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 67.1-E12103 - PI | [5 empty] | ARRANGEMENT CEILING PANEL PASSENGER AREA (TC) | Interior | • | [5 empty] | •
|  |  | 67.1-E12043 - PI | [5 empty] | ARRANGEMENT CEILING PANEL PASSENGER AREA (M&T) | Interior |  | • | • | • | • | •
|  |  |  | 67.1-E12003 |  |  |  |  | SIDE CEILING PANEL 1 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.2-G14051 |  |  |  | CROSS SECTION HOLLOW PROFILE 8x30 | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12017 |  |  |  | CROSS SECTION PANEL HOLDER PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12030 |  |  |  | CROSS SECTION PANEL MOUNTING PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12004 |  |  |  |  | SIDE CEILING PANEL 2 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12005 |  |  |  |  | SIDE CEILING PANEL 3 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12006 |  |  |  |  | SIDE CEILING PANEL 4 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 67.1-E12015 |  |  |  | COVER MAINTENANCE RUNNING TEXT EXTERIOR | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12007 |  |  |  |  | SIDE CEILING PANEL 5 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12034 |  |  |  |  | SIDE CEILING PANEL 6 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12037 |  |  |  |  | SIDE CEILING PANEL 7 PASSENGER AREA | Interior |  | • | • | • | • | • | [18 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12035 |  |  |  |  | SIDE CEILING PANEL 8 PASSENGER AREA (TAMBAHAN) | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12036 |  |  |  |  | SIDE CEILING PANEL 9 PASSENGER AREA (TAMBAHAN) | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12044 |  |  |  |  | SIDE CEILING PANEL 10 PASSENGER AREA (TAMBAHAN) | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12009 |  |  |  |  | MID CEILING PANEL 1 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 64.1-E12015 |  |  |  | CROSS SECTION RUBBER SPACER WINDOW MOULDING PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 67.1-E12016 |  |  |  | DIFFUSER AC 1 | Interior | • | • | • | • | • | • | •
[6 empty] | 67.1-E12022 |  |  | CROSS SECTION DIFFUSER AC PROFILE | Interior | • | • | • | • | • | • | •
[6 empty] | 67.1-E12023 |  |  | CROSS SECTION RUBBER DIFFUSER AC | Interior | • | • | • | • | • | • | •
[5 empty] | 67.1-E12018 |  |  |  | MID CEILING GRILL | Interior | • | • | • | • | • | • | •
[6 empty] | 67.1-E12024 |  |  | CROSS SECTION CEILING GRILL PROFILE | Interior | • | • | • | • | • | • | •
[6 empty] | 67.1-E12030 |  |  | CROSS SECTION HOLDER GRILL PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12010 |  |  |  |  | MID CEILING PANEL 2 PASSENGER AREA | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12106 |  |  |  |  | SIDE CEILING PANEL 1 PASSENGER AREA (TC) | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12107 |  |  |  |  | SIDE CEILING PANEL 2 PASSENGER AREA (TC) | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12108 |  |  |  |  | SIDE CEILING PANEL 3 PASSENGER AREA (TC) (TAMBAHAN) | Interior | • | [5 empty] | •
|  |  |  | 67.1-E12109 |  |  |  |  | SIDE CEILING PANEL 4 PASSENGER AREA (TC) (TAMBAHAN) | Interior | • | [5 empty] | •
|  |  |  | 67.1-E12110 |  |  |  |  | MID CEILING PANEL 1 PASSENGER AREA (TC) | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12111 |  |  |  |  | MID CEILING PANEL 2 PASSENGER AREA (TC) | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12112 |  |  |  |  | MID CEILING PANEL 3 PASSENGER AREA (TC) | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 67.1-E12119 |  |  |  | DIFFUSER AC 1 (TC) | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12122 |  |  |  |  | MID CEILING PANEL 4 PASSENGER AREA (TC) | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 67.1-E12019 |  |  |  | DIFFUSER AC 2 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12008 |  |  |  |  | MAINTENANCE COVER ROLL FILTER RETURN AIR (PINDAHAN) | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12025 |  |  |  |  | MOULDING GAP CEILING 1 | Interior | • | • | • | • | • | • | •
[5 empty] | 67.1-E12020 |  |  |  | CROSS SECTION MOULDING GAP PROFILE | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
|  |  |  | 67.1-E12027 |  |  |  |  | EDGE COVER SIDE CEILING PANEL 1 | Interior | • | • | • | • | • | • | •
[5 empty] | 67.1-E12029 |  |  |  | CROSS SECTION EDGE COVER PROFILE | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12028 |  |  |  |  | EDGE COVER SIDE CEILING PANEL 2 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12031 |  |  |  |  | MAINTENANCE COVER AC PANEL | Interior |  | • | • | • | • | •
|  | 67.1-E12102 - PI | [6 empty] | FITTING DOOR LINTEL (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  | 67.1-E12033 - PI | [6 empty] | FITTING DOOR LINTEL (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 67.1-E12001 | [5 empty] | DOOR LINTEL 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12011 |  |  |  |  | DOOR LINTEL PANEL 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12012 |  |  |  |  | COVER EMERGENCY DOOR RELEASE DOOR LINTEL | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12013 |  |  |  |  | EDGE BRUSH DOOR LINTEL | Interior | • | • | • | • | • | • | •
[5 empty] | 67.1-E12021 |  |  |  | CROSS SECTION EDGE BRUSH | Interior | • | • | • | • | • | • | •
|  |  | 67.1-E12002 | [5 empty] | GAS SPRING DOOR LINTEL | Interior | • | • | • | • | • | • | •
|  |  | 67.1-E12038 | [5 empty] | DOOR LINTEL 2 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12040 |  |  |  |  | DOOR LINTEL PANEL 2 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12041 |  |  |  |  | COVER MAINTENANCE ACCESS DOOR LINTEL | Interior | • | • | • | • | • | • | •
|  |  | 67.1-E12039 | [5 empty] | DOOR LINTEL 3 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12042 |  |  |  |  | DOOR LINTEL PANEL 3 | Interior | • | • | • | • | • | • | •
|  |  | 67.1-E12104 | [5 empty] | DOOR LINTEL 1 (TC) | Interior | • | [5 empty] | •
|  |  |  | 67.1-E12116 |  |  |  |  | DOOR LINTEL PANEL 1 (TC) | Interior | • | [5 empty] | •
|  |  |  | 67.1-E12117 |  |  |  |  | EDGE BRUSH DOOR LINTEL | Interior | • | [5 empty] | •
|  |  | 67.1-E12105 | [5 empty] | DOOR LINTEL 2 (TC) | Interior | • | [5 empty] | •
|  |  |  | 67.1-E12118 |  |  |  |  | DOOR LINTEL PANEL 2 (TC) | Interior | • | [5 empty] | •
|  | 67.2-E12101 - PI | [6 empty] | ARRANGEMENT COMPONENT ON CEILING (TC) | Interior | • | [5 empty] | •
|  | 67.2-E12011 - PI | [6 empty] | ARRANGEMENT COMPONENT ON CEILING (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12102 - PI | [5 empty] | FITTING CEILING LAMP PASSENGER AREA (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 67.2-E12012 - PI | [5 empty] | FITTING CEILING LAMP PASSENGER AREA (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-07-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  |  | 67.2-E12001 |  |  |  |  | CEILING LAMP LED TUBE | Interior | • | • | • | • | • | • | •
[5 empty] | 64.2-G14052 |  |  |  | CROSS SECTION LAMP LED TUBE | Interior | • | • | • | • | • | • | •
[5 empty] | 64.2-G14053 |  |  |  | END CAP CEILING LAMP 1 | Interior | • | • | • | • | • | • | •
[5 empty] | 64.2-G14054 |  |  |  | END CAP CEILING LAMP 2 | Interior | • | • | • | • | • | • | •
|  |  | 67.2-E12103 - PI | [5 empty] | FITTING SPEAKER PASSENGER AREA (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12013 - PI | [5 empty] | FITTING SPEAKER PASSENGER AREA (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12104 - PI | [5 empty] | FITTING CCTV PASSENGER AREA (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12014 - PI | [5 empty] | FITTING CCTV PASSENGER AREA (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12105 - PI | [5 empty] | FITTING SMOKE DETECTOR PASSENGER AREA (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12015 - PI | [5 empty] | FITTING SMOKE DETECTOR PASSENGER AREA (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12106 - PI | [5 empty] | FITTING TANGENTIAL FAN (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 67.2-E12016 - PI | [5 empty] | FITTING TANGENTIAL FAN (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 67.2-E12027 |  |  |  |  | BOX TANGENTIAL FAN | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12028 |  |  |  |  | BRACKET TANGENTIAL FAN | Interior | • | • | • | • | • | • | •
|  |  | 67.2-E12108 | [5 empty] | FITTING TOP HANDRAIL & HANDGRIP (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 67.2-E12018 | [5 empty] | FITTING TOP HANDRAIL & HANDGRIP (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 67.2-E12003 |  |  |  |  | PIPE HANDRAIL 1 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12004 |  |  |  |  | PIPE HANDRAIL 2 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12118 |  |  |  |  | PIPE HANDRAIL 3 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12009 |  |  |  |  | PIPE HANDRAIL 4 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12010 |  |  |  |  | PIPE HANDRAIL 5 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12036 |  |  |  |  | PIPE HANDRAIL 6 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12119 |  |  |  |  | PIPE HANDRAIL 1 (TC) | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12120 |  |  |  |  | PIPE HANDRAIL 2 (TC) | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12005 |  |  |  |  | HANDGRIP 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12006 |  |  |  |  | HANDGRIP 2 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.3-G13007 |  |  |  |  | JOINT 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.3-G13008 |  |  |  |  | JOINT 2 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12033 |  |  |  |  | PACKING PLATE 1 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12034 |  |  |  |  | PACKING PLATE 2 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12035 |  |  |  |  | PACKING PLATE 3 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12128 |  |  |  |  | PACKING PLATE 1 (TC) | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-E12129 |  |  |  |  | PACKING PLATE 2 (TC) | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-07-16 | [12 empty] | CLOSED | N/A | CLOSED | N/A |  |  | IZA | APK | EKN
|  |  | 67.2-E12109 - PI | [5 empty] | FITTING EMERGENCY DOOR RELEASE ON DOOR LINTEL (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12019 - PI | [5 empty] | FITTING EMERGENCY DOOR RELEASE ON DOOR LINTEL (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12110 - PI | [5 empty] | FITTING DOOR INSULATION BUTTON (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12020 - PI | [5 empty] | FITTING DOOR INSULATION BUTTON (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12111 - PI | [5 empty] | FITTING PAS MONITOR (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | [13 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 67.2-E12021 - PI | [5 empty] | FITTING PAS MONITOR (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12112 - PI | [5 empty] | FITTING ENTRANCE DOOR BUZZER (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12022 - PI | [5 empty] | FITTING ENTRANCE DOOR BUZZER (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12113 - PI | [5 empty] | FITTING ENTRANCE DOOR INDICATOR LAMP (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12023 - PI | [5 empty] | FITTING ENTRANCE DOOR INDICATOR LAMP (M&T) | Interior |  | • | • | • | • | •
|  |  | 67.2-E12114 - PI | [5 empty] | FITTING DUCTING AC (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-16 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 67.2-E12024 - PI | [5 empty] | FITTING DUCTING AC (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-16 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 67.2-E12007 |  |  |  |  | DUCTING AC 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12008 |  |  |  |  | DUCTING AC 2 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12122 |  |  |  |  | DUCTING AC 1 (TC) | Interior | • | [5 empty] | •
|  |  |  | 67.2-E12123 |  |  |  |  | DUCTING AC 2 (TC) | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12124 |  |  |  |  | DUCTING AC 3 (TC) | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12125 |  |  |  |  | DUCTING AC 4 (TC) | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12126 |  |  |  |  | DUCTING AC 5 (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12130 - PI | [5 empty] | FITTING HARTING CONNECTION AC (TC) | Interior | • | [5 empty] | •
|  |  | 67.2-E12026 - PI | [5 empty] | FITTING HARTING CONNECTION AC (M&T) | Interior |  | • | • | • | • | •
|  |  |  | 672E1202900 |  |  |  |  | BRACKET HARTING CONNECTION AC | Interior | • | • | • | • | • | • | •
|  |  | 67.2-E12030 - PI | [5 empty] | FITTING PANEL AC | Interior | • | • | • | • | • | • | •
|  |  | 67.2-E12031 - PI | [5 empty] | FITTING HDMI SPLITTER | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12032 |  |  |  |  | BRACKET HDMI SPLITTER | Interior | • | • | • | • | • | • | •
|  |  | 67.2-E12037 - PI | [5 empty] | FITTING SENSOR TEMPERATURE & HUMIDITY | Interior | • | • | • | • | • | • | •
|  |  |  | 67.2-E12038 |  |  |  |  | BRACKET SENSOR TEMPERATURE & HUMIDITY | Interior | • | • | • | • | • | • | •
|  | 67.3-E12101 - PI | [6 empty] | FITTING SLOT FOR M8 BOLT (TC) | Interior | • | [5 empty] | • | A3 |  | 0 | 0 | 2024-03-22 | 2024-07-09 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  | 67.3-E12013 - PI | [6 empty] | FITTING SLOT FOR M8 BOLT (M&T) | Interior |  | • | • | • | • | • |  | A3 |  | 0 | 0 | 2024-05-22 | 2024-07-02 | [11 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  | 67.3-E12001 | [5 empty] | SLOT FOR M8 BOLT 1 | Interior | • | • | • | • | • | • | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.3-E12002 |  |  |  |  | CROSS SECTION SLOT FOR M8 BOLT | Interior | • | • | • | • | • | • | • | [20 empty] | N/A
|  |  | 67.3-E12008 | [5 empty] | SLOT FOR M8 BOLT 2 | Interior |  | • | • | • | • | • |  | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 67.3-E12102 | [5 empty] | SLOT FOR M8 BOLT 1 (TC) | Interior | • | [5 empty] | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 67.3-E12005 | [5 empty] | SLOT FOR M8 BOLT 2 (TC) | Interior | • | [5 empty] | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 67.3-E12006 | [5 empty] | SLOT FOR M8 BOLT 3 (TC) | Interior | • | • | • | • | • | • | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 67.3-E12007 | [5 empty] | SLOT FOR M8 BOLT 4 (TC) | Interior | • | • | • | • | • | • | • | A3 | 1 | 0 | 0 | 2024-05-05 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  | 67.3-E12103 - PI | [6 empty] | FITTING FRAME CEILING (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  | 67.3-E12014 - PI | [6 empty] | FITTING FRAME CEILING (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 67.3-E12003 | [5 empty] | FRAME CEILING 1 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12004 | [5 empty] | FRAME CEILING 2 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12005 | [5 empty] | FRAME CEILING 3 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12006 | [5 empty] | FRAME CEILING 4 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12007 | [5 empty] | FRAME CEILING 5 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12008 | [5 empty] | FRAME CEILING 6 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12009 | [5 empty] | FRAME CEILING 7 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12010 | [5 empty] | FRAME CEILING 8 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12011 | [5 empty] | FRAME CEILING 9 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12012 | [5 empty] | FRAME CEILING 10 | Interior | • | • | • | • | • | • | •
|  |  | 67.3-E12015 | [5 empty] | FRAME CEILING 11 | Interior |  | • | • | • | • | •
|  |  | 67.3-E12016 | [5 empty] | FRAME CEILING 12 | Interior |  | • | • | • | • | •
|  |  | 67.3-E12017 | [5 empty] | FRAME CEILING 13 | Interior |  | • | • | • | • | •
|  |  | 67.3-E12018 | [5 empty] | FRAME CEILING 14 | Interior |  | • | • | • | • | •
|  |  | 67.3-E12104 | [5 empty] | FRAME CEILING 1 (TC) | Interior | • | [5 empty] | •
|  |  | 67.3-E12105 | [5 empty] | FRAME CEILING 2 (TC) | Interior | • | [5 empty] | •
|  |  | 67.3-E12106 | [5 empty] | FRAME CEILING 3 (TC) | Interior | • | [5 empty] | •
|  |  | 67.3-E12107 | [5 empty] | FRAME CEILING 4 (TC) | Interior | • | [5 empty] | •
| 73.0-E12101 - PI | [7 empty] | ARRANGEMENT PASSENGER COMPARTMENT (TC) | Interior | • | [5 empty] | •
| 73.0-E12001 - PI | [7 empty] | ARRANGEMENT PASSENGER COMPARTMENT (M&T) | Interior |  | • | • | • | • | •
|  | 73.1-E12101 - PI | [6 empty] | FITTING PASSENGER SEAT (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  | 73.1-E12017 - PI | [6 empty] | FITTING PASSENGER SEAT (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 73.1-E12001 | [5 empty] | PASSENGER SEAT 7 SEATER | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12020 |  |  |  |  | FRAME SEAT 3 SEATER | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12106 |  |  |  |  | FRAME SEAT 4 SEATER | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12006 |  |  |  |  | COVER PLATE 1 SEAT 7 SEATER | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12008 |  |  |  |  | COVER PLATE 2 SEAT 7 SEATER | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12009 |  |  |  |  | COVER PLATE 3 SEAT 7 SEATER | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12007 |  |  |  |  | BOTTOM REST CUSHION 4 SEAT | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12012 |  |  |  |  | BOTTOM REST CUSHION 3 SEAT | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12011 |  |  |  |  | BACK REST CUSHION 4 SEAT | Interior | • | • | • | • | • | • | •
|  |  |  | 73.1-E12014 |  |  |  |  | BACK REST CUSHION 3 SEAT | Interior | • | • | • | • | • | • | •
|  |  | 73.1-E12104 | [5 empty] | PASSENGER SEAT 4 SEATER | Interior | • | [5 empty] | •
|  |  |  | 73.1-E12106 |  |  |  |  | FRAME SEAT 4 SEATER | Interior | • | [5 empty] | •
|  |  |  | 73.1-E12107 |  |  |  |  | COVER PLATE 1 SEAT 4 SEATER | Interior | • | [5 empty] | •
|  |  |  | 73.1-E12108 |  |  |  |  | COVER PLATE 2 SEAT 4 SEATER | Interior | • | [5 empty] | •
|  |  |  | 73.1-E12111 |  |  |  |  | COVER PLATE 3 SEAT 4 SEATER | Interior | • | [5 empty] | •
|  |  |  | 73.1-E12007 |  |  |  |  | BOTTOM REST CUSHION 4 SEAT | Interior | • | [5 empty] | •
|  |  |  | 73.1-E12011 |  |  |  |  | BACK REST CUSHION 4 SEAT | Interior | • | [5 empty] | •
|  |  | 73.1-E12204 | [5 empty] | PASSENGER SEAT 3 SEATER | Interior |  | • | • | • | • | •
|  |  |  | 73.1-E12020 |  |  |  |  | FRAME SEAT 3 SEATER | Interior |  | • | • | • | • | •
|  |  |  | 73.1-E12021 |  |  |  |  | COVER PLATE 1 SEAT 3 SEATER | Interior |  | • | • | • | • | •
|  |  |  | 73.1-E12026 |  |  |  |  | COVER PLATE 2 SEAT 3 SEATER | Interior |  | • | • | • | • | •
|  |  |  | 73.1-E12023 |  |  |  |  | COVER PLATE 3 SEAT 3 SEATER | Interior |  | • | • | • | • | •
|  |  |  | 73.1-E12012 |  |  |  |  | BOTTOM REST CUSHION 3 SEAT | Interior |  | • | • | • | • | •
|  |  |  | 73.1-E12014 |  |  |  |  | BACK REST CUSHION 3 SEAT | Interior |  | • | • | • | • | •
|  |  | 73.1-E12112 - PI | [5 empty] | FITTING SEAT PARTITION (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 73.1-E12029 - PI | [5 empty] | FITTING SEAT PARTITION (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 73.1-E12015 |  |  |  |  | SEAT PARTITION 1 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 73.1-E12016 |  |  |  |  | SEAT PARTITION 2 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  | 73.2-E12101 - PI | [6 empty] | ARRANGEMENT MISCELLANOUS PART (TC) | Interior | • | [5 empty] | •
|  | 73.2-E12003 - PI | [6 empty] | ARRANGEMENT MISCELLANOUS PART (M&T) | Interior |  | • | • | • | • | •
|  |  | 73.2-E12102 - PI | [5 empty] | FITTING JANITOR CABINET | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED |  | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  |  | 73.2-E12106 |  |  |  |  | JANITOR CABINET 1 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 55.3-E12115 |  |  |  | CROSS SECTION PARTITION PANEL HOLDER 1 | Interior | • | [5 empty] | •
[5 empty] | 55.3-E12116 |  |  |  | CROSS SECTION PARTITION PANEL HOLDER 2 | Interior | • | [5 empty] | •
[5 empty] | 55.3-E12117 |  |  |  | CROSS SECTION DOOR PANEL HOLDER | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 55.3-E12118 |  |  |  | CROSS SECTION HOLLOW PROFILE 30x20 | Interior | • | [5 empty] | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 73.2-E12111 |  |  |  | SIDE PANEL 1 JANITOR CABINET | Interior | • | [5 empty] | •
[5 empty] | 73.2-E12112 |  |  |  | SIDE PANEL 2 JANITOR CABINET | Interior | • | [5 empty] | •
[5 empty] | 73.2-E12113 |  |  |  | FRONT PANEL 1 JANITOR CABINET | Interior | • | [5 empty] | •
[5 empty] | 73.2-E12114 |  |  |  | REAR PANEL JANITOR CABINET | Interior | • | [5 empty] | •
[5 empty] | 73.2-E12115 |  |  |  | FRAME & BRACKET JANITOR CABINET | Interior | • | [5 empty] | •
[5 empty] | 73.2-E12116 |  |  |  | DOOR PANEL 1 JANITOR CABINET | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 73.2-E12117 |  |  |  | DOOR PANEL 2 JANITOR CABINET | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 73.2-E12118 |  |  |  | TOP PANEL JANITOR CABINET 1 | Interior | • | [5 empty] | •
[5 empty] | 73.2-E12122 |  |  |  | TOP COVER JANITOR CABINET 1 | Interior | • | [5 empty] | •
[5 empty] | 73.2-E12123 |  |  |  | FRONT PANEL 2 JANITOR CABINET | Interior | • | [5 empty] | • |  | 1 | A3 | A | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 73.2-E12124 |  |  |  | FRONT PANEL 3 JANITOR CABINET | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 73.2-E12107 |  |  |  |  | JANITOR CABINET 2 | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 73.2-E12119 |  |  |  | DOOR PANEL 3 JANITOR CABINET | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
[5 empty] | 73.2-E12120 |  |  |  | DOOR PANEL 4 JANITOR CABINET | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 73.2-E12103 - PI | [5 empty] | FITTING EMERGENCY DOOR RELEASE BUTTON (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 73.2-E12005 - PI | [5 empty] | FITTING EMERGENCY DOOR RELEASE BUTTON (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 73.2-E12001 |  |  |  |  | BOX EMERGENCY DOOR RELEASE BUTTON | Interior | • | • | • | • | • | • | •
|  |  |  | 73.2-E12002 |  |  |  |  | COVER EMERGENCY DOOR RELEASE BUTTON | Interior | • | • | • | • | • | • | •
|  |  | 73.2-E12104 - PI | [5 empty] | FITTING FIRST AID KIT (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | EPP | APK | EKN
|  |  | 73.2-E12006 - PI | [5 empty] | FITTING FIRST AID KIT (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-07-02 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | ARB | APK | EKN
|  |  |  | 73.2-E12108 |  |  |  |  | BOX FIRST AID KIT | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 73.2-E12105 - PI | [5 empty] | FITTING EMERGENCY LADDER | Interior | • | [5 empty] | •
|  |  |  | 73.2-E12109 |  |  |  |  | EMERGENCY LADDER | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-03-15 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 73.2-E12110 |  |  |  |  | HOLDER EMERGENCY LADDER | Interior | • | [5 empty] | •
|  | 73.3-E12101 - PI | [6 empty] | FITTING TOP LUGGAGE RACK (TC) | Interior | • | [5 empty] | • | A3 | 1 | A3 | 0 | 2024-05-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  | 73.3-E12007 - PI | [6 empty] | FITTING TOP LUGGAGE RACK (M&T) | Interior |  | • | • | • | • | • |  | A3 | 1 | A3 | 0 | 2024-05-21 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 73.3-E12001 | [5 empty] | TOP LUGGAGE RACK 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 73.3-E12002 |  |  |  |  | FRAME 1 TOP LUGGAGE RACK | Interior | • | • | • | • | • | • | •
|  |  |  | 73.3-E12003 |  |  |  |  | FRAME 2 TOP LUGGAGE RACK | Interior | • | • | • | • | • | • | •
|  |  |  | 73.3-E12004 |  |  |  |  | END CAP 2 TOP LUGGAGE RACK | Interior | • | • | • | • | • | • | •
|  |  |  | 73.3-E12005 |  |  |  |  | COVER PLATE 1 TOP LUGGAGE RACK | Interior | • | • | • | • | • | • | •
|  |  |  | 73.3-E12006 |  |  |  |  | END CAP 1 TOP LUGGAGE RACK | Interior | • | • | • | • | • | • | •
|  |  | 73.3-E12102 | [5 empty] | TOP LUGGAGE RACK 2 | Interior | • | [5 empty] | •
|  |  |  | 73.3-E12104 |  |  |  |  | COVER PLATE 2 TOP LUGGAGE RACK | Interior | • | [5 empty] | •
| 75.0-E12101 - PI | [7 empty] | ARRANGEMENT MOULDING & SILL PLATE (TC) | Interior | • | [5 empty] | •
| 75.0-E12001 - PI | [7 empty] | ARRANGEMENT MOULDING & SILL PLATE (M&T) | Interior |  | • | • | • | • | •
|  | 75.1-E12101 - PI | [6 empty] | FITTING SILL PLATE SLIDING ENTRANCE DOOR (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  | 75.1-E12003 - PI | [6 empty] | FITTING SILL PLATE SLIDING ENTRANCE DOOR (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-07-10 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 75.1-E12001 | [5 empty] | SILL PLATE SLIDING ENTRANCE DOOR 1 | Interior | • | • | • | • | • | • | •
|  |  | 75.1-E12002 | [5 empty] | SILL PLATE SLIDING ENTRANCE DOOR 2 | Interior | • | • | • | • | • | • | •
|  |  | 75.1-E12004 | [5 empty] | SILL PLATE SLIDING ENTRANCE DOOR 3 | Interior | • | • | • | • | • | • | •
|  |  | 75.1-E12102 | [5 empty] | SILL PLATE SLIDING ENTRANCE DOOR 1 (TC) | Interior | • | [5 empty] | •
|  |  | 75.1-E12103 | [5 empty] | SILL PLATE SLIDING ENTRANCE DOOR 2 (TC) | Interior | • | [5 empty] | •
|  | 75.2-E12101 - PI | [6 empty] | FITTING MOULDING DOOR POST (TC) | Interior | • | [5 empty] | • | A3 | 4 | A3 | 0 | 2024-07-09 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  | 75.2-E12011 - PI | [6 empty] | FITTING MOULDING DOOR POST (M&T) | Interior |  | • | • | • | • | • |  | A3 | 4 | A3 | 0 | 2024-06-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | KRS | APK | EKN
|  |  | 75.2-E12001 | [5 empty] | MOULDING DOOR POST 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 67.1-E12021 |  |  |  |  | CROSS SECTION EDGE BRUSH | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12002 | [5 empty] | MOULDING DOOR POST 2 | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12014 | [5 empty] | MOULDING DOOR POST 3 | Interior | • | • | • | • | • | • | •
|  | 75.2-E12102 - PI | [6 empty] | FITTING MOULDING SIDEWALL (TC) | Interior | • | [5 empty] | •
|  | 75.2-E12012 - PI | [6 empty] | FITTING MOULDING SIDEWALL (M&T) | Interior |  | • | • | • | • | •
|  |  | 75.2-E12003 | [5 empty] | MOULDING SIDEWALL 1 | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12004 | [5 empty] | MOULDING SIDEWALL 2 | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12005 | [5 empty] | MOULDING SIDEWALL 3 | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12006 | [5 empty] | MOULDING SIDEWALL 4 | Interior | • | • | • | • | • | • | •
|  | 75.2-E12103 - PI | [6 empty] | FITTING MOULDING GANGWAY DOOR (TC) | Interior | • | [5 empty] | •
|  | 75.2-E12013 - PI | [6 empty] | FITTING MOULDING GANGWAY DOOR (M&T) | Interior |  | • | • | • | • | •
|  |  | 75.2-E12007 | [5 empty] | MOULDING GANGWAY DOOR 1 | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12008 | [5 empty] | MOULDING GANGWAY DOOR 2 | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12009 | [5 empty] | MOULDING GANGWAY DOOR 3 | Interior | • | • | • | • | • | • | •
|  |  | 75.2-E12010 | [5 empty] | MOULDING GANGWAY DOOR 4 | Interior | • | • | • | • | • | • | •
| 76.0-E12101 - PI | [7 empty] | ARRANGEMENT ENDWALL AREA (TC) | Interior | • | [5 empty] | •
| 76.0-E12001 - PI | [7 empty] | ARRANGEMENT ENDWALL AREA (M&T) | Interior |  | • | • | • | • | •
|  | 76.1-E12001 - PI | [6 empty] | FITTING DOOR LINTEL ENDWALL | Interior | • | • | • | • | • | • | •
|  |  | 76.1-E12007 | [5 empty] | PANEL DOOR LINTEL ENDWALL | Interior | • | [5 empty] | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 76.1-E12008 | [5 empty] | HANGER DOOR LINTEL | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-A72028 |  |  |  |  | PROFILE ALUMUNIUM EKSTRUSI 3 | Interior | • | • | • | • | • | • | •
|  |  | 76.1-E12009 | [5 empty] | ENDWALL DOOR LINTEL | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 65.1-A72018 |  |  |  |  | ALUMUNIUM EXTRUSION 4 | Interior | • | • | • | • | • | • | •
|  | 76.1-E12102 - PI | [6 empty] | FITTING ADDITIONAL FRAME GANGWAY (TC) -> perhatikan pemasangan di TC2 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-07-15 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 76.1-E12003 | [5 empty] | ADDITIONAL FRAME GANGWAY 1 | Interior | • | • | • | • | • | • | •
|  |  | 76.1-E12004 | [5 empty] | ADDITIONAL FRAME GANGWAY 2 | Interior | • | • | • | • | • | • | •
|  | 76.1-E12002 - PI | [6 empty] | FITTING ENDWALL PANEL | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-03-04 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 76.1-E12010 | [5 empty] | FRAME 1 FOR ENDWALL PANEL | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 76.1-E12011 | [5 empty] | FRAME 2 FOR ENDWALL PANEL | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 76.1-E12012 | [5 empty] | ENDWALL PANEL 1 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 76.1-E12013 | [5 empty] | ENDWALL PANEL 2 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 76.1-E12014 | [5 empty] | ENDWALL PANEL 3 | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 76.1-E12015 | [5 empty] | HANGER ENDWALL PANEL | Interior |  | • | • | • | • | • |  |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  |  | 67.2-A72028 |  |  |  |  | PROFILE ALUMUNIUM EKSTRUSI 3 | Interior |  | • | • | • | • | •
|  | 76.2-E12101 - PI | [6 empty] | ARRANGEMENT COMPONENT ON ENDWALL (TC) | Interior | • | [5 empty] | •
|  | 76.2-E12001 - PI | [6 empty] | ARRANGEMENT COMPONENT ON ENDWALL (M&T) | Interior |  | • | • | • | • | •
|  |  | 76.2-E12102 - PI | [5 empty] | FITTING ENDWALL CABINET (TC) | Interior | • | [5 empty] | • | A3 | 1 | A3 | 0 | 2024-07-11 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  | 76.2-E12002 - PI | [5 empty] | FITTING ENDWALL CABINET (M&T) | Interior |  | • | • | • | • | • |  | A3 | 1 | A3 | 0 | 2024-07-11 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | MRN | APK | EKN
|  |  |  | 76.2-E12005 |  |  |  |  | ENDWALL CABINET 1 | Interior | • | • | • | • | • | • | •
[5 empty] | 55.3-E12115 |  |  |  | CROSS SECTION PARTITION PANEL HOLDER 1 | Interior | • | • | • | • | • | • | •
[5 empty] | 55.3-E12116 |  |  |  | CROSS SECTION PARTITION PANEL HOLDER 2 | Interior | • | • | • | • | • | • | •
[5 empty] | 55.3-E12117 |  |  |  | CROSS SECTION DOOR PANEL HOLDER | Interior | • | • | • | • | • | • | • | [17 empty] | CLOSED |  | CLOSED | N/A
[5 empty] | 76.2-E12009 |  |  |  | SIDE PANEL 1 ENDWALL CABINET | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12018 |  |  |  | FRONT PANEL 1 ENDWALL CABINET | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12013 |  |  |  | DOOR PANEL 1 ENDWALL CABINET | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12015 |  |  |  | TOP PANEL ENDWALL CABINET 1 | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12019 |  |  |  | TOP COVER ENDWALL CABINET 1 | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12020 |  |  |  | FRONT PANEL 2 ENDWALL CABINET | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12021 |  |  |  | SIDE PANEL 3 ENDWALL CABINET | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12022 |  |  |  | FRAME & BRACKET ENDWALL PANEL | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12023 |  |  |  | REAR PANEL ENDWALL CABINET | Interior | • | • | • | • | • | • | •
|  |  |  | 76.2-E12104 |  |  |  |  | ENDWALL CABINET (TC) | Interior | • | [5 empty] | •
|  |  |  | 76.2-E12006 |  |  |  |  | ENDWALL CABINET 2 | Interior |  | • | • | • | • | •
[5 empty] | 76.2-E12010 |  |  |  | SIDE PANEL 2 ENDWALL CABINET | Interior | • | • | • | • | • | • | •
[5 empty] | 76.2-E12109 |  |  |  | DOOR PANEL ENDWALL CABINET (TC) | Interior | • | [5 empty] | •
[5 empty] | 76.2-E12114 |  |  |  | TOP PANEL ENDWALL CABINET 2 | Interior | • | [5 empty] | •
[5 empty] | 76.2-E12016 |  |  |  | TOP COVER ENDWALL CABINET 2 | Interior | • | [5 empty] | •
[5 empty] | 76.2-E12011 |  |  |  | FRONT PANEL 3 ENDWALL CABINET | Interior | • | [5 empty] | •
[5 empty] | 76.2-E12115 |  |  |  | SIDE PANEL 4 ENDWALL CABINET | Interior |  | • | • | • | • | •
[5 empty] | 76.2-E12113 |  |  |  | DOOR PANEL 2 ENDWALL CABINET | Interior |  | • | • | • | • | •
[5 empty] | 76.2-E12015 |  |  |  | TOP PANEL ENDWALL CABINET 1 | Interior |  | • | • | • | • | •
|  |  | 76.2-E12103 - PI | [5 empty] | FITTING BASE PLATE ENDWALL ELECTRIC CABINET (TC) | Interior | • | [5 empty] | •
|  |  | 76.2-E12003 - PI | [6 empty] | Interior |  | • | • | • | • | •
|  |  |  | 76.2-E12007 |  |  |  |  | BASE PLATE ENDWALL ELECTRIC CABINET 1 | Interior | • | • | • | • | • | • | •
|  |  |  | 76.2-E12008 |  |  |  |  | BASE PLATE ENDWALL ELECTRIC CABINET 2 | Interior | • | • | • | • | • | • | •
|  |  | 76.2-E12004 - PI | [5 empty] | FITTING INHIBIT DOOR SWITCH | Interior | • | • | • | • | • | • | •
|  |  | 99.0-E12005 | [5 empty] | BRACKET TOP RAIL | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12006 | [5 empty] | DOOR STOPPER | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12007 | [5 empty] | DOOR STOPPER 2 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12008 | [5 empty] | DOOR STOPPER 3 | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12009 | [5 empty] | HANGER DOOR ENTRANCE | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12010 | [5 empty] | PLATE HANGER DOOR ENTRANCE | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12011 | [5 empty] | SHIM PACKING | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12012 | [5 empty] | TOGGLE LATCH CLAMP | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-02-29 | [12 empty] | CLOSED | N/A | CLOSED | N/A
|  |  | 99.0-E12004 | [5 empty] | FITTING ENTRANCE DOOR PRESERIES (M) | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-07-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
|  |  | 99.0-E12020 | [5 empty] | FITTING ENTRANCE DOOR PRESERIES REKA | Interior | • | • | • | • | • | • | • |  | 1 | A3 | 0 | 2024-07-14 | [12 empty] | CLOSED | N/A | CLOSED | CLOSED |  |  | IZA | APK | EKN
ELECTRIC
|  | 593E12018 | [6 empty] | KONEKSI HEAD LAMP | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12019 | [6 empty] | KONEKSI FOG LAMP | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12020 | [6 empty] | KONEKSI FRONT WHITE SIGNAL LAMP | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12021 | [6 empty] | KONEKSI FRONT RED SIGNAL LAMP | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12111 | [6 empty] | KONEKSI SWITCH PANEL 1 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12112 | [6 empty] | KONEKSI SWITCH PANEL 2 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12113 | [6 empty] | KONEKSI SWITCH PANEL 3 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12115 | [6 empty] | KONEKSI SWITCH PANEL 5 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12116 | [6 empty] | KONEKSI SWITCH PANEL 6 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12117 | [6 empty] | KONEKSI SWITCH PANEL 7 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12118 | [6 empty] | KONEKSI SWITCH PANEL 8 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12119 | [6 empty] | KONEKSI SWITCH PANEL 9 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
|  | 593E12120 | [6 empty] | KONEKSI SWITCH PANEL 10 | Electric | [8 empty] | 2 |  | 0 | 2023-12-20 | [12 empty] | CLOSED |  | CLOSED
SPECIAL PROCESS
|  | 210E1210201 | [6 empty] | PROSES BLASTING & PRIMER WELDING UNDERFRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-18 | [14 empty] | CLOSED |  |  |  | AZA | APK | EKN
|  | 210E1210202 | [6 empty] | PROSES PENGECATAN PRIMER COMPLETED UNDERFRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-18 | [14 empty] | CLOSED |  |  |  | AZA | APK | EKN
|  | 211E1220101 | [6 empty] | PROSES BLASTING & PENGECATAN AREA YANG TERTUTUP KOMPONEN DRAFGEAR STOPER & END CENTERSILL | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-18 | [14 empty] | CLOSED |  |  |  | HAS | APK | EKN
|  | 212E1200101 | [6 empty] | PROSES BLASTING & PRIMER WELDING BOLSTER BAGIAN DALAM | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-18 | [14 empty] | CLOSED |  |  |  | HAS | APK | EKN
|  | 212K7200101 | [6 empty] | PROSES BLASTING DAN PRIMER INNER BOLSTER | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [16 empty] | Open |  | Open
|  | 210K7200101 | [6 empty] | PROSES BLASTING DAN PRIMER WELDING UNDEFRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [16 empty] | Open |  | Open
2 |  | 280E1210201 | [6 empty] | PROSES SURFACE PREPARATION INNER CARBODY | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-01 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | AZA | APK | EKN
3 |  | 280E1210202 | [6 empty] | PROSES PEMBERSIHAN "HEAT TINT" PADA CARBODY | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-14 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | FRA | APK | EKN
4 |  | 280E1210203 | [6 empty] | PROSES PRIMER INTERIOR CARBODY KRL KCI | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-18 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | HAS | APK | EKN
5 |  | 280E1210204 | [6 empty] | PROSES APLIKASI ANTISKID ROOF | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 21/1/2024 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | AZA | APK | EKN
6 |  | 280E1210205 | [6 empty] | FITTING SPINDLE PIN | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-02 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | FRA | APK | EKN
7 |  | 280E1210206 | [6 empty] | PENGERJAAN FLOOR CONSTRUCTION ( SIKAFLOOR ) | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-01 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | HAS | APK | EKN
8 |  | 280E1210207 | [6 empty] | PROSES APLIKASI BITUMINOUS | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-10 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | AZA | APK | EKN
9 |  | 280E1210208 | [6 empty] | PROSES SEALENT PADA CARBODY KERETA KCI | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-07 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | FRA | APK | EKN
10 |  | 280E1210209 | [6 empty] | PROSES BLACK COAT UNDERFRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-03-18 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | HAS | APK | EKN
11 |  | 280E1210210 | [6 empty] | FITTING OUTSIDE COLOUR SCHEME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [17 empty] | N/A |  |  |  |  | FRA | APK | EKN
12 |  | 280E1210211 | [6 empty] | PROSES PEMBERSIHAN DAN PENGECATAN PIPA | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-13 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | AZA | APK | EKN
13 |  | 280E1210212 | [6 empty] | PENGECATAN KOMPONEN UF | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-05 | [12 empty] | CLOSED | N/A | CLOSED |  |  |  | HAS | APK | EKN
|  | 280E1210213 | [6 empty] | PROSES APLIKASI DEMPUL DAN SURFACER MASKARA TC | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [17 empty] | N/A |  |  |  |  | HAS | APK | EKN
|  | 280E1210214 | [6 empty] | PROSES APLIKASI FINISH COAT MASKARA | Special Process | ● | [5 empty] | ● | [23 empty] | HAS | APK | EKN
|  | 292K72001 | [6 empty] | INSULATION OF BODY SIDE (TC) | Special Process | ● | [5 empty] | ● | A3 |  |  |  | 2024-04-29 | [12 empty] | CLOSED |  | CLOSED |  |  |  | EPP | APK | EKN
|  | 292E12201 | [6 empty] | FITTING INSULATION OF BODY SIDE (M) | Special Process |  | ● | ● |  |  |  |  | A3 |  |  |  | 2024-05-17 | [12 empty] | CLOSED |  | CLOSED |  |  |  | HAS | APK | EKN
|  | 293E12001 | [6 empty] | INSULATION OF BODY END | Special Process |  | ● | ● | ● | ● | ● |  | A3 |  |  |  | 2024-05-14 | [12 empty] | CLOSED |  | CLOSED |  |  |  | AZA | APK | EKN
|  | 294E12101 | [6 empty] | INSULATION OF CABIN | Special Process | ● | [5 empty] | ● | A3 |  |  |  | 2024-06-07 | [12 empty] | CLOSED |  | CLOSED |  |  |  | HAS | APK | EKN
|  | 295E12001 | [6 empty] | INSULATION OF ROOF & CEILING | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-05-17 | [12 empty] | CLOSED |  | CLOSED |  |  |  | KRS | APK | EKN
14 |  | 295E12101 | [6 empty] | INSULATION OF ROOF & CEILING | Special Process | ● | [5 empty] | ● | A3 |  |  |  | 2024-06-06 | [12 empty] | CLOSED |  | CLOSED |  |  |  | HAS | APK | EKN
15
|  | MB1122030100 | [6 empty] | PROSES GRID BLASTING BOGIE FRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-01 | [14 empty] | CLOSED |  |  |  | FRA | APK | EKN
|  | MB1122030101 | [6 empty] | PROSES PENGECATAN PRIMER DAN TOP COAT BOGIE FRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-21 | [14 empty] | CLOSED |  |  |  | FRA | APK | EKN
|  | MB1122030102 | [6 empty] | PROSES PENGECATAN BOGIE SET | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 |  |  |  | 2024-02-28 | [14 empty] | CLOSED |  |  |  | FRA | APK | EKN
SERIES
|  | 210E121020201 | [6 empty] | PROSES PENGECATAN PRIMER COMPLETED UNDERFRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | AZA | APK | EKN
|  | 211E122010101 | [6 empty] | PROSES BLASTING & PENGECATAN AREA YANG TERTUTUP KOMPONEN DRAFGEAR STOPER & END CENTERSILL | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | HAS | APK | EKN
|  | 212E120010101 | [6 empty] | PROSES BLASTING & PRIMER BOLSTER BAGIAN DALAM | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | HAS | APK | EKN
|  | 280E121020301 | [6 empty] | PROSES PRIMER INTERIOR CARBODY KRL KCI | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | FRA | APK | EKN
|  | 280E121020401 | [6 empty] | PROSES APLIKASI ANTISKID ROOF | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | AZA | APK | EKN
|  | 280E121020901 | [6 empty] | PROSES BLACK COAT UNDERFRAME | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | FRA | APK | EKN
|  | 280E121021101 | [6 empty] | PROSES PEMBERSIHAN DAN PENGECATAN PIPA | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | AZA | APK | EKN
|  | 280E121021301 | [6 empty] | PROSES APLIKASI DEMPUL DAN SURFACER MASKARA TC | Special Process | ● | [5 empty] | ● | A3 | [22 empty] | FRA | APK | EKN
|  | 280E121021401 | [6 empty] | PROSES APLIKASI FINISH COAT MASKARA | Special Process | ● | [5 empty] | ● | A3 | [22 empty] | FRA | APK | EKN
|  | 673E1201401 | [6 empty] | PROSES APLIKASI PRIMER FRAME CEILLING | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | HAS | APK | EKN
|  | 641E1202001 | [6 empty] | PROSES APLIKASI PRIMER INNER FRAMING SIDEWALL | Special Process | ● | ● | ● | ● | ● | ● | ● | A3 | [22 empty] | HAS | APK | EKN
|  | MB112203010101 | [6 empty] | PROSES PENGECATAN PRIMER DAN TOP COAT BOGIE FRAME | [31 empty] | FRA | APK | EKN
|  | MB112203010201 | [6 empty] | PROSES PENGECATAN BOGIE SET | [31 empty] | FRA | APK | EKN
|  | PPS | [6 empty] | PPS | Special Process | ● | ● | ● | ● | ● | ● | ● | A4 | [17 empty] | CLOSED | CLOSED |  |  |  | WPK | EKN/TAR | KTT
|  | BOM Series | [6 empty] | Special Process | Special Process | ● | ● | ● | ● | ● | ● | ● | A4 | [17 empty] | CLOSED | CLOSED |  |  |  | WPK | EKN/TAR | ADA
|  | BOM Pre Series | [6 empty] | Special Process | Special Process | ● | ● | ● | ● | ● | ● | ● | A4 | [17 empty] | CLOSED | CLOSED |  |  |  | WPK | EKN/TAR | KTT
|  | MEMO PEMILIHAN CAT | [6 empty] | M-056-422-2023 | Special Process | ● | ● | ● | ● | ● | ● | ● | A4 | [17 empty] | CLOSED | CLOSED |  |  |  | WPK | EKN/TAR | KTT
[9 empty] | DISIAPKAN OLEH : |  | DIPERIKSA OLEH :
[9 empty] | EKO NOVIANTO |  | TARMUJI

## jadwal weeks (hidden)
| Revisi | [5 empty] | : | [7 empty] | 17
| Tanggal Revisi | [5 empty] | : |  |  | Rencana
Progres Sesuai rencana
% Selesai Sesuai rencana
BOGIE 438 | [9 empty] | Progres Tidak Sesuai rencana
% Selesai Tidak Susuai Rencana
DRAWING NUMBER | [7 empty] | ACTIVITY | Start Date | Finish Date | PLANING |  | REAL |  | % | PIC | 2016 |  |  |  |  | 2017
[11 empty] | Start week | Time Frame | Real Start | Real duration |  |  | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
00.0-M25000 | [7 empty] | BOGIE ARRANGEMENT |  |  | 2
| 01.0-M25000 | [6 empty] | WHEEL AND AXLE |  |  | 2 |  |  |  | #REF!
| 01.0-A17000 | [6 empty] | WHEEL AND AXLE |  |  | 9
|  | 01.0-M25001 | [5 empty] | WHEEL |  |  | 14
|  | 01.0-A17001 | [5 empty] | WHEEL |  |  | 14
|  | 01.0-M25002 | [5 empty] | AXLE |  |  | 16
|  | 01.0-A17002 | [5 empty] | AXLE |  |  | 60
|  | 01.0-M25003 | [5 empty] | STAMPING OF WHEEL |  |  | 13
|  | 01.0-M25004 | [5 empty] | STAMPING OF AXLE |  |  | 70
|  | 01.0-M25005 | [5 empty] | TREAD PROFILE |  |  | 17
| 02.0-M25000 | [6 empty] | AXLE BOX ASSEMBLY |  |  | 17
|  | 02.0-M25001 | [5 empty] | AXLE BOX |  |  | 16
|  | 02.0-M25003 | [5 empty] | JOURNAL ROLLER BEARING CLASS C |  |  | 16
|  | 02.0-M25004 | [5 empty] | STOPPER |  |  | 16
|  | 02.0-M25007 | [5 empty] | HANGER |  |  | 16
| 03.0-M25000 | [6 empty] | BOGIE FRAME ASS'Y |  |  | 16
|  | 03.0-M25001 | [5 empty] | MAIN CONSTRUCTION OF BOGIE FRAME |  |  | 17
|  | 03.0-M25002 | [5 empty] | BOGIE FRAME MACHINING |  |  | 17
|  | 03.0-M25003 | [5 empty] | SPRING GUIDE |  |  | 17
|  | 03.0-M25004 | [5 empty] | SPRING GUIDE |  |  | 17 |  | 17 | 1
| 03.1-M25000 | [6 empty] | SIDE BEAM |  |  | 17
| 03.2-M25000 | [6 empty] | TRANSOM |  |  | 17
| 03.3-M25000 | [6 empty] | END BEAM |  |  | 17
| 03.5-M25000 | [6 empty] | CENTER BEAM |  |  | 16
| 03.8-M25000 | [6 empty] | ARRANGEMENT BRACKET |  |  | 16
|  | 03.8-M25001 | [5 empty] | BRAKE LEVER BRACKET |  |  | 16
|  | 03.8-M25002 | [5 empty] | BRAKE LEVER HANGER BRACKET |  |  | 16
|  | 03.8-M25003 | [5 empty] | BRAKE BLOCK HANGER BRACKET (1) |  |  | 16
|  | 03.8-M25004 | [5 empty] | BRAKE BLOCK HANGER BRACKET (2) |  |  | 17
|  | 03.8-M25005 | [5 empty] | BOLSTER GUIDE |  |  | 17
|  | 03.8-M25006 | [5 empty] | BOLSTER GUIDE & LATERAL DAMPER |  |  | 17
| 06.0-M25001 | [6 empty] | CONICAL BONDED RUBBER SPRING (KP) |  |  | 17
|  | 06.0-M25003 | [5 empty] | LINER BONDET |  |  | 17
|  | 06.0-M25004 | [5 empty] | RETAINER PLATE |  |  | 17
|  | 06.0-M25005 | [5 empty] | LINNER |  |  | 16
|  | 06.0-M25006 | [5 empty] | PRIMARY SUSPENSION ASS'Y |  |  | 16
|  | 06.0-M25007 | [5 empty] | LOCKING PLATE |  |  | 16
| 07.0 - M25000 | [6 empty] | SWING BOLSTER DEVICE |  |  | 16
|  | 07.0 - M25001 | [5 empty] | HANGER BRACKET |  |  | 16
|  | 07.0 - M25002 | [5 empty] | SWING LINK |  |  | 17
|  | 07.0 - M25003 | [5 empty] | PIN |  |  | 17
|  | 07.0 - M25004 | [5 empty] | SPRING PLANK |  |  | 17
|  | 07.0 - M25005 | [5 empty] | GUIDE RUBBER |  |  | 3
|  | 07.0 - M25006 | [5 empty] | LINER FOR GUIDE RUBBER |  |  | 3
|  | 07.0 - A17007 | [5 empty] | BOLSTER SPRING |  |  | 4
|  | 07.0-A74007 | [5 empty] | BOLSTER SPRING |  |  | 4
|  | 07.0-B33007 | [5 empty] | BOLSTER SPRING |  |  | 9
|  | 07.0-C55007 | [5 empty] | BOLSTER SPRING |  |  | 9
|  | 07.0 - M25008 | [5 empty] | BOLSTER SPRING LINER |  |  | 55
|  | 07.0 - M25009 | [5 empty] | BOLSTER SPRING UPPER SEAT |  |  | 9
|  | 07.0 - M25010 | [5 empty] | OIL DAMPER |  |  | 7
|  | 07.0 - M25011 | [5 empty] | UPPER BOLSTER |  |  | 55
|  | 07.0 - M25012 | [5 empty] | BOTTOM CENTER PLATE |  |  | 17
|  | 07.0 - M25013 | [5 empty] | CENTER PLATE LINER |  |  | 3
|  | 07.0 - M25014 | [5 empty] | CENTER PLATE STUFFING |  |  | 3
|  | 07.0 - M25015 | [5 empty] | UPPER CENTER PLATE |  |  | 22
|  | 07.0 - M25016 | [5 empty] | LINER FOR CENTER PLATE |  |  | 55
|  | 07.0 - M25017 | [5 empty] | CENTER PIN |  |  | 55
|  | 07.0 - M25018 | [5 empty] | SIDE BEARER ASS'LY |  |  | 55
|  | 07.0 - M25019 | [5 empty] | SIDE BEARER HOUSING |  |  | 21
|  | 07.0 - M25020 | [5 empty] | WEARING PLATE ASS'Y |  |  | 21
|  | 07.0 - M25021 | [5 empty] | RUBBER FOR SIDE BEARER |  |  | 55
|  | 07.0 - M25022 | [5 empty] | SEAT FOR RUBBER |  |  | 55
|  | 07.0 - M25023 | [5 empty] | LINER FOR SIDE BEARER |  |  | 55
|  | 07.0 - M25024 | [5 empty] | BOLSTER WEARING PLATE ASS'Y |  |  | 55
|  | 07.0 - M25025 | [5 empty] | BOLSTER WEARING PLATE |  |  | 55
|  | 07.0 - M25026 | [5 empty] | RUBBING PLATE |  |  | 55
|  | 07.0 - M25027 | [5 empty] | LINER FOR BOLSTER WEARING PLATE |  |  | 55
|  | 07.0 - M25028 | [5 empty] | RUBBER STOPPER |  |  | 55
|  | 07.0 - M25029 | [5 empty] | DISTANCE PIECE AND LINER FOR RUBBER STOPPER |  |  | 55
|  | 07.0 - M25030 | [5 empty] | SAFETY WIRE |  |  | 55
|  | 07.0 - M25031 | [5 empty] | PLUG |  |  | 55
|  | 07.0 - M25032 | [5 empty] | SPLIT COTTER |  |  | 55
|  | 07.0 - M25033 | [5 empty] | BRACKET LATERAL DAMPER |  |  | 55
|  | 07.0 - M25034 | [5 empty] | LATERAL DAMPER |  |  | 55
|  | 07.0 - M25035 | [5 empty] | BUSH TABLE |  |  | 55
|  | 07.0 - M25009 | [5 empty] | BOLSTER SPRING UPPER SEAT |  |  | 21
| 08.0 - M25000 | [6 empty] | BRAKE GEAR |  |  | 21
|  | 08.0 - M25001 | [5 empty] | BRAKE LEVER (1) |  |  | 56
|  | 08.0 - M25002 | [5 empty] | BRAKE LEVER (2) |  |  | 56
|  | 08.0 - M25003 | [5 empty] | BRAKE LEVER (3) |  |  | 56
|  | 08.0 - M25004 | [5 empty] | BRAKE LEVER HANGER |  |  | 56
|  | 08.0 - M25005 | [5 empty] | BRAKE ROD |  |  | 56
|  | 08.0 - M25006 | [5 empty] | CONNECTING LINK |  |  | 56
|  | 08.0 - M25007 | [5 empty] | BRAKE PULL ROD |  |  | 56
|  | 08.0 - M25008 | [5 empty] | BRAKE BEAM |  |  | 56
|  | 08.0 - M25009 | [5 empty] | BRAKE BLOCK HANGER |  |  | 56
|  | 08.0 - M25010 | [5 empty] | BRAKE BLOCK (BLOK REM) |  |  | 56
|  | 08.0 - M25011 | [5 empty] | BRAKE BLOCK HEAD |  |  | 21
|  | 08.0 - M25012 | [5 empty] | SHOE KEY |  |  | 21
|  | 08.0 - M25013 | [5 empty] | ADJUSTING DEVICE |  |  | 56
|  | 08.0 - M25014 | [5 empty] | ADJUSTING PLATE |  |  | 56 | bar: 2017 51 56 to 2017 52 57
|  | 08.0 - M25015 | [5 empty] | SPRING |  |  | 56
|  | 08.0 - M25016 | [5 empty] | SPRING SEAT |  |  | 56
|  | 08.0 - M25017 | [5 empty] | PIN TABLE |  |  | 56
|  | 08.0 - M25018 | [5 empty] | BUSH TABLE |  |  | 56
|  | 08.0 - M25019 | [5 empty] | SAFETY BAND |  |  | 56
|  | 08.0 - M25020 | [5 empty] | SPLIT COTTER |  |  | 56
| 12.0 - M25000 | [6 empty] | ARRANGGEMENT OF BUILDERS PLATE & BOGIE TYPE |  |  | 56
|  | 12.0 - M25001 | [5 empty] | BUILDERS PLATE |  |  | 56
|  | 12.0 - M25002 | [5 empty] | BOGIE TYPE & BOGIE NO. PLATE |  |  | 21
|  | 12.0 - E11002 | [5 empty] | BUILDERS PLATE |  |  | 21

## jadwal hari
[14 empty] | 31 | [15 empty] | Rencana | [48 empty] | 2017
[10 empty] | Rencana | [23 empty] | Sesuai rencana
| Tanggal : | [8 empty] | Progres Sesuai rencana | [6 empty] | PERIODE YG DISOROT:
| Revisi : | [8 empty] | % Selesai Sesuai rencana | [43 empty] | 1 | 2 | 3 | 4 | Tanggal Susuai kalender
PI LIST KRDE BIM | [9 empty] | Progres Tidak Sesuai rencana
[10 empty] | % Selesai Tidak Susuai Rencana | [6 empty] | PERIODE /DAYS | [12 empty] | % Selesai Tidak Susuai Rencana | [23 empty] | 1 | 2 | 3 | 4 | Hari Dalam Proyek
DRAWING NUMBER | [7 empty] | ACTIVITY | Start Date | Finish Date | PLANING |  | REAL |  | % | PIC
[11 empty] | Start Days | Time Frame | Real Start | Real Duration |  |  | 2016-10-01 | [30 empty] | 2016-12-01 | [30 empty] | 2017-01-01 | [30 empty] | 2017-02-01 | [27 empty] | 2017-03-01 | [30 empty] | 2017-04-01 | [29 empty] | May 2017 | [30 empty] | 2017-06-01 | [29 empty] | 2017-07-01 | [30 empty] | 2017-08-01 | [30 empty] | 2017-09-01 | [29 empty] | 1931-10-01 | [30 empty] | 2017-11-01 | [29 empty] | 2017-12-01
[17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396
00.0-M25000 | [10 empty] | 13
| 01.0-M25000 | [9 empty] | 10
| 01.0-A17000 | [9 empty] | 116
|  | 01.0-M25001 | [8 empty] | 12
|  | 01.0-A17001 | [8 empty] | 117
|  | 01.0-M25002 | [8 empty] | 12
|  | 01.0-A17002 | [8 empty] | 116
|  | 01.0-M25003 | [8 empty] | 12
|  | 01.0-M25004 | [8 empty] | 12
|  | 01.0-M25005 | [8 empty] | 12
| 02.0-M25000 | [9 empty] | 10
|  | 02.0-M25001 | [8 empty] | 10
|  | 02.0-M25003 | [8 empty] | 12
|  | 02.0-M25004 | [8 empty] | 12
|  | 02.0-M25007 | [8 empty] | 12
| 03.0-M25000 | [9 empty] | 12
|  | 03.0-M25001 | [8 empty] | 10
|  | 03.0-M25002 | [8 empty] | 17
|  | 03.0-M25003 | [8 empty] | 17
|  | 03.0-M25004 | [8 empty] | 17 |  | 17
| 03.1-M25000 | [9 empty] | 9
| 03.2-M25000 | [9 empty] | 9
| 03.3-M25000 | [9 empty] | 10
| 03.5-M25000 | [9 empty] | 10
| 03.8-M25000 | [9 empty] | 13
|  | 03.8-M25001 | [8 empty] | 12
|  | 03.8-M25002 | [8 empty] | 12
|  | 03.8-M25003 | [8 empty] | 12
|  | 03.8-M25004 | [8 empty] | 12
|  | 03.8-M25005 | [8 empty] | 12
|  | 03.8-M25006 | [8 empty] | 13
| 06.0-M25001 | [9 empty] | 13
|  | 06.0-M25003 | [8 empty] | 13
|  | 06.0-M25004 | [8 empty] | 13
|  | 06.0-M25005 | [8 empty] | 13
|  | 06.0-M25006 | [8 empty] | 13
|  | 06.0-M25007 | [8 empty] | 56
| 07.0 - M25000 | [9 empty] | 376
|  | 07.0 - M25001 | [8 empty] | 377
|  | 07.0 - M25002 | [8 empty] | 380
|  | 07.0 - M25003 | [8 empty] | 379
|  | 07.0 - M25004 | [8 empty] | 377
|  | 07.0 - M25005 | [8 empty] | 375
|  | 07.0 - M25006 | [8 empty] | 375
|  | 07.0 - A17007 | [8 empty] | 83
|  | 07.0-A74007 | [8 empty] | 70
|  | 07.0-B33007 | [8 empty] | 94
|  | 07.0-C55007 | [8 empty] | 94
|  | 07.0 - M25008 | [8 empty] | 370
|  | 07.0 - M25009 | [8 empty] | 55
|  | 07.0 - M25010 | [8 empty] | 379
|  | 07.0 - M25011 | [8 empty] | 367
|  | 07.0 - M25012 | [8 empty] | 146
|  | 07.0 - M25013 | [8 empty] | 14
|  | 07.0 - M25014 | [8 empty] | 14
|  | 07.0 - M25015 | [8 empty] | 118
|  | 07.0 - M25016 | [8 empty] | 377
|  | 07.0 - M25017 | [8 empty] | 379
|  | 07.0 - M25018 | [8 empty] | 380
|  | 07.0 - M25019 | [8 empty] | 142
|  | 07.0 - M25020 | [8 empty] | 142
|  | 07.0 - M25021 | [8 empty] | 380
|  | 07.0 - M25022 | [8 empty] | 380
|  | 07.0 - M25023 | [8 empty] | 380
|  | 07.0 - M25024 | [8 empty] | 380
|  | 07.0 - M25025 | [8 empty] | 380
|  | 07.0 - M25026 | [8 empty] | 380
|  | 07.0 - M25027 | [8 empty] | 380
|  | 07.0 - M25028 | [8 empty] | 380
|  | 07.0 - M25029 | [8 empty] | 380
|  | 07.0 - M25030 | [8 empty] | 380
|  | 07.0 - M25031 | [8 empty] | 380
|  | 07.0 - M25032 | [8 empty] | 380
|  | 07.0 - M25033 | [8 empty] | 380
|  | 07.0 - M25034 | [8 empty] | 378
|  | 07.0 - M25035 | [8 empty] | 380
|  | 07.0 - M25009 | [8 empty] | 55
| 08.0 - M25000 | [9 empty] | 140
|  | 08.0 - M25001 | [8 empty] | 384
|  | 08.0 - M25002 | [8 empty] | 384
|  | 08.0 - M25003 | [8 empty] | 384
|  | 08.0 - M25004 | [8 empty] | 384
|  | 08.0 - M25005 | [8 empty] | 384
|  | 08.0 - M25006 | [8 empty] | 384
|  | 08.0 - M25007 | [8 empty] | 384
|  | 08.0 - M25008 | [8 empty] | 384
|  | 08.0 - M25009 | [8 empty] | 384
|  | 08.0 - M25010 | [8 empty] | 384
|  | 08.0 - M25011 | [8 empty] | 140
|  | 08.0 - M25012 | [8 empty] | 140
|  | 08.0 - M25013 | [8 empty] | 20
|  | 08.0 - M25014 | [8 empty] | 19
|  | 08.0 - M25015 | [8 empty] | 19
|  | 08.0 - M25016 | [8 empty] | 19
|  | 08.0 - M25017 | [8 empty] | 19
|  | 08.0 - M25018 | [8 empty] | 19
|  | 08.0 - M25019 | [8 empty] | 17
|  | 08.0 - M25020 | [8 empty] | 17
| 12.0 - M25000 | [9 empty] | 19
|  | 12.0 - M25001 | [8 empty] | 19
|  | 12.0 - M25002 | [8 empty] | 133
|  | 12.0 - E11002 | [8 empty] | 134

## OIL Setup
Meeting / Project Title | DRAWING LIST LRT PALEMBANG
Definition of KPIs and (Filter-) clusters need to be done here. Attention: Changes in format keep high risk of KPI calculation mismatch!
KPI | Risk Level | Requester | Open / Closed | Function responsible | Sheet | Paper | Revision
Fabrication | High | General | Open | Internal | 1 | A0 | 0
Mechanical System | Modarate | Quality | Progressing | Eksternal | 2 | A1 | A
Interior |  | PM | Closed |  | 3 | A2 | B
Special Process | Low | ToT | Revisi |  | 4 | A3 | C
Bogie |  | Material | Cancelled |  | 5 | A4 | D
Electric |  | ENG | N/A |  | 6 |  | E
Finishing |  | Technical |  |  | 7 |  | F
[5 empty] | 8 |  | G
[5 empty] | 9 |  | H
[5 empty] | 10 |  | -
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
|  |  | no status |  | 100
cell marked with this colour can be changed to add an additional Key word for the drop down menue

## KPI Calculation - tb selected
Cell marked with this colour can be selected with "x" to allow for filtering the KPI on tab "Open Item List" Attention: --> After selection with "x" filter in column C the selcted items only to show your personal selected KPI on tab "Open Item List". --> Change of KPI selection requires unfiltering of column C before. --> Selection of more than 8 KPI not useful to keep visibility on Tab1.
[12 empty] | Fab |  |  |  | Fab |  |  |  |  | Spesial Proses |  |  |  | Spesial Proses |  |  |  |  | Mechanic |  |  |  | Mechanic |  |  |  |  | Interior |  |  |  | Interior
Actions qtty not closed | Use | KPI | [5 empty] | TOTAL | CLOSED + CANCELLED |  |  | Plan | Actual |  |  | Plan | Actual | Forecast |  |  | Plan | Actual |  |  | Plan | Actual | Forecast |  |  | Plan | Actual |  |  | Plan | Actual | Forecast |  |  | Plan | Actual |  |  | Plan | Actual | Forecast
| x |  |  |  | 59 |  |  |  |  | FEB | W1 |  |  | FEB'23 | W1 |  |  |  | FEB | W1 |  |  | FEB'23 | W1 |  |  |  | FEB | W1 |  |  | FEB'23 | W1 |  |  |  | FEB | W1 |  |  | FEB'23 | W1
| x | [5 empty] | 0 |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2
| x | [9 empty] | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3
| x | [9 empty] | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4
| x | [8 empty] | MAR | W1 |  |  | MAR'23 | W1 |  |  |  | MAR | W1 |  |  | MAR'23 | W1 |  |  |  | MAR | W1 |  |  | MAR'23 | W1 |  |  |  | MAR | W1 |  |  | MAR'23 | W1
| x | [9 empty] | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2
| X | Total | [8 empty] | W3 |  |  |  | W3 |  |  | 3 |  | W3 |  |  |  | W3 |  |  | 3 |  | W3 |  |  |  | W3 |  |  | 3 |  | W3 |  |  |  | W3 |  |  | 3
Total items | [10 empty] | W4 |  |  |  | W4 |  |  | 6 |  | W4 |  |  |  | W4 |  |  | 6 |  | W4 |  |  |  | W4 |  |  | 6 |  | W4 |  |  |  | W4 |  |  | 6
Closed items | [10 empty] | W5 |  |  |  | W5 |  |  | 9 |  | W5 |  |  |  | W5 |  |  | 9 |  | W5 |  |  |  | W5 |  |  | 9 |  | W5 |  |  |  | W5 |  |  | 9
[10 empty] | APR | W1 |  |  | APR'23 | W1 |  |  | 13 | APR | W1 |  |  | APR'23 | W1 |  |  | 13 | APR | W1 |  |  | APR'23 | W1 |  |  | 13 | APR | W1 |  |  | APR'23 | W1 |  |  | 13
[11 empty] | W2 |  |  |  | W2 |  |  | 15 |  | W2 |  |  |  | W2 |  |  | 15 |  | W2 |  |  |  | W2 |  |  | 15 |  | W2 |  |  |  | W2 |  |  | 15
[11 empty] | W3 |  |  |  | W3 |  |  | 16 |  | W3 |  |  |  | W3 |  |  | 16 |  | W3 |  |  |  | W3 |  |  | 16 |  | W3 |  |  |  | W3 |  |  | 16
[11 empty] | W4 |  |  |  | W4 |  |  | 17 |  | W4 |  |  |  | W4 |  |  | 17 |  | W4 |  |  |  | W4 |  |  | 17 |  | W4 |  |  |  | W4 |  |  | 17
[10 empty] | MAY | W1 |  |  | MAY'23 | W1 |  |  | 18 | MAY | W1 |  |  | MAY'23 | W1 |  |  | 18 | MAY | W1 |  |  | MAY'23 | W1 |  |  | 18 | MAY | W1 |  |  | MAY'23 | W1 |  |  | 18
[11 empty] | W2 |  |  |  | W2 |  |  | 20 |  | W2 |  |  |  | W2 |  |  | 20 |  | W2 |  |  |  | W2 |  |  | 20 |  | W2 |  |  |  | W2 |  |  | 20
[11 empty] | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3
[11 empty] | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4
[11 empty] | W5 |  |  |  | W5 |  |  |  |  | W5 |  |  |  | W5 |  |  |  |  | W5 |  |  |  | W5 |  |  |  |  | W5 |  |  |  | W5
[10 empty] | JUNE | W1 |  |  | JUNE'23 | W1 |  |  |  | JUNE | W1 |  |  | JUNE'23 | W1 |  |  |  | JUNE | W1 |  |  | JUNE'23 | W1 |  |  |  | JUNE | W1 |  |  | JUNE'23 | W1
[11 empty] | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2
[11 empty] | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3
[11 empty] | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4
[10 empty] | JULY | W1 |  |  | JULY'23 | W1 |  |  |  | JULY | W1 |  |  | JULY'23 | W1 |  |  |  | JULY | W1 |  |  | JULY'23 | W1 |  |  |  | JULY | W1 |  |  | JULY'23 | W1
[11 empty] | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2 |  |  |  |  | W2 |  |  |  | W2
[11 empty] | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3 |  |  |  |  | W3 |  |  |  | W3
[11 empty] | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4 |  |  |  |  | W4 |  |  |  | W4
|  |  | Total JO Drawing | Total JO Revisi
Actions qtty not closed | Use | KPI |  | Progressing |  | Revisi | Cancelled | TOTAL | CLOSED + CANCELLED
x
x
x
x
x
x
| X | Total
Actions qtty not closed | Use | KPI |  |  |  | Revisi | Cancelled | TOTAL | CLOSED + CANCELLED
x
x
x
x
x
x
x
| X | Total

## Suggestions for Improvement (hidden)
Description of Idea / Suggestion | Exact Position (Table/Column/Line) | Originator | Date | Status of Application (Yes or No) | Approved by | Comments
Term "Open Items" should be re-named as "Total Items" | "Open Item List", D1 | T. Popovic | 2015-12-10 | Yes | T. Popovic | Calculated sum of items equals the total number of items, not only the open ones
Include line 11 (E11-H11) into calculation | "KPI Calculation tb selected", E12-H12, D13 | T. Popovic | 2015-12-17 | Yes | T. Popovic | Check if all items are calculated properly as not all lines may be included