## Sheet1
No | Proyek | nodokumen | namadokumen | level | drafter | checker | deadlinerelease | documentkind | realisasi | status
|  | 00.0-I111001 | GENERAL ARRAGEMENT GERBONG DATAR BERAT MUAT (BM) 54 TON |  | AFR | FKH |  |  | 16-05-2024 | RELEASED
|  | 21.1-I111001 | END BEAM (R) |  | AFR | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.1-I111003 | END BEAM (L) |  | GCP | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.1-I111004 | STRIKER ASSY |  | DAN | SDI |  |  | 03-07-2024 | RELEASED
|  | 21.1-I111005 | BRACKET OF YOKE R\ L |  | AFR | ATD |  |  | 16-05-2024 | RELEASED
|  | 21.2-I111001 | BOLSTER (R) |  | AFR | ATD |  |  | 16-05-2024 | RELEASED
|  | 21.2-I111002 | BOLSTER (L) |  | AFR | ATD |  |  | 16-05-2024 | RELEASED
|  | 21.3-I111001 | CROSS BEAM 1 (R) |  | AFR | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.3-I111003 | CROSS BEAM 2 (L) |  | GCP | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.3-I111004 | CROSS BEAM 2 (R) |  | GCP | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.8-I24035 | GRAB HANDLE |  | DAN | KRZ |  |  | 22-05-2024 | RELEASED
|  | 75.1-I24001 | STEP AND FITTING |  | DAN | KRZ |  |  | 22-05-2024 | RELEASED
|  | 21.1-I111002 | END CENTER SILL ASSY | - | - | - |  |  | 27-05-2024 | RELEASED
|  | 21.3-I111005 | SIDE FRAME |  | GCP | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.8-I27017 | HANDBRAKE WHEEL BRACKET |  | AFR | ATD |  |  | 27-05-2024 | RELEASED
|  | 21.8-I111041 | GUIDE RIGING BRACKET |  | AFR | ATD |  |  | 27-05-2024 | RELEASED
|  | 21.8-I111042 | TRUNION NUT BRACKET |  | AFR | ATD |  |  | 27-05-2024 | RELEASED
|  | 21.8-I111047 | RECERVOIR TANK BRACKET |  | AFR | ATD |  |  | 27-05-2024 | RELEASED
|  | 21.8-I111053 | BRAKE RELEASE BRACKET |  | AFR | ATD |  |  | 27-05-2024 | RELEASED
|  | 202-BRM-P1007XX000-24 | BILL OF MATERIAL (ESTIMATION) |  | FKH | RVN |  |  | 31-05-2024 | RELEASED
|  | 201\/BRM\/P1007XX000\/24 | BILL OF MATERIAL (ESTIMATION) |  | FKH | BAS |  |  | 29-02-2024 | RELEASED
|  | 21.8-I27013 | END COCK KEY & FITTING |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 28.1-I24001 | MARKING OF HAND BRAKE WHEEL |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I24007 | SHIM |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I24018 | CARRIER ASS'Y |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I24019 | CARRIER SPRING |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I24020 | CARRIER KEY |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I24021 | CARRIER |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I24022 | WARE PLATE CARRIER |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I27013 | BRACKET OF YOKE 3 |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.1-I27014 | SUPPORT OF YOKE |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.2-I24002 | UNCOUPLING ROD |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.2-I27001 | UNCOUPLING LEVER DEVICE |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.2-I27003 | UNCOUPLING ROD BRACKET |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.5-I24003 | SAFETY CHAIN |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 30.5-I24004 | SPRING FOR SAFETY CHAIN |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 32.1-I24006 | BRAKE COUPLING HOSE |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 32.7-I24001 | PIPE CLAMP |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 32.7-I24002 | PIPE CLAMP (U-BOLT) |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.1-I24004 | TRUNNION NUT |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.1-I24007 | HAND BRAKE WHEEL |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.1-I24008 | TRUNNION LINK |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.1-I24009 | GUIDE OF BRAKE |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.1-I27011 | HAND BRAKE PULL ROD |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.2-I24010 | GUIDE OF BRAKE RIGING |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.2-I24011 | GUIDE OF BRAKE RIGING |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.2-I27003 | CONNECTING ROD |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.2-I27004 | CONTROL ROD |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.2-I27008 | PULL ROD |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.2-I27009 | TURN BUCKLE |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.7-I27004 | PIN AND RING TABLE |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 34.7-I27005 | BUSH TABLE |  | DAN | FKH |  |  | 03-06-2024 | RELEASED
|  | 35.1-I24002 | OPERATING VALVE |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 73.6-I24001 | STOP BLOCK |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 91.0-I27001 | U BOLT (FOR CLAMP BOGIE) |  | AFR | FKH |  |  | 03-06-2024 | RELEASED
|  | 21.0-I111002 | MAIN COSTRUCTION OF UNDERFRAME | - | - | - |  |  | 25-06-2024 | RELEASED
|  | 21.3-I111006 | CENTER SILL ASS'Y |  | GCP | FKH |  |  | 03-06-2024 | RELEASED
|  | 21.3-I111002 | CROSS BEAM 1 (L) |  | AFR | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.8-I111043 | DISTRIBUTOR VALVE BRACKET |  | GCP | SDI |  |  | 05-06-2024 | RELEASED
|  | 21.0-I111001 | ARRANGEMENT OF UNDERFRAME ASSY |  | AFR | ATD |  |  | 05-06-2024 | RELEASED
|  | 21.8-I111038 | ARRANGEMENT BRACKET & FRAME ON U\/F | - | - | - |  |  | 05-06-2024 | RELEASED
|  | 21.8-I111039 | CYLINDER BRAKE BRACKET |  | DAN | FKH |  |  | 05-06-2024 | RELEASED
|  | 21.8-I111044 | PIPE BRACKET (1\/4") |  | GCP | FKH |  |  | 05-06-2024 | RELEASED
|  | 21.8-I111049 | PIPE BRACKET (1 1\/4" & 1\/2") |  | GCP | FKH |  |  | 05-06-2024 | RELEASED
|  | 21.8-I111056 | FITTING BRACKET STOP BLOCK |  | DAN | KRZ |  |  | 05-06-2024 | RELEASED
|  | 21.8-I111060 | GRIP BAR |  | GCP | KRZ |  |  | 05-06-2024 | RELEASED
|  | 21.8-I111046 | PIPE BRACKET ( 1 1\/4" ) |  | DAN | SDI |  |  | 06-06-2024 | RELEASED
|  | 21.8-I111040 | BRAKE LEVER BRACKET |  | DAN | FKH |  |  | 12-06-2024 | RELEASED
|  | 21.8-I111050 | PIPE BRACKET (1\/2" & 1\/4") |  | GCP | FKH |  |  | 12-06-2024 | RELEASED
|  | 21.8-I111058 | BRAKE LEVER BRACKET |  | AFR | KRZ |  |  | 12-06-2024 | RELEASED
|  | 21.8-I111059 | FOOT STEP |  | AFR | KRZ |  |  | 12-06-2024 | RELEASED
|  | 36.9-I111054 | ANTI THEFT DEVICE ASSEMBLY |  | GCP | FKH |  |  | 12-06-2024 | RELEASED
|  | 07.0-I27012 | UPPER CEN TER PLATE |  | DAN | FKH |  |  | 19-06-2024 | RELEASED
|  | 21.3-I111007 | LIFTING BRACKET 01 |  | GCP | FKH |  |  | 19-06-2024 | RELEASED
|  | 201-BRM-P1007XX000-24 | BILL OF MATERIAL (ESTIMATION) |  | FKH | BAS |  |  | 24-06-2024 | RELEASED
|  | 202-BRM-P1007XX000 -24 | BILL OF MATERIAL (ESTIMATION) |  | FKH | RVN |  |  | 24-06-2024 | RELEASED
|  | 21.4-I111001 | SAFETY FOR CONTAINER DOOR |  | GCP | FKH |  |  | 25-06-2024 | RELEASED
|  | 21.8-I111048 | PIPE BRACKET (1\/2") |  | AFR | ATD |  |  | 25-06-2024 | RELEASED
|  | 21.8-I111052 | ANTI THEFT BRACKET |  | DAN | SDI |  |  | 25-06-2024 | RELEASED
|  | 201-BRM-P1007XX000 -24 | BILL OF MATERIAL (ESTIMATION) 1164 PPCW 54T |  | FKH | BAS |  |  | 06-02-2024 | RELEASED
|  | 00.0-I27005 | ACCEPTANCE CRITERIA |  | GCP | FKH |  |  | 03-07-2024 | RELEASED
|  | 32.7-I27003 | RESERVOIR SUPPORT |  | AFR | ATD |  |  | 10-07-2024 | RELEASED
|  | 21.8-I111061 | BASE FOOT STEP |  | AFR | FKH |  |  | 10-07-2024 | RELEASED
28.1-A17001
202\/BRM\/P1007XX000\/24
00.0-I27006
00.4-I27003
00.4-I27004
01.0-I24001
01.0-I24002
01.0-I24003
01.0-I24004
02.0-I24001
02.0-I24002
02.0-I24003
02.0-I24004
|  | 02.0-I24005 | JOURNAL BEARING D (5 1\/2 x 10) |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
02.0-I24006
02.0-I111007
03.0-124001
03.0-124002
03.0-124003
03.1-124001
03.1-124002
03.1-124003
03.1-124004
07.0-I27000
07.0-I24001
07.0-I24002
07.0-I24003
07.0-I24004
07.0-I27005
07.0-I24006
07.0-I27007
07.0-I24008
07.0-I24013
08.0-I24001
08.0-I24002
08.0-I24003
08.0-I24005
08.0-I24007
08.0-I24009
08.0-I24010
08.0-I24012
08.0-I24016
08.0-Z80017
08.0-I24004
08.0-I24006
08.0-I24008
08.0-I24011
08.0-I24013
08.0-Z80014
08.0-I24015
21.3-I111008
21.8-I111045
21.8-I27051
21.8-I24023
21.8-I27054
28.0-I111001
28.0-I111003
28.0-I27004
28.0-I27005
28.2-I27001
30.0-I111001
30.0-I111003
30.0-I111004
|  | 31.0-I111011 |  |  | FRS | FKH |  |  | 22-07-2024 | RELEASED
|  | 31.0-I111012 |  |  | FRS | FKH |  |  | 22-07-2024 | RELEASED
|  | 31.0-I111013 |  |  | FRS | FKH |  |  | 22-07-2024 | RELEASED
|  | 31.0-I111014 |  |  | FRS | FKH |  |  | 22-07-2024 | RELEASED
|  | 31.0-I111015 |  |  | FRS | FKH |  |  | 22-07-2024 | RELEASED
30.5-I24002
30.1-I111004
32.1-I24003
32.1-I24004
30.1-I111005
30.1-I111006
32.1-I24001
30.1-I111007
31.0-I111002
|  | 31.9-I111003 |  |  | AFR | FKH |  |  | 11-07-2024 | RELEASED
|  | 30.1-I111008 | FITTING OF BRAKE CYLINDER |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
31.4-I24001
|  | 32.0-I111001 |  |  | GCP | FKH |  |  | 11-07-2024 | RELEASED
56.0-I111004
32.8-I111004
56.0-I111002
34.0-I111007
31.4-I24002
34.0-I111008
34.1-I24005
34.2-I27001
34.2-I27010
35.1-I24003
35.1-I24004
35.1-I24005
36.0-I111002
36.1-I24001
|  | 28.0-I24004 | LABEL HOLDER ASS'Y |  | AFR | FKH |  |  | 11-07-2024 | RELEASED
|  | 34.2-I111001 | BRAKE LEVER |  | GCP | FKH |  |  | 11-07-2024 | RELEASED
|  | 34.2-I111003 | CONNECTING ROD |  | GCP | FKH |  |  | 11-07-2024 | RELEASED
|  | 34.2-I111012 | BRAKE LEVER |  | GCP | FKH |  |  | 11-07-2024 | RELEASED
|  | 01.0-I111001 |  |  | GCP | FKH |  |  | 22-07-2024 | RELEASED
|  | 01.0-I111002 | WHEEL SET |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 01.0-I111003 | WHEEL |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 01.0-I111004 | AXLE |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 02.1-I111001 | CLASS D BEARING ADAPTER |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
03.0-1111000
03.0-1111001
03.0-1111002
03.0-1111003
03.0-1111004
03.0-1111005
|  | 06.0-I111000 | DAMPING ASSY |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 06.0-I111001 | WEDGE |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 06.0-I111002 | WEDGE FRICTION PLATE |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 06.0-I111003 | VIBRATION DAMPING OUTER CIRCULAR SPRING |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 06.0-I111004 | VIBRATION DAMPING INNER CIRCULAR SPRING |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 06.0-I111005 | WASHER |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 07.0-I111000 | BOLSTER ASSY |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 07.1-I111001 | BOLSTER |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 07.1-I111002 | WEARING PLATE |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 07.1-I111003 | FIXED LEVER FULCRUM SEAT COMPOSITION |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111000 | BRAKE RIGGING |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111001 | COMPOSITE BRAKE SHOE |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 08.0-I111002 | ELASTIC BRAKE SHOE PIN RING |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111003 |  |  | GCP | FKH |  |  | 22-07-2024 | RELEASED
|  | 08.0-I111004 | BRAKE LEVER ASSY |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111005 | BOTTOM CONNECTION ROD ASSY |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111011 | CONNECTING ROD |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111012 | CLAMP PLATE |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 08.0-I111006 | FULCRUM |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111007 |  |  | GCP | FKH |  |  | 22-07-2024 | RELEASED
|  | 08.0-I111013 | SAFETY CABLE END |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 08.0-I111014 | SAFETY CABLE JOINT |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 13.0-I111001 | CENTER PIN |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 13.0-I111002 | SIDE BEARING |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 13.0-I111003 | VERTICAL WEAR LINER |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 13.0-I111004 | HORIZONTAL WEAR LINER |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 06.0-I111006 | OUTER SPRING |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 06.0-I111007 | INNER SPRING |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 02.1-I111011 | GUIDE KEY |  | GCP | FKH |  |  | 24-07-2024 | RELEASED
|  | 02.1-I111012 | BOLT M20X80 |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
32.7-I111001
34.2-I111011
35.1-I24001
36.0-I111003
00.0-I111006
32.7-i27003
28.2-I111001
32.7-I111007
34.0-I111001
|  | 34.1-I111010 | HAND BRAKE PULL ROD |  | GCP | FKH |  |  | 22-07-2024 | RELEASED
|  | 03.0-I111000 | SIDE FRAME ASSY |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 03.0-I111001 | SIDE FRAME |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 03.0-I111002 | WEAR PLATE |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 03.0-I111003 | GUIDE WEAR PLATE |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 03.0-I111004 | GUIDE FRAME WEAR PLATE |  | GCP | FKH |  |  | 23-07-2024 | RELEASED
|  | 03.0-I111005 | FLAT HEAD FOLDING BOLT |  | GCP | FKH |  |  | 24-07-2024 | RELEASED