## Sheet1
No | No Dokumen | Nama Dokumen | Drafter | Checker | Realisasi | Status
1 | MD_TL251E121016 | TRUN BUCKEL SUPPORT WELDING SHEETING ROO | AEH | HAF | 02-05-2024 | RELEASED
2 | MD_ML210E121022 | MAL LUBANG PLUG WELD SIDE SILL UNDERFRAME | RAP | HAF | 02-05-2024 | RELEASED
3 | MD_TL210E120022 | ALAT UKUR DIAGONAL BO | WWP | HAF | 03-05-2024 | RELEASED
4 | MD_JG210E121022 | JIG STAND FOR REFORMING UNDERFRAME (TC, T, MC) | WWP | RSA | 25-06-2024 | RELEASED
5 | MD_ML211E1200204 | MAL BENDING PLATE END BEAM | AEH | HAF | 14-05-2024 | RELEASED
6 | MD_JG2550E122022 | JIG CEILING FRAME (M) | RAP | HAF | 17-05-2024 | RELEASED
7 | MD_TL210E120021 | ALAT UKUR DIAGONAL CORNER | APS | HAF | 17-05-2024 | RELEASED
8 | MD_ML221E120071 | MAL DOOR AND WINDOW (TC, T, M) | SLV | HAF | 22-05-2024 | RELEASED
60 | MD_JG251E121018 | JIG WELDING ROOF (ADD. COUNTER BENDING) | YDP | RSA | 25-06-2024 | RELEASED
61 | MD_JG999TB16220001 | RIG UJI AXLE BOX MB1122 & TB1622 | HAN | RSA | 12-06-2024 | RELEASED
62 | MD_JG221E121172 | JIG FRAME DOOR SUPPORT (SPOT PORTABLE) | APS | RSA | 12-06-2024 | RELEASED
63 | MD_ML210E121021 | MAL CEK LEBAR UNDERFRAME | ADT | RSA | 12-06-2024 | RELEASED
64 | MD_JG231E120024 | JIG ENDWALL (FRAME) ALT-2 | AEH | RSA | 12-06-2024 | RELEASED
65 | MD_MLB213E1210101 | MAL SIDESILL & COVER SIDESILL | HAN | RSA | 19-06-2024 | RELEASED
66 | MD_JG221E120032 | STAND MEJA JIG PORTABLE SPOT WELDING SIDEWALL | JOV | HAF | 21-06-2024 | RELEASED
67 | MD_ML241E121011 | MAL FRAME DRIVER CAB | ADT | RSA | 25-06-2024 | RELEASED
68 | MD_JG200E120014 | JIG STAND CARBODY ASSY TC, T, M (ALTERNATIF 2 CHOWEL) | WWP | RSA | 25-06-2024 | RELEASED
69 | MD_JG200E120013 | JIG STAND FOR REFORMING CARBODY (TC, T, M) | WWP | RSA | 25-06-2024 | RELEASED
70 | MD_JG200E120012 | JIG STAND CARBODY ASSY KRL KCI (T,TC,M) | WWP | RSA | 25-06-2024 | RELEASED
71 | MD_JG231E120025 | SUPPORT BOTTOM JIG ENDWALL (FRAME) ALT-2 | AEH | RSA | 26-06-2024 | RELEASED
72 | MD_TL673E121011 | TOOL GO NO GO SLOT FRAME BOLT M8 (TC, T, M) | SLV | RSA | 27-06-2024 | RELEASED
73 | MDJG673E120141 | JIG FITTING FRAME CEILING (M,T,TC) | YDP | ERS | 02-07-2024 | RELEASED
74 | MDJG245E121021 | JIG CEILING FRAME ON CAB ( TC1 DAN TC2 ) | AEH | RSA | 05-07-2024 | RELEASED
75 | MDJG251E120043 | JIG INDIRECT SPOT WELDING FRAME PANTOGRAPH | YDP | RSA | 05-07-2024 | RELEASED
76 | MDML671E120251 | MAL MOULDING GAP CEILING 1 | YDP | RSA | 11-07-2024 | RELEASED
77 | MDML671E120271 | MAL EDGE COVER SIDE CEILING PANEL 1 & 2 | YDP | RSA | 11-07-2024 | RELEASED
78 | MDML211E1200204 | MAL BENDING PLATE END BEAM | ADH | RSA | 12-07-2024 | RELEASED
79 | MDML642E120011 | MAL FITTING ROLLER BLIND 1 | SLV | RSA | 12-07-2024 | RELEASED
80 | MD-JG251E121013 | JIG INDIRECT SPOT ROOF FRAMING REAR TC1 TC2 M2 T1 T2 T3 | AEH | HAF | 30-10-2023 | RELEASED
81 | MD-JIG211E121011 | JIG END EUNDERFRAME 2 (UNDER MASKAR - TC) | RAP | HAF | 09-10-2023 | RELEASED
82 | MD-JG221E120031 | MEJA PORTABEL SPOT WELDING MIDDLE SIDEWALL 1 & 2 | JOF | HAF | 09-10-2023 | RELEASED
83 | MD-JG221E120033 | JIG PORTABEL SPOT WELDING MIDDLE SIDEWALL 1 & 2 | JAF | HAF | 23-10-2023 | RELEASED
84 | MD-JG221E120052 | JIG PORTABEL SPOT WELDING END SIDEWALL | APS | HAF | 26-10-2023 | RELEASED
85 | MD-JG221E120053 | MEJA JIG PORTABEL SPOT WELDING END SIDEWALL 2 | APS | HAF | 23-10-2023 | RELEASED
86 | MD-JG221E121081 | MEJA JIG PORTABLE SPOT WELDING MIDDLE SIDEWALL 3 | JAF | HAF | 23-10-2023 | RELEASED
87 | MD-JG221E121082 | JIG PORTABEL SPOT WELDING MIDDLE SIDEWALL 3 | JAF | HAF | 26-10-2023 | RELEASED
88 | MD-JG221E121091 | MEJA JIG PORTABEL SPOT WELDING BEHIND CAB SIDEWALL | APS | HAF | 26-10-2023 | RELEASED
89 | MD-JG221E121092 | JIG PORTABEL SPOT WELDING BEHIND CAB SIDEWALL | APS | HAF | 26-10-2023 | RELEASED
90 | MD-JG221E121131 | MEJA JIG PORTABEL SPOT WELDING CABIN SIDEWALL | APS | HAF | 27-10-2023 | RELEASED
91 | MD-JG221E121132 | JIG PORTABLE SPOT WELDING CABIN SIDEWALL | APS | HAF | 09-10-2023 | RELEASED
92 | MD-JG251E121011 | JIG INDIRECT SPOT ROOF FRAMING TOTAL TC1 TC2 M2 T1 T2 T3 | AEH | HAF | 09-10-2023 | RELEASED
93 | MD-JG251E121012 | JIG INDIRECT SPOT ROOF FRAMING FRONT TC1 TC2 M2 T1 T2 T3 | AEH | HAF | 09-10-2023 | RELEASED
94 | MD-JG251E121014 | SIDE BASIC JIG ROOF | AEH | HAF | 09-10-2023 | RELEASED
95 | MD-JG251E121015 | JIG ROOF ASSY - WELDING SHEETING (TC T M) | PUR | HAF | 09-10-2023 | RELEASED
96 | MD-JG200E120012 | JIG STAND CARBODY ASSY KRL KCI (T, TC, M) | APS | HAF | 27-10-2023 | RELEASED
97 | MD-JG200E120013 | JIG STAND FOR REFORMING CARBODY (TC T M) | RAP | HAF | 11-10-2023 | RELEASED
98 | MD-JG210E121022 | JIG STAND FOR REFORMING UNDERFRAME (TC T MC) | AEH | HAF | 27-10-2023 | RELEASED
99 | MD-JG211E120011 | JIG END UNDERFRAME 1 (TC T MC) | WIDYA | HAF | 11-10-2023 | RELEASED
100 | MD-JG221E120054 | JIG PORTABEL SPOT WELDING END SIDEWALL 2 | APS | HAF | 26-10-2023 | RELEASED
101 | MD-TL221E120021 | TOP CLAMP SIDEWALL CARBODY | SLV | HAF | 11-10-2023 | RELEASED
102 | MD-JG251E121016 | JIG ROOF - RAIN GUTTER,REFORMING (TC,T,M) | ADW | HAF | 26-10-2023 | RELEASED
103 | MD-TL221E120022 | TOP CLAMP 2 DOOR SIDEWALL CARBOY | SLV | HAF | 16-10-2023 | RELEASED
104 | MD-JG200E120011 | FITTING TOOL ASSY CARBODY (TC,T,M) | RAP | HAF | 18-10-2023 | RELEASED
105 | MD-JG231E120022 | JIG ENDWALL FRAME | ADW | HAF | 19-10-2023 | RELEASED
106 | MD-JG231E120021 | JIG DOOR POST ENDWALL | APS | HAF | 23-10-2023 | RELEASED
107 | MD-JG221E120051 | MEJA JIG PORTABEL SPOT WELDING END SIDEWALL | APS | HAF | 26-10-2023 | RELEASED
108 | MD-JG241E121011 | JIG DRIVER CAB | ADT | HAF | 26-10-2023 | RELEASED
109 | MD-JG251E120041 | JIG INDIRECT SPOT ROOF FRAMING AC | AEH | HAF | 26-10-2023 | RELEASED
110 | MD-JG251E120043 | JIG INDIRECT SPOT WELDING FRAME PANTOGRAPH | PUR | HAF | 30-10-2023 | RELEASED
111 | MDJG251E120041 | JIG STAND CARBODY ASSY TC, T, M (ALTERNATIF 2 CHOWEL) | ADH | HAF | 19-12-2023 | RELEASE
112 | MDTL221E121022 | BOGIE TEMPORARY SIDEWALL KRL KCI | ADH | HAF | 05-12-2023 | RELEASE
113 | MDTL251E121011 | TOOL ANGKAT ROOF | SLV | HAF | 05-12-2023 | RELEASE
114 | MDJG221E12111 | JIG DRIVER CAB ENTRANCE | YDP | HAF | 08-12-2023 | RELEASE
115 | MDJG210E121022 | JIG STAND FOR REFORMING UNDERFRAME (TC, T, MC) | RAP | HAF | 19-12-2023 | RELEASE
116 | MDJG221E120071 | JIG PASSENGER ENTRANCE (TC1,2 M1 M2 T1 T2 T3) | RAM | HAF | 19-12-2023 | RELEASE
117 | MDJG231E120022 | JIG ENDWALL FRAME | APS | HAF | 19-12-2023 | RELEASE
118 | MDJG251E121014 | SIDE BASE JIG ROOF | ADH | HAF | 19-12-2023 | RELEASE
119 | MDML671E121031 | MAL ASSY CEILING PANEL (TC, T, M) | SLV | RSA | 17-07-2024 | RELEASED
120 | MDML556E121021 | MAL CEK SUDUT DRIVER CABIN PANEL | SLV | RSA | 18-07-2024 | RELEASED
121 | MDTL673E121012 | TOOL SETTING SLOT FRAME BOLT M8 (TC,T,M) ALTERNATIF 2 | RAP | RSA | 18-07-2024 | RELEASED
122 | MDTL672E120240 | ADJUSTABLE STAND DUCTING AC ALL TYPE | RAM | RSA | 19-07-2024 | RELEASED
123 | MDJG211E120011 | JIG END UNDER FRAME 1 (TC, T, MC) | WAH | HAF | 29-12-2023 | RELEASE
124 | MDJG221E121132 | JIG PORTABEL SPOT WELDING CABIN SIDEWALL | APS | HAF | 02-11-2023 | RELEASE
125 | MDJG251E121012 | JIG INDIRECT SPOT ROOF FRAMING FRONT TC1 TC2 M2 T1 T2 T3 | AEH | HAF | 02-11-2023 | RELEASE
126 | MDJG11220381201 | JIG MINOR BRACKET MOTOR SUPPORT 1 & 2 | HAN | HAF | 02-11-2023 | RELEASE
127 | MDJG251E122011 | JIG INDIRECT SPOT ROOF FRAMING M1 | AEH | HAF | 08-11-2023 | RELEASE
128 | MDML251E120041 | MAL JIG INDIRECT FRAME AC ROOF | RAM | HAF | 10-11-2023 | RELEASE
129 | MDTL001XXX0373 | MEJA DATAR (3500 x 6000) | AEH | HAF | 14-11-2023 | RELEASE
130 | MDML200E120012 | FRAME DATUM FLOOR | WAH | RSA | 22-07-2024 | RELEASED

## Sheet2
btw persentase progress saat fase 'progressing maupun revising' harus diisi oleh drafter setiap hari
[6 empty] | DESIGN DRAWING & MANUFACTURING DRAWING | [17 empty] | hasil progress tersebut diinputkan oleh PIC ke dokumen status setiap 2 hari
JIG 16 TS KRL KCI (TB1622 & MB1122)
|  |  |  | KODE PROYEK | TB1622/MB1122 |  |  |  |  | DD JIG |  | MD JIG |  | #N/A |  | #N/A |  | #N/A
[14 empty] | #DIV/0! |  | #DIV/0! |  | #DIV/0!
|  |  |  | Total Item to Release | Revised Item | BOGIE |  |  |  | PROGRESS |  | PROGRESS
|  |  |  | 23 | 0 |  |  |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
[14 empty] | #DIV/0! |  | #DIV/0! |  | #DIV/0!
|  |  |  | Closed Item | Progressed Item
|  |  |  | 0 | 0 |  |  |  |  | CANCELLATION |  | (1) Single Part |  | (2) Minor Assy |  | (3) Sub-Assy |  | (4) Total Assy
[10 empty] | RATE | 0% | 100% |  | 100% |  | 100% |  | 100%
RUMUS
NO | Drawing No. (INPUT) | Drawing Name (INPUT) | Rev. | Drawing Number | Title |  | Grouping | Phase | Progress Scoring | Release Date |  |  |  |  | Drawing Status |  | AUTHOR INITIAL |  |  | Vault Status
[10 empty] | Rev 0 | Rev A | Rev B | Rev C | Rev D | DD | MD | DW | CK | APV | EO | ECO 1 | ECO 2 | ECO 3
1 |  |  |  | JGMB11220301001 | JIG 1 BOGIE FRAME - SETTING |  | Bogie Frame | Total Assy | #N/A | 2023-10-11 |  |  |  |  | Open | Closed | HAN | HAF | UMM
2 |  |  |  | JGMB11220301002 | JIG 2 BOGIE FRAME - FULL WELDING - ROTARY |  | Bogie Frame | Total Assy | #N/A | 2023-10-11 |  |  |  |  | Open | Closed | HAN | HAF | UMM
3 |  |  |  | JGMB11220301003 | JIG 3 BOGIE FRAME - BRACKET |  | Bogie Frame | Total Assy | #N/A | 2023-10-24 |  |  |  |  | Open | Closed | HAN | HAF | UMM
4 |  |  |  | JGTB16220310001 | JIG SIDEFRAME - MINOR WEB PLATE |  | Side Frame | Minor Assy | #N/A | 2023-10-05 |  |  |  |  | Open | Closed | YDP | HAF | UMM
5 |  |  |  | JGTB16220310002 | JIG SIDEFRAME - MINOR BOTTOM PLATE |  | Side Frame | Minor Assy | #N/A | 2023-10-05 |  |  |  |  | Open | Closed | HAN | HAF | UMM
6 |  |  | 0 | JGTB16220310003 | JIG 1 SIDEFRAME - SETTING WEB RIB |  | Side Frame | Sub-Assy | #N/A | 2023-10-10 |  |  |  |  | Open | Closed | YDP | HAF | UMM
7 |  |  | 0 | JGTB16220310004 | JIG 2 SIDEFRAME - SETTING TOP BOTTOM |  | Side Frame | Sub-Assy | #N/A | 2023-10-11 |  |  |  |  | Open | Closed | YDP | HAF | UMM
8 |  |  |  | JGTB16220310005 | JIG 3 SIDEFRAME - FULL WELD |  | Side Frame | Sub-Assy | #N/A | 2023-10-16 |  |  |  |  | Open | Closed | YDP | HAF | UMM
9 |  |  |  | MLTB16220310001 | MAL PROFILE TOP PLATE SIDEFRAME |  | Side Frame | Single Part | #N/A | 2023-10-16 |  |  |  |  | Open | Closed | YDP | HAF | UMM
10 |  |  |  | MLTB16220310002 | MAL PROFILE BOTTOM PLATE SIDEFRAME |  | Side Frame | Single Part | #N/A | 2023-10-16 |  |  |  |  | Open | Closed | YDP | HAF | UMM
11 |  |  |  | JGTB16220320001 | JIG 1 TRANSOM - SETTING |  | Cross Beam | Sub-Assy | #N/A | 2023-10-03 |  |  |  |  | Open | Closed | HAN | HAF | UMM
12 |  |  | 0 | JGTB16220320002 | JIG 2 TRANSOM - FULL WELDING |  | Cross Beam | Sub-Assy | #N/A | 2023-10-04 |  |  |  |  | Open | Closed | YDP/ BRILIAN | HAF | UMM
13 |  |  | 0 | JGMB11220381201 | JIG MINOR MOTOR SUPPORT 1 & 2 |  | Bogie Frame | Minor Assy | #N/A | 2023-10-31 |  |  |  |  | Open | Closed | HAN | HAF | UMM
14 |  |  |  | JGMB11220381202 | JIG MINOR GEARBOX SUPPORT |  | Bogie Frame | Minor Assy | #N/A | 2023-10-26 |  |  |  |  | Open | Closed | HAN | HAF | UMM
15 |  |  |  | JG999MB11220000 | RIG UJI FATIGUE BOGIE KRL KCI |  | Rig Uji Bogie | Sub-Assy | #N/A | 2023-11-27 |  |  |  |  | Open | Closed | HAN | HAF | UMM
16 |  |  |  | JG999MB11220001 | RIG UJI FATIGUE BOGIE KRL KCI |  | Rig Uji Bogie | Sub-Assy | #N/A | 2023-11-23 |  |  |  |  | Open | Closed | HAN | HAF | UMM
17 |  |  |  | JG999MB11220002 | SIDECLAMP AIR SPRING |  | Rig Uji Bogie | Minor Assy | #N/A | 2023-11-21 |  |  |  |  | Open | Closed | HAN | HAF | UMM
18 |  |  |  | JG999MB11220003 | LATERAL FORCE SUPPORT |  | Rig Uji Bogie | Single Part | #N/A | 2023-11-23 |  |  |  |  | Open | Closed | HAN | HAF | UMM
19 |  |  |  | JG999MB11220004 | LONGITUDINAL FORCE SUPPORT |  | Rig Uji Bogie | Single Part | #N/A | 2023-11-21 |  |  |  |  | Open | Closed | HAN | HAF | UMM
20 |  |  |  | JG999MB11220005 | BRAKE FORCE SUPPORT |  | Rig Uji Bogie | Single Part | #N/A | 2023-11-21 |  |  |  |  | Open | Closed | HAN | HAF | UMM
21 |  |  |  | JG999MB11220006 | STAND ACTUATOR |  | Rig Uji Bogie | Minor Assy | #N/A | 2023-11-23 |  |  |  |  | Open | Closed | HAN | HAF | UMM
22 |  |  |  | JG999MB11220007 | CONNECTOR GEARBOX |  | Rig Uji Bogie | Single Part | #N/A | 2023-11-21 |  |  |  |  | Open | Closed | YDP | HAF | UMM
23 |  |  |  | JG999MB11220008 | CONNECTOR MOTOR SUPPORT |  | Rig Uji Bogie | Minor Assy | #N/A | 2023-11-21 | 2023-11-23 |  |  |  | Open | Closed | YDP | HAF | UMM

## Sheet3
btw persentase progress saat fase 'progressing maupun revising' harus diisi oleh drafter setiap hari
[6 empty] | DESIGN DRAWING & MANUFACTURING DRAWING | [15 empty] | hasil progress tersebut diinputkan oleh PIC ke dokumen status setiap 2 hari
JIG 16 TS KRL KCI
|  |  |  | KODE PROYEK | E12 |  |  |  |  | MD JIG |  | #N/A |  | #N/A |  | #N/A
[12 empty] | #DIV/0! |  | #DIV/0! |  | #DIV/0!
|  |  |  | Total Item to Release | Revised Item | CARBODY |  |  |  | PROGRESS
|  |  |  | 50 | 0 |  |  |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
[12 empty] | #DIV/0! |  | #DIV/0! |  | #DIV/0!
|  |  |  | Closed Item | Progressed Item
|  |  |  | 0 | 0 |  |  |  |  | (1) Single Part |  | (2) Minor Assy |  | (3) Sub-Assy |  | (4) Total Assy
[10 empty] | 100% |  | 100% |  | 100% |  | 100%
RUMUS
NO | Drawing No. (INPUT) | Drawing Name (INPUT) | Rev. | Drawing Number | Title |  | Grouping | Phase | Progress Scoring | Release Date | [5 empty] | AUTHOR INITIAL |  | Vault Status
[10 empty] | Rev 0 | Rev A | Rev B | Rev C | Rev D | MD | DW | CK | EO | ECO 1 | ECO 2 | ECO 3
1 |  |  | 0 | JG200E120011 | FITTING TOOL ASSY CARBODY (TC, T, M) |  | CARBODY | Total Assy | #N/A | 2023-10-16 |  |  |  |  | Closed | RAP | HAF
2 |  |  | 0 | JG200E120012 | JIG STAND CARBODY ASSY (TC, T, M) |  | CARBODY | Total Assy | #N/A | 2023-10-10 | 2023-10-26 |  |  |  | Closed | APS/ BRILIAN | HAF
3 |  |  | 0 | JG200E120013 | JIG STAND FOR REFORMING CARBODY (TC, T, M) |  | CARBODY | Total Assy | #N/A | 2023-10-09 |  |  |  |  | Closed | RAP | HAF
4 |  |  | 0 | JG210E121021 | JIG UNDERFRAME (TC, T, MC) |  | Underframe | Sub-Assy | #N/A | 2023-09-26 | 2023-11-16 |  |  |  | Closed | RAP | HAF
5 |  |  |  | JG210E121022 | JIG STAND FOR REFORMING UNDERFRAME (TC, T, MC) |  | Underframe | Sub-Assy | #N/A | 2023-10-10 | 2023-10-26 |  |  |  | Closed | APS / OKTIAN | HAF
6 |  |  |  | JG211E120011 | JIG END UNDERFRAME 1 (TC, T, MC) |  | Underframe | Sub-Assy | #N/A | 2023-10-09 |  |  |  |  | Closed | APS / WIDYA | HAF
7 |  |  |  | JG211E121011 | JIG END UNDERFRAME 2 (UNDER MASKARA - TC) |  | Underframe | Sub-Assy | #N/A | 2023-10-05 |  |  |  |  | Closed | APS / RAP | HAF
8 |  |  |  | JG211E121021 | JIG 1 END CENTERSILL (SETTING) |  | Underframe | Sub-Assy | #N/A | 2023-11-27 |  |  |  |  | Closed | RAP | HAF
9 |  |  |  | JG211E121022 | JIG 2 END CENTERSILL (FULL WELD) |  | Underframe | Sub-Assy | #N/A | 2023-11-22 |  |  |  |  | Closed | RAM | HAF
10 |  |  |  | JG212E120011 | JIG 1 BOLSTER (TC, T, M) |  | Underframe | Sub-Assy | #N/A | 2023-09-21 |  |  |  |  | Closed | OKTIAN | HAF
11 |  |  |  | JG212E120012 | JIG 2 BOLSTER (TC, T, M) |  | Underframe | Sub-Assy | #N/A | 2023-09-21 |  |  |  |  | Closed | OKTIAN | HAF
12 |  |  |  | JG221E120031 | MEJA JIG PORTABEL SPOT WELDING MIDDLE SIDEWALL 1 & 2 |  | Side Wall | Sub-Assy | #N/A | 2023-10-04 |  |  |  |  | Closed | JAF | HAF
13 |  |  |  | JG221E120033 | JIG PORTABLE SPOT WELDING SIDEWALL 1 & 2 |  | Side Wall | Sub-Assy | #N/A | 2023-10-04 | 2023-10-21 |  |  |  | Closed | JAF | HAF
14 |  |  |  | JG221E121081 | MEJA JIG PORTABEL SPOT WELDING MIDDLE SIDEWALL 3 |  | Side Wall | Sub-Assy | #N/A | 2023-10-04 | 2023-10-21 |  |  |  | Closed | JAF | HAF
15 |  |  |  | JG221E121082 | JIG PORTABEL SPOT WELDING MIDDLE SIDEWALL 3 |  | Side Wall | Sub-Assy | #N/A | 2023-10-04 | 2023-10-24 |  |  |  | Closed | JAF | HAF
16 |  |  |  | JG221E120051 | MEJA JIG PORTABEL SPOT WELDING END SIDEWALL |  | Side Wall | Sub-Assy | #N/A | 2023-09-25 | 2023-10-24 |  |  |  | Closed | APS | HAF
17 |  |  |  | JG221E120052 | JIG PORTABEL SPOT WELDING END SIDEWALL |  | Side Wall | Sub-Assy | #N/A | 2023-10-04 | 2023-10-25 |  |  |  | Closed | APS | HAF
18 |  |  |  | JG221E120053 | MEJA JIG PORTABEL SPOT WELDING END SIDEWALL 2 |  | Side Wall | Sub-Assy | 0.9 | 2023-10-05 | 2023-10-23 |  |  |  | Closed | APS | HAF
19 |  |  |  | JG221E120054 | JIG PORTABEL SPOT WELDING END SIDEWALL 2 |  | Side Wall | Sub-Assy | 0.9 | 2023-10-09 | 2023-10-24 |  |  |  | Closed | APS | HAF
20 |  |  |  | JG221E121091 | MEJA JIG PORTABEL SPOT WELDING BEHIND CAB SIDEWALL |  | Side Wall | Sub-Assy | 0.9 | 2023-10-04 | 2023-10-26 |  |  |  | Closed | APS / JAF | HAF
21 |  |  |  | JG221E121092 | JIG PORTABEL SPOT WELDING BEHIND CAB SIDEWALL |  | Side Wall | Sub-Assy | 0.9 | 2023-10-04 | 2023-10-26 |  |  |  | Closed | APS / JAF | HAF
22 |  |  |  | JG221E121131 | MEJA JIG PORTABEL SPOT WELDING CABIN SIDEWALL |  | Side Wall | Sub-Assy | #N/A | 2023-10-09 | 2023-10-26 |  |  |  | Closed | APS / JAF | HAF
23 |  |  |  | JG221E121132 | JIG PORTABEL SPOT WELDING CABIN SIDEWALL |  | Side Wall | Sub-Assy | #N/A | 2023-10-05 | 2023-10-31 |  |  |  | Closed | APS / JAF | HAF
24 |  |  |  | JG221E120032 | STAND MEJA JIG PORTABLE SPOT WELDING SIDEWALL |  | Side Wall | Minor Assy | #N/A | 2023-09-21 |  |  |  |  | Closed | JAF | HAF
25 |  |  |  | JG231E120021 | JIG FRAME DOOR POST END WALL |  | End Wall / Mask | Sub-Assy | #N/A | 2023-10-21 |  |  |  |  | Closed | ADW / APS | HAF
26 |  |  |  | JG231E120022 | JIG FRAME ENDWALL |  | End Wall / Mask | Sub-Assy | #N/A | 2023-10-19 |  |  |  |  | Closed | ADW / APS | HAF
27 |  |  |  | ML231E120011 | MAL ARCH RAIL TOP BEAM OF END WALL |  | End Wall / Mask | Single Part | #N/A | 2023-11-02 |  |  |  |  | Closed | RAM | HAF
28 |  |  |  | JG241E121011 | JIG DRIVER CAB |  | End Wall / Mask | Sub-Assy | #N/A | 2023-10-26 |  |  |  |  | Closed | ADT | HAF
29 |  |  |  | JG251E120041 | JIG INDIRECT SPOT WELDING FRAME AC ROOF |  | Roof | Sub-Assy | #N/A | 2023-10-26 |  |  |  |  | Closed | YDP / AEH | HAF
30 |  |  |  | JG251E120043 | JIG INDIRECT SPOT WELDING FRAME PANTOGRAPH |  | Roof | Sub-Assy | #N/A | 2023-10-27 |  |  |  |  | Closed | PUR | HAF
31 |  |  |  | JG251E121011 | JIG INDIRECT SPOT ROOF FRAMING TOTAL TC1 TC2 M2 T1 T2 T3 |  | Roof | Sub-Assy | #N/A | 2023-10-04 | 2023-11-03 |  |  |  | Closed | YDP/ AEH | HAF
32 |  |  |  | JG251E121012 | JIG INDIRECT SPOT ROOF FRAMING FRONT TC1 TC2 M2 T1 T2 T3 |  | Roof | Sub-Assy | #N/A | 2023-10-04 | 2023-10-31 | 2023-11-24 |  |  | Closed | YDP / AEH / OKTIAN | HAF
33 |  |  |  | JG251E121013 | JIG INDIRECT SPOT ROOF FRAMING REAR TC1 TC2 M2 T1 T2 T3 |  | Roof | Sub-Assy | #N/A | 2023-09-27 | 2023-10-27 | 2023-11-24 |  |  | Closed | AEH | HAF
34 |  |  |  | JG251E121014 | SIDE BASE JIG ROOF |  | Roof | Sub-Assy | #N/A | 2023-09-26 |  |  |  |  | Closed | AEH | HAF
35 |  |  |  | JG251E121015 | JIG ROOF ASSY - WELDING SHEETING (TC, T, M) |  | Roof | Sub-Assy | #N/A | 2023-10-05 |  |  |  |  | Closed | PUR | HAF
36 |  |  |  | JG251E121016 | JIG ROOF ASSY - RAIN GUTTER/REFORMING (TC, T, M) |  | Roof | Sub-Assy | #N/A | 2023-10-11 | 2023-10-25 |  |  |  | Closed | PUR | HAF
37 |  |  |  | JG251E122011 | JIG INDIRECT SPOT ROOF FRAMING M1 |  | Roof | Sub-Assy | #N/A | 2023-11-08 |  |  |  |  | Closed | AEH | HAF
38 |  |  |  | ML251E121013 | MAL SEAM WELDING ROOF SHEETING |  | Roof | Single Part | #N/A | 2023-10-30 |  |  |  |  | Closed | REA | HAF
39 |  |  |  | ML251E121015 | MAL SINGLE PART ROOF |  | Roof | Single Part | #N/A | 2023-11-02 |  |  |  |  | Closed | REA | HAF
40 |  |  |  | ML251E120041 | MAL JIG INDIRECT SPOT WELDING ROOF |  | Roof | Single Part | #N/A | 2023-11-10 |  |  |  |  | Closed | RAM | HAF
41 |  |  |  | TL221E120021 | TOP CLAMP SIDEWALL CARBODY |  | Roof | Minor Assy | #N/A | 2023-10-10 |  |  |  |  | Closed | SLV | HAF
42 |  |  |  | TL221E120022 | TOP CLAMP 2 SIDEWALL CARBODY |  | Roof | Minor Assy | #N/A | 2023-10-12 |  |  |  |  | Closed | SLV | HAF
43 |  |  |  | TL001XXX0112 | STAND ROTARY BOLSTER TURUN ULANG |  | Underframe | Minor Assy | #N/A | 2023-11-09 |  |  |  |  | Closed | SLV | HAF
44 |  |  |  | TL001XXX0126 | STAND ROTARY BOLSTER TANPA MOTOR TURUN ULANG |  | Underframe | Minor Assy | #N/A | 2023-11-09 |  |  |  |  | Closed | SLV | HAF
45 |  |  |  | TL001XXX0108 | ALAT UKUR DIMENSI KERETA TURUN ULANG |  | CARBODY | Minor Assy | #N/A | 2023-11-09 |  |  |  |  | Closed | SLV | HAF
46 |  |  |  | TL001XXX0373 | MEJA DATAR 3500 X 6000 TURUN ULANG |  | Underframe | Minor Assy | #N/A | 2023-11-10 |  |  |  |  | Closed | AEH | HAF
47 |  |  |  | TL001XXX0375 | MEJA PENYAMBUNGAN SIDEWALL ( ALTERNATIF 2 ) TURUN ULANG |  | Underframe | Minor Assy | #N/A | 2023-11-21 |  |  |  |  | Closed | AEH | HAF
48 |  |  |  | TL251E121012 | ALAT TEMPORARY HANDLING ROOF |  | Roof | Minor Assy | #N/A | 2023-11-23 |  |  |  |  | Closed | AEH | HAF
49 |  |  |  | JG251G130012 | SUPPORT CLAMP CARLINE JIG ROOF TURUN ULANG |  | Roof | Minor Assy | #N/A | 2023-11-23 |  |  |  |  | Closed | AEH | HAF
50 |  |  |  | TL251G133012 | TURN BUCKLE ROOF TURUN ULANG |  | Roof | Minor Assy | #N/A | 2023-11-23 |  |  |  |  | Closed | AEH | HAF
51 |  |  |  | TL200G141012 | TOOL STAND ROOF TURUN ULANG |  | Roof | Minor Assy | #N/A | 2023-11-23 |  |  |  |  | Closed | SLV | HAF
52
53
54
55
|  |  |  | TL251E121011 | TOOL ANGKAT ROOF | [10 empty] | SLV
|  |  |  | TL221E121021 | PUNCH DIES SIDEWALL SHEETING
|  |  |  | ML221E121021 | MAL GUSSET SIDEWALL
|  |  |  | TL231E120011 | PUNCH DIES CARLINE ENDWALL
|  |  |  | ML251E121014 | MAL BIDDING ROOF
|  |  |  | JG255E121011 | FITTING JIG CEILING FRAME
|  |  |  | JG255E121012 | JIG CEILING SUPPORT
|  |  |  | TL200E120011 | SUPPORT LIFTING
|  |  |  | JG251E120042 | JIG MINOR ASSY FRAME OF AIR CONDITIONER
|  |  |  | TL221E121022 | BOGIE TEMPORARY SIDEWALL KRL KCI | [10 empty] | AEH